## WC Infrastructure Pipeline
Western Cape Infrastructure Project Pipeline
No. | Project Lead / Owner | Public / Private sector | location | Sector | Jurisdiction | Timeline | Project name | Project description | Estimated Total Project Value
PROJECTS SCORED
1. | Department of Infrastructure | Public Sector / Provincial Government | Cape Town | Social | City of Cape Town |  | IAM: Leeuloop Precinct Development | • Located in Cape Town CBD’s Heritage Protection Overlay Zoned Mixed Use (MU3). • Site currently used for office/storage and parking. • WCG-owned land (Erf 172814), 2881m2, Title T57893/2012. • No objections received from government departments or public notices regarding disposal. | Approximate value: R918 million
2. | Department of Infrastructure | Public Sector / Provincial Government | Cape Town | Social | City of Cape Town |  | IAM: Founders Garden Artscape | The Western Cape Government will develop the Founders Garden site in Cape Town into a high-rise, mixed-use development prioritising social housing. The project will feature over 2,000 residential units, with nearly half dedicated to social housing. Retail, commercial spaces, and public amenities like an Early Childhood Development Centre which will support the community. The development aims to maximise social housing while promoting sustainable urban growth. | Approximate value:R2,256 billion
3. | Department of Infrastructure | Public Sector / Provincial Government | Cape Town | Social | City of Cape Town |  | IAM: Oude Molen Precinct | The Oude Molen Precinct redevelopment aims to create a sustainable, mixed-use development based on live-work-play principles and transit-oriented development (TOD). Covering 13.15 hectares, the project will deliver 1,364 residential units (34% affordable), alongside commercial, educational, and retail spaces. The initiative integrates heritage preservation and environmental sustainability, enhancing access to housing and jobs while aligning with Cape Town’s socio-economic development goals. | Approximate value:R2,356 billion
4. | Department of Infrastructure | Public Sector / Provincial Government | Cape Town | Economic | City of Cape Town |  | IAM: Provincial Pavement Testing Laboratory (PPTL) | The project is nearing the completion of the site enablement process. All statutory applications (Heritage & Land Use Management) have been approved and the rights are in place, following the required public and stakeholder engagement. It is a mixed-use housing development. | Approximate value: R356 million
5. | Department of Infrastructure | Public Sector / Provincial Government | Stikland | Social | City of Cape Town |  | IAM: Stikland Mixed Housing | Mixed use housing | Approximate value:R10 billion
6. | Department of Infrastructure | Public Sector / Provincial Government | Cape Town (Northern Suburbs) | Economic | City of Cape Town |  | Roads: Wingfield Interchange project | A rapid rise in Cape Town’s urban population has led to an increase in travel demand, resulting in high congestion levels across some of the major routes in the City (City of Cape Town, 2017). This high level of congestion is undesirable as it imposes large direct costs on the road user and the economy through delays and reduction in traffic flow. Providing holistic and sustainable urban transportation solutions to reduce congestion has thus become critical. The Western Cape Government’s Department of Infrastructure formulated a strategic infrastructure project, called the Cape Town Freeway Integrator (CTFI), to integrate major routes in the city with the aim of improving mobility, unlocking growth potential and accelerating development. The Southern Growth Corridor, commonly known as “The Wingfield Interchange Project”, is one of the first mega-infrastructure projects that forms part of the CTFI. | Approximate value: R11 billion
7. | Department of Infrastructure | Public Sector / Provincial Government | Cape Town (Northern Suburbs) | Economic | City of Cape Town |  | Roads: Cape Town Integrator R300 Ring Road | The extension of the R300 to the north is one of the phases that will ultimately create a ring road around the Cape Metro. This phase is focused on the section between De Bron Rd as the southern limit and Wellington Rd as the northern Limit. The SANRAL is responsible for the section between Stellenberg Interchange on the N1 up to the De Bron Rd limit. This phase will be constructed as a 6-lane freeway with crossing structures at De Bron Rd, Legato Dr, Amadeus Dr and Wellington Road. | Approximate value:R1,27 billion
8. | Department of Infrastructure | Public Sector / Provincial Government | Worcester | Social | Breede Valley Municipality |  | HS: Transhex Housing Development (Alternative Energy) | Transhex Catalytic Housing Project is located on the south eastern periphery of Worcester along the R60 heading toward Robertson. Transhex Catalytic Housing Project will eventually add 381.57ha of land to Worcester. Transhex Catalytic Housing Project will provide the following land uses: Residential (BNG) Social Housing Education (ECD, Pre primary, Primary & Secondary Schools) Public Open Space (including Sports fields) Commercial/ Business Project 3254 Transhex Catalytic Housing Development has been identified by the National Department of Human Settlements as a Catalytic Project. Through this project the Department, in collaboration with the Breede Valley Municipality, intends to deliver 8 218 new housing opportunities in Worcester The Transhex Project is currently being implemented in 3 Main Phases 1 2 3 PHASE 1: 2546 serviced sites are completed together with the associated Upgrade of the R60 and installation of a Storm water canal for the total of R 345,659,542.10 SUB PHASE 1.1 : 190 ABT Top structures completed for the total of R 43 335 893,79. SUB PHASES 1.2 TO 1.5 : 1 229 Top structures is currently in the Procurement Phase and a contractor is expected to be appointed during October 2025, Estimation: R300m. | Approximate value: R845,5 million
9 | Department of Infrastructure | Public Sector / Provincial Government | Sanddrift | Social | City of Cape Town |  | HS: Sanddrift Mixed Housing Development | Mixed use housing | Approximate value: R10 billion
10 | Department of Environmental Affairs and Development Planning | Public Sector / Provincial Government | Across the Western Cape | Ecological | Across the Western Cape |  | Ecological Infrastructure Investment within Strategic watersource areas of the Western Cape | The project forms part of the Western Cape Ecological InfrastructurecInvestment Framework, which sets out to improve human wellbeing in the province by investing in ecological infrastructure associated with improved water security, reduced flood and fire risk, and improved agricultural yield. Investment in ecological infrastructure leverages many benefits, often with real commercial value, which contributes meaningfully to the Sustainable Development Goals and other national and provincial objectives. | Approximate value: R3 billion
11 | Department of Environmental Affairs and Development Planning | Public Sector / Provincial Government | Across the Western Cape | Ecological | Across the Western Cape |  | Provincial Public-sector Strategic Offset Bank Project values to be determined after completion of feasibility. | The proposed Provincial Strategic Offset Bank aims to proactively conserve ecosystems impacted by public sector developments. This initiative will streamline the offsetting processes, reducing costs and project delays while enhancing conservation outcomes. By consolidating offset requirements into larger, strategically placed offsets, the approach improves biodiversity protection and reduces long-term management costs. The project addresses inefficiencies in current ad-hoc offsetting methods, which are costly and often yield limited conservation value. A market size and demand analysis will be conducted in collaboration with key Western Cape Government Departments to inform implementation. | To be determined
12 | Deparment of Economic Development and Tourism | Public Sector / Provincial Government | Saldanha | Economic | Saldanha Municipality West Coast District Municipality |  | Saldanha Port Development including possible green energy (Marine Infrastructure Mega Projects) | Harbour and Tourism Infrastructure | Approximate value:R8,4 billion
13 | Overberg District Municipality | Public Sector / Local Government | Overberg | Social | Overberg |  | Karwyderskraal Waste Facility | The Karwyderskraal Regional Landfill Facility is an existing landfill site owned and managed by the Overberg District Municipality since March 2000. It serves the waste disposal requirements for the municipalities of Theewaterskloof, Overstrand and Cape Agulhas. The site currently comprises four cells, of which the first cell, Cell 1, was completed towards the end of 2001. Subsequently, construction of Cell 2 was completed in April 2005, Cell 3 in February 2015 and Cell 4 in April 2019, with Cell 4 projected to reach its capacity by October 2026. This new phase of the project entails the construction of a new disposable cell, Cell 5A, the development of an organic waste diversion facility, the extension of the composting area, and the extension of the entrance road. | Approximate value: R80,194 million
14 | Overberg District Municipality | Public Sector / Local Government | Overberg | Economic and Water | Overberg / Western Cape/ Natonal |  | Overberg Dam - Potential Water security project in the Overberg | The Overberg Dam is a proposed catalytic infrastructure project in the Breede River, covering an area of approximately 123 million m3. Positioned as part of the Western Cape Infrastructure Project Pipeline, the dam seeks to enhance long-term water security while driving economic growth, agricultural expansion, job creation, and regional resilience. Aligned with provincial, national, and Joint District and Metro Approach (JDMA) priorities, the project will unlock new opportunities in tourism, exports, green energy, logistics and sustainable development. The project also promotes the Western Cape Infrastructure 2050 (WCIF 2050) principles as it harnesses infrastructure innovation to drive equitable economic growth, regenerative ecosystems and spatial justice. | To be determined by Feasibility study
15 | Deparment of Economic Development and Tourism with various stakeholders | Public Sector / Provincial Government | West Coast, Saldanha | Technology | Across the Western Cape |  | Creation of a regulatory sandbox to position the Western Cape as a Global Hub for Drone Innovation. | The Western Cape Government is developing a Regulatory Sandbox for Drones and UAVs to position the province as a global hub for drone innovation. The Sandbox provides a controlled, real-world environment to test emerging technologies, support adaptive regulation, and catalyse commercial applications. Aligned with the Western Cape Infrastructure Framework 2050 and the Growth for Jobs Strategy, the project supports the growth of inclusive value chains across logistics, agriculture, inspection and public services. Viable test sites have been identified, with a phased approach enabling scalable operations from VLOS to BVLOS and UTM integration. The Sandbox also supports STEM education, job creation and investment attraction. | Phase 1 Approximate value: R2,1 million
16 | Deparment of Economic Development and Tourism with various stakeholders | Public Sector / Provincial Government | West Coast, Saldanha | Economic | Saldanha |  | Small harbours redevelopment: Saldanha Bay | The proposal outlines Phase 1 of the development of the Saldanha Bay Small Harbour, prepared jointly by the Saldanha Bay Municipality (SBM) and the Department of Economic Development and Tourism (DEDAT), aimed at improving harbour operations, infrastructure, and economic activity. It recommends that custodianship of the harbour be partially delegated to SBM via a long-term lease from the Department of Public Works and Infrastructure (DPW&I). The development is proposed in phases, starting with securing a long-term lease for Sea Harvest, upgrading and outsourcing operations of the slipway, and pursuing further property leases and redevelopment of Pepper Bay for tourism and commercial activity. | To be determined
17 | Deparment of Economic Development and Tourism with various stakeholders | Public Sector / Provincial Government | Cross border between Namibia and South Africa, West Coast, Saldanha | Water and Energy | Saldanha |  | Western Cape Green Hydrogen pipeline | The development of cross-border Hydrogen Infrastructure between Namibia and South Africa through the establishment of a large-scale green hydrogen pipeline network involving three key Hydrogen hubs – Lüderitz, Boegoebaai/Prieska, and Saldanha Bay – each demonstrating different levels of readiness and development potential. A phased approach is proposed for this project, beginning with hub development (Phase 0), followed by connecting the hubs via a pipeline (Phase 1), and ultimately expanding to inland industrial centres like Gauteng (Phase 2). A coordinated, inclusive, and phased implementation plan is recommended to ensure the project’s long-term success. | Approximate value:: R53,135 billion
18 | Deparment of Economic Development and Tourism | Public Sector / Provincial Government | Garden Route | Economic | George |  | George Convention Centre | Project proposal by the Western Cape Department of Economic Development and Tourism (DEDAT) to commission a feasibility study and business case for developing a convention centre in George, aimed at growing the Meetings, Incentives, Conferences, and Exhibitions (MICE) sector in the Garden Route region. Despite strong tourism in the area, there is a lack of facilities that can host large-scale events (over 500 to 1500+ attendees). The George Local Municipality has identified municipally owned land for the proposed centre and requested provincial support. | Approximate value:: R2,3 billion
19 | Deparment of Economic Development and Tourism | Public Sector / Provincial Government | West Coast, Danger Bay | Water and Energy | Saldanha Municipallity |  | Water Desalination Project | The West Coast District Municipality (WCDM), facing near-capacity extraction from existing water sources, initiated the Saldanha Seawater Reverse Osmosis (SWRO) Desalination Plant project to secure sustainable water supply for the region’s 22 towns and 876 farms. Following an extensive study started in 2007, a 25.5 megalitre per day (ML/d) SWRO desalination facility in the Saldanha Bay area was selected as the most viable solution. The proposed plant, located at Danger Bay near Saldanha, will use advanced reverse osmosis technology to convert seawater into potable water meeting WHO drinking standards. With a final production capacity of 25.5 ML/d, the plant will intake approximately 60 ML/d of seawater and discharge around 36 ML/d of brine back to the sea. The facility will be built in three 8.5 ML/d phases, targeting full capacity by 2026. All core infrastructure will be sized for the ultimate capacity during initial construction to optimize long-term costs and scalability. Key features of the concept design include a highly redundant and flexible plant layout with two parallel treatment trains to ensure operational resilience. Major components cover seawater intake, pre-treatment (including dissolved air flotation and membrane filtration), the reverse osmosis process, chemical dosing, and brine disposal. Intake and outfall infrastructure options considered include micro-tunneling and horizontal directional drilling to minimize environmental and coastal impacts. The design philosophy prioritizes whole-of-life cost optimization, environmental sustainability, and adaptability to evolving water treatment technologies. Detailed pilot testing by WorleyParsons and CSIR provided the critical seawater quality data informing design parameters. With a planned operational lifespan of at least 25 years, the plant will directly connect to WCDM’s Besaansklip Reservoirs via new dedicated pipelines, strengthening the region's water security. The next project phase includes finalising detailed design and procurement, | Approximate value: R5 million
20 | Department of Cultural Affairs and Sport | Public Sector / Provincial Government | Cape town | Social | City of Cape Town |  | Provincial Archives Project | The Provincial Archives Project is a six-phased construction-ready infrastructure investment to expand the Western Cape Archives and Records Service (WCARS). With over 57,000 linear meters of backlog, the WCARS has reached full capacity, risking legal non-compliance and fragmented governance. Phase 1 is valued at R328.7 million. It includes a purpose-built archival facility featuring high-density shelving, cold storage and digital infrastructure. The project strengthens transparency, improves service delivery and ensures the long-term preservation of public records across the Western Cape Government. | Approximate value: R1,225 billion
21 | Department of Cultural Affairs and Sport | Public Sector / Provincial Government | Phillipi | Social | City of Cape Town |  | Phillipi Stadium Upgrade | Built over 40 years ago, the Philippi Stadium is located in one of Cape Town’s most socio-economically strained areas, the stadium presents an urgent yet catalytic opportunity for the Western Cape Government to reassert its commitment to infrastructure equity, youth empowerment, public safety, and community revitalisation. Extensive vandalism since 2021 has stripped the facility of all services, including plumbing, electrical and security. Structural engineers have declared both the East and West stands as unsafe for public access. The upgrade to the stadium consists of three phases that outline the critical need for interim functional recovery, comprehensive structural rehabilitation and long-term compliance with the Safety at Sports and Recreational Events Act (SASREA). | Approximate value:R40 million
22 | Deparment of Infrastructure | Public Sector / Provincial Government | George | Economic | George Municipality |  | Roads: George Western Bypass | The project consists of a new 13km long greenfields road that will act as bypass to west of George by connecting the N2 to the Outeniqua Pass (N9/N12). The bypass will deliver a much-needed improvement to George's transport infrastructure and will relieve the congested transport corridors within George. The bypass will deliver considerable economic and social benefits to George, which will flow from reduced transport costs, fewer accidents, improved residential and commercial amenity on the outskirts of George and in the CBD with improved air quality and less road traffic noise. | Approximate value: R1,1 billion
23 | Deparment of Health and Wellness | Public Sector / Provincial Government | Elsies River | Social | City of Cape Town |  | Elisies River Community Health Centre part of a bigger portfolo of projects | The new Elsies River CHC is intended to incorporate the WCGHW services of the existing CHC as well as City of Cape Town’s smaller clinics of Elsies River Clinic & Adriaanse Clinic. PROPOSED NEW FACIILITY: New Community Health Centre to serve population of 90,000 Primary Health Care component 07h00 -16h00 Mon - Fri Emergency Centre and Midwife Obstetric Unit: 24/7 Portion of X-ray Unit will be operational after-hours to serve EC and MOU | Approximate value: R338million
24 | Deparment of Health and Wellness | Public Sector / Provincial Government | Valkenburg | Social | City of Cape Town |  | Valkenberg Hospital Forensic Precinct Project | The hospital is currently located on ‘two sites” divided by a highway (M5) and the Liesbeeck River. The Forensic High Security Ward (Ward 20) is situated on the Valkenberg East side and the rest of the hospital (including all support services/facilities) is located on the Valkenberg West side. The plan for the proposed upgrade rationalises the hospital onto the Valkenberg West side. The Forensic Mental Health Service (FMHS) provides a multi-disciplinary approach for the assessment of defendants referred by the courts, and treatment and rehabilitation of forensic patients. Teaching, training and academic research activities are integral to this service provision. | Approximate valude: R1,3 billion part of bigger Revitalisation project
25 | Deparment of Health and Wellness | Public Sector / Provincial Government | Paarl | Social | Drakenstein Municipality |  | Paarl CDC part of a bigger portfolo of projects | The new Paarl CDC is proposed on a vacant plot that forms part of the Dal Josafat planned low cost housing development located on the North of Fairyland, Groenheuwel & South East Mbekweni. The new Paarl CDC will consolidate the services of the existing Mbekweni CDC, Phola Park clinic and Dalevale Clinic. | Approximate value part of a bigger portfolo of Rural PHC projects: R1,1 billion
26 | Deparment of Health and Wellness | Public Sector / Provincial Government | Malmesbury | Social | Swartland Municipality |  | Swartland District Hospital | New & Replacement Asset Facility Type: New 150 bed District Hospital (Level 1 service with limited Level 2) | Approximate value: R1,2 billion
27 | Deparment of Health and Wellness | Public Sector / Provincial Government | Groote Schuur | Social | City of Cape Town |  | Groote Schuur Hospital - Electrical System Upgrade – Replace 11kV Switchgear part of a bigger portfolo of projects | The purpose of the medium voltage network upgrade portion of the project is for the upgrading and replacement of the existing oil insulated 11kV switchgear in the main and secondary substations with new SF6 and air insulated switchgear with associated accessories. Aging transformers, as identified, will also be replaced with new units and transformers inside buildings will be replaced with dry-type transformers eliminating the risk of fire caused by oil-filled transformers under fault conditions. The scope of the project has limited remote monitoring, control and automation. SCADA will be provided for the Main HV substation (interface with City of Cape Town) with a local control panel. A new fibre optic cable network will be installed for unit protection purposes only, replacing the current copper pilot wire system. All the equipment will be supplied to enable remote monitoring, control and automation in the future | Approximate value a bigger portfolo of projects in terms of backlog maintenance: R2,2 billion
28 | Deparment of Health and Wellness | Public Sector / Provincial Government | Green Point | Social | City of Cape Town |  | New Somerset hospital – r, r n R baclog maintenance | The project at NSH is for urgent weatherproofing, structural repairs and fire safety to selected building at NSH. The intent of the project is to mitigate Health and Safety Risks to patients. Applicable buildings are North Block, West Block ,Shipley, Louis Blumberg, Medical Waste & Laundry & Charles Murray. The project is also aimed at increasing the longevity of this facility. | Approximate value: R396 million
29 | Deparment of Health and Wellness | Public Sector / Provincial Government | Green Point | Social | City of Cape Town |  | New Somerset Hospital - Fire Compliance part of a bigger portfolo of projects | New Somerset Hospital is part of a series of fire compliance projects as part of an overall strategy. New Somerset Hospital is one of SA’s oldest public hospitals. Fire compliance is critical to protecting its occupants and preserving its legacy. | Apprroximate value for bigger portfolo of projects of various firecompliance of various WCDHW facilities : R575 millon
30 | Deparment of Agricutlure | Public Sector / Provincial Government | Elsenburg, Stellenbosch | Social | Stellenbosch Municipality |  | Elsenberg College Hostel upgrading and expansion | Elsenberg College Hostel upgrading and expansion | To be determined
31 | Deparment of Agricutlure | Public Sector / Provincial Government | Across the Western Cape | Economic and Social | Western Cape |  | Upgrading and Expansion of Agri-processing facilities | Upgrading and Expansion of Agri-processing facilities including Mobile units. | Approximate value: R11,2 million
32 | Deparment of Agricutlure | Public Sector / Provincial Government | Olifants Doring | Ecological | Cederberg Municipality |  | Oliifants Doring Ecological Infrastructure Project | Ecological Infrastructure projects focussing on West Coast area. | Appoximate value: R47,106million
33 | Mobility Department | Public Sector / Provincial Government | Cape Town | Social & technology infrastructure | City of Cape Town |  | Shayela Smart | Suite of minibus taxi (MBT) improvement and transformation interventions. Shayela Smart is a joint initiative between WCG, CoCT and SANTACO WC to incrementally improve, integrate and formalise MBT services over the long-term, strengthen regulation and address key industry issues. | Approximatevalue: R1,160 billion over 4 financial years
34 | Mobility Department | Public Sector / Provincial Government | George | Social & technology infrastructure | George Municipality |  | George Intergrated Public Transport Network (GIPTN) | GO GEORGE provides a safe, reliable, affordable and accessible quality bus service to the residents of George.​ The current focus is completing the roll out of Phase 4A routes and rolling out Phases 5 and 6. This requires focussed efforts to improve infrastructure facilities to support the expanded service | Approximatevalue: R818 million over 3 financial years
35 | Mobility Department | Public Sector / Provincial Government | Stellenbosch | Social | Stellenbosch Municipality and City of Cape Town |  | Park and Ride | The Department completed a pre-feasibility study of Park and Rides (P&R) to support long-term decongestion, focusing on pilot option Stellenbosch and City of Cape Town | Approximate Ivalue; ~R215m over 3 years, to roll out one new route per year with parking facilities.
36 | Mobility Department | Public Sector / Provincial Government | Across the Western Cape | Economic | Across the Western Cape |  | Freight Rail Support Framework | A terminal network is needed to drive integration and support rail viability, i.e., rail supporting infrastructure​ Potential for WCMD, DOI (& municipalities) to provide land for facility/terminal development and collaborate with private sector to fund and develop the terminals​ | To be determined
37 | Mobility Department | Public Sector / Provincial Government | Hermanus | Social infrastructure | Overstrand Muncipality |  | NMT Demonstration Town | The NMT Demonstration Town aims to test NMT improvement measures and create a model for a safe, high-quality, comprehensive NMT network that can be replicated across the province. Pilot in Hermanus. To be determined in Business Case (December 2025) | Approximate value: R266 million
38 | Mobility Department | Public Sector / Provincial Government | Beaufort West | Social | Beaufort West Municipality |  | Rural Intertown Transport Solution | Construction of stops, shelters and PTIs where required​ The Department is investigating a Rural Intertown Transport Solution to provide safe, reliable and affordable transport between towns in rural areas to improve access to economic opportunities and essential services.​ To be determined in Business Cases (December 2025) | Approximate value: R33.1miillion
39 | Cape Winelands Airport Company | Private Sector | Fisante Kraal Airfield | Economic | City of Cape Town Cape Winelands |  | Cape Winelands Airport | The Cape Winelands Airport plan delineates a strategic vision for the airport’s evolution from a modest airfield to an influential commercial and aviation centre. The blueprint underscores the airport’s ambitious goal to emerge as a global leader in sustainability, technology, and growth rates. More than just an aviation hub, the strategy emphasizes the airport’s potential as an engine for regional economic development and local community inclusion. Located in the iconic city of Cape Town, a destination celebrated by global and local travellers alike, Cape Winelands Airport is poised to harness unparalleled opportunities. Its strategic importance transcends tourism, aligning with Cape Town’s thriving business landscape. The core goal is to establish a cohesive link with Cape Town, fostering a partnership that mutually benefits both the city and the airport. (Subject to regulatory approval) The airport’s transformation will include the development of key airport infrastructure such as; New terminal building, Cargo processing facility,New hangarage, Fuelling facilities, Hotel accommodation for passengers and flight students Heliport,Warehousing and logistics facilities.The combination of transport linkages and commercial activity can galvanise demand for light-industrial facilities such as logistics, warehousing and even air freight (depending on sufficient flight connectivity). Each of these activities generates non-aeronautical revenue that can support the development of the airport and create a diversified business. | Approximate value: Phase 1" R10 billion
40 | Private Sector | Private Sector | Paardevlei | Social | City of Cape Town |  | Somerset Bay | Mixed use housing in Paardevlei | To be determined
41 | Deparment of Infrastructure | Public | Pacaltsdorp | Social | George |  | Erf 325 Pacaltsdorp (Syferfontein) | Mixed use housing Development The planning and Implementation of 6500 units in Erf 325 West, Syferfontein, George Erf 325 West is situated West of Beach Road directly South of Delville Park with primary access off Olympic Street. Erf 325 West comprises vast tracks of environmentally sensitive areas, riverines and wetlands. The developable portions of Erf 325 West is divided into four distinct portions as depicted in the draft layout plan. A large portion of land is earmarked for rehabilitation and development for recreational, sport fields and possibly light industry to further support the beneficiary community. portions of the Remainder of Erf 325, Pacaltsdorp, which forms part of the Commonage of Pacaltsdorp. This development is ideally suited in terms of accessibility to work and facilities in the town and within the urban area of George. The area is approximately 191 hectares and the land is owned by George Municipality. | Approximate: R 2 billion
42 | Deparment of Infrastructure | Public | Welmoed | Social | City of Cape Town |  | Welmoed (Penhill) | Mixed used Housing Development: To transform areas of informality on designated sites in the Corridor into urban neighbourhoods, where dignity of persons is sustained & quality of life is improved. The Welmoed Project is located 40 km, East from the City Centre adjacent to the Van Riebeek Road | R 1,423,131,469.86
43 | Grabouw Development Agency | Private Sector | Grabouw | Economic | Theewaterskloof Municipality |  | Industrial Park | Open property alongside the N2 Farm RE/5/313 (22.72 hectare. Types of potential clients Light industrial and manufacturing Retail, Transport, Chemical (Petrol station),Fruit juice, Fruit market, Fruit storage / cold rooms Inland harbor, Incubator Hub. | To be determined by Feasibility study
44 | Grabouw Development Agency | Private Sector | Grabouw | Social and Economic | Theewaterskloof Municipality |  | Elgin City | Elgin City is an extremely ambitious project that will completely change the fortunes of Grabouw if implemented. The high-level plan is to build 2 700 upmarket houses on a 70-hectare property. Elgin City is an extremely ambitious project that will completely change the fortunes of Grabouw if implemented. The high level plan is to build 2 700 upmarket houses on a 70 hectare property. Since the Covid pandemic many people still work from home and would much prefer a country living environment for their families. This property is ideal as it is close to bulk infrastructure and will significantly boost tax levies for the municipality. The GDA is currently sourcing developers to enable this projects that will massively boost tax revenue to the TWK municipality. Impact This project has the potential to transform the area into a high income housing estate that will create hundreds of jobs during the construction phase and many more once the estate is up and running. Location Farm Nr: RE/80/319 and RE/44/319 Area (Ha): 56.63 and 12.46 | To be determined
45 | Grabouw Development Agency | Private Sector | Grabouw | Economic | Theewaterskloof Municipality |  | ⁠⁠Park of Unity | Public works own the land between the Grabouw police station and the Padstal. On this land is the waste water facility as well as the solid waste collection point. The property is more than 1 300 hectares. The main entrance to town is adjacent to this property and hence it has the potential to set the scene for anyone arriving in town. This property was historically earmarked for low cost housing or a cemetery. However, this property is ideally located to create a space that will attract tourists and a safe space for Grabouw residents. It is proposed the waste water outflow be used for a variety of irrigation projects so that the land can be transformed in either a park of unity or a fynbos golf course. It is crucial that this property be developed in a nurturing way in order to inlock project number 14 that is adjacent to this property but on the other side of the Palmiet river. Impact. A park of unity / golf course will set Grabouw aside from other towns in the area. If done correctly it will also unlock project 12, a project aimed at transforming the tax base of Grabouw. Location Erf Nr: 4233 Area (Sqm): 1321658.9 | To be determined
46 | Swartland Municipality | Public | Chatsworth | Energy & Water Infrastructure | Swartland Municipality | 3 years (Short term) | Chatworth Bulk Water Upgrades and new 5ML Reservoir | Due to population growth and a planned affordable housing project at Chatsworth/Riverlands, the bulkwater supply system to Chatsworth and surrounding areas has to be upgraded. The Chatsworth/Riverlands development is located in the southernmost part of Swartland Municipality, bordering the City of Cape Town. These areas are currently supplied with potable water from the Kleindam Reservoirs in Malmesbury, which form part of the greater Swartland Bulk Water Distribution System. This system sources raw water from the Voëlvlei Dam, which is treated at the Voëlvlei Water Treatment Works (WTW) and distributed via a network of pumped bulk pipelines to towns across the municipality. This upgrade will significantly alleviate pressure on the existing Swartland system and ensure long-term water security for the southern settlements of the municipality. | 54500000
47 | Swartland Municipality | Public | Darling | Energy & Water Infrastructure | Swartland Municipality |  | Upgrading of the Darling Waste Water Treatment Works | Upgrading of the Darling Waste Water Treatmen Works to address the in Darling due to Housing and Industrial Businesss developments. | 90000000
48 | Swartland Municipality | Public |  | Energy & Water Infrastructure | Swartland Municipality |  | Swartland Bulk Water Supply: Kasteelberg to Riebeek Kasteel & Riebeek Kasteel New 4.5ML Reservoir | Swartland Bulk Water Supply: Kasteelberg to Riebeek Kasteel & Riebeek Kasteel New 4.5ML Reservoir | 85000000
49 | Swartland Municipality | Public |  | Energy & Water Infrastructure | Swartland Municipality |  | Upgrading of the bulk water pipeline system between the Wesbank Reservoir and the areas of Malmesbury and Abbotsdale | The proposed upgrading of the bulk water pipeline system between the Wesbank Reservoir and the areas of Malmesbury and Abbotsdale, as part of Swartland Municipality’s long-term infrastructure development strategy. The new bulk water line will extend from Alfa Street to the Old Malmesbury Road and serve key developments, including existing and future industrial areas, rural developments, and the communities of Abbotsdale, Chatsworth, and Kalbaskraal | 19700000
50 | Housing Development Agency | Public | Strand | Social | City of Cape Town |  | Erf 14443 Strand Development | The Erf 14443 Strand Development is a strategic initiative by the Housing Development Agency (HDA) to address the growing demand for affordable and social housing in the City of Cape Town. This project aims to repurpose underutilized state-owned land into a sustainable, well-managed housing development that enhances urban regeneration and economic growth. Key Objectives:- Provide quality, affordable housing for low-income earners, young professionals, and families.- Align with national and municipal housing policies for integrated urban development.- Promote sustainable building practices and improve housing opportunities. | 431560490
51 | Housing Development Agency | Public | Sea Point | Social | City of Cape Town |  | Erf 1220 Sea Point Luxury Apartments | Luxury mixed-use housing development. The project envisions the transformation of this property into a contemporary ten-storey luxury mixed-use development. By leveraging the property's prime location and existing zoning, the development will contribute to the area's growth and revitalization, making it a desirable destination for residents and businesses alike. | Aoproximate:R 518,491,750
52 | Housing Development Agency | Public | Blouberg strand | Social | City of Cape Town |  | Erf 1117 Bloubergstrand | The Erf 1117 Bloubergstrand Development is a strategic initiative to address the growing demand for affordable and social housing in the City of Cape Town. This project aims to repurpose underutilised state-owned land into a sustainable, well-managed housing development that enhances urban regeneration and economic growth. | To be determined
R131 billion

## City of Cape Town
No | Municipality | CPX | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comment/ Notes | DLG/ DoI Assitance Required | Last Update Date
1 | City of Cape Town | C11.86063 | Potsdam WWTW - Extension | Wastewater | Milnerton | 23329241829.36 | 1 EFF | IDP | Execution | In Exection |  | Immediate |  | Water & Santitation Directorate | Sameeh Johaadien | 2014-11-03 | 2028-01-28 | Reasons: In recent years, there has been increasing development pressure in the catchment, necessitating an additional capacity extension. Goal: Extension and upgrading the PWWTP from a capacity of 47Ml/d to a capacity of 100Ml/d. Comment/Notes: Increase of quality and quantity for: - recycled/reused as a source of water for a multitude of water-demanding activities such as agriculture, recreational impoundments, landscaping , industrial and other non-potable requirements; - provide an environmentally safe disposal system for the treated wastewater which will not be reused.
2 | City of Cape Town | C12.86059 | Macassar WWTW Extension | Wastewater | Macassar | 18305302183.32 | 1 EFF | IDP | Execution | In Exection |  | Immediate |  | Water & Santitation Directorate | Marcel Woodman | 2011-07-01 | 2032-01-30 | Reasons: To increase the capacity of the Macassar WWTW to improve service and capacity to the region and also support further development Goal: Increase daily Treatment capacity by 32Ml/d. During the project a bypass line to the inlet works will be installed as well the rebuild of a failed clarifier Refurbishment and improvements to existing works. Comment/Notes: Improved sewerage service to the community as well provide additional capacity for further development in the area.
3 | City of Cape Town | CPX.0005615 | Cape Flats Rehabilitation | Reticulation | Cape Flats | 10427833032.3 | 1 EFF | IDP | Execution | In Exection |  | Immediate |  | Water & Santitation Directorate | Comfort Mathenjwa | 2017-03-01 | 2030-06-30 | Reasons: The Cape Flats system, consisting out of a twin sewer, is 70+ years old and shows corrosion on the inside of the pipe and a few collapses were recorded confirming the vunerability of the materrial which requires rehabilitation to ensure the servcie is availabe to the consumers. Goal: The goal is to rehabilitate a total of 28km of sewer main and manholes to ensure the longetivity of the system. Comment/Notes: A rehabilitated 28km of bulk sewer pipeline from Bridgetown pump-station to Cape Flats WWTW, improving capacity and flow c haracteristics within bulk sewer infrastructure. The reliability of the system will be reinstated with a life expactancy of 100 years or more.
4 | City of Cape Town | CPX.0007972 | BWAS:Muldersvlei Reservoir & Pipeline | Bulk Water | Muldersvlei | 7175739587.84 | 4 NT USDG | IDP | Execution | In Exection |  | Immediate |  | Water & Santitation Directorate | Gavin George | 2010-07-01 | 2032-11-04 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City#s water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Goal: The BWAS essentially consists of a 500M#/day water treatment plant (WTP), two 300M# bulk storage reservoirs, a raw water pipeline supplying water from the Berg River Scheme to the new WTP and pipelines conveying water from the WTP to the new reservoirs and into the existing bulk water supply system. The infrastructure components comprising the BWAS are: # 3 -500M#/day water treatment plant # 3 -300M# bulk storage reservoir # 6 -300M# transfer reservoir # 2 -30km pipeline from the existing Berg River Dam to WTP # 4 -13km pipeline from bulk storage reservoir to transfer reservoir #7 - 13km pipeline from the transfer reservoir to the existing Glen Garry Reservoir # 5 -A pumpstation and flow control installation This project item is for the construction of the -300M# bulk storage reservoir Comment/Notes: The City#s Bulk Water Supply System supplies water to Cape Town, as well as the neighbouring towns of Stellenbosch, Paarl and Wellington. Cape Town is a growing city with a resultant growth in the demand for water. The surrounding region is also experiencing similar growth and a resultant growth in water demand. While the implementation of water demand management by Cape Town and surrounding towns has been successful, the demand for water is expected to continue to grow into the future. # The Bulk Water Augmentation Scheme is required to increase the overall treatment, bulk conveyance and bulk storage capacity of the City#s Bulk Water Supply System to ensure the future supply of water to Cape Town and surrounding towns, and to prevent the need for implementation of water restrictions in future due to inadequate capacity to supply peak period water demand. # The Bulk Water Augmentation Scheme will significantly increase the flexibility of operation of the Bulk Water Supply System, and also increase the security of supply of water to Cape Town.
5 | City of Cape Town | CPX.0019944 | Zandvliet WWTW 60ML/d | Wastewater | Zandvliet | 3980000000 | 1 EFF | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Keith Olsen | 2024-07-01 | 2041-06-30 | Reasons: To increase the capacity of the Zandlviet WWTW by 60 Ml/d, to improve service and capacity to the region and also support further development. The Zandvliet wastewater treatment works (WWTW) treats effluent from the southern parts of Kuils River, Delft, Blackheath, Blackheath Industria, Blue Downs, Eerste River, De Wijnlanden, Thembokwezi, Mxolisi Phetani, and Khayelitsha. First commissioned in 1989 as an activated sludge works treating settled wastewater, the Plant has undergone several upgrades over the years to keep pace with the increasing wastewater volumes due to expanding population and stricter environmental regulations. In recent years, the Zandvliet WWTW underwent a signifacant upgrade of 18Ml/d, completed in 2023, bringing the Plant's total capacity to 90Ml/d. The upgrade aimed not only to increase the Plant's capacity but also addressed many of its operational bottlenecks. Goal: The upgrade included the construction of a new inlet works and a new dewatering facility. Primary settling tanks (PSTs) were introduced to reduce the organic loading on the downstream conventional activated sludge (CAS) works. Original CAS reactors were refurbished and new secondary settling tanks (SSTs) were added to increase aeration capacity. Additionally, the existing membrane bioreactor (MBR) was refurbished to improve operational efficiency and streamline treatment process, while a new MBR was commissioned not only as per project upgrade brief, but also further boost the Plant's treatment capacity and efficiency. A new disinfection system was installed to treat effluent to meet the stringent environmental standarded before being released into the environment. Overall, the Plant is now mechanically equipped to treat the capacity of 90Ml/d, with civil infrastructure built to support an ultimate capacity of 150Ml/d. Comment/Notes: Improved sewerage service to the community as well provide additional capacity for further development in the area.
6 | City of Cape Town | CPX.0036535 | Mitchells Plain WWTW Capacity Expansion | Wastewater | Mitchells Plain | 3744468784 | 1 EFF | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Mishka Slamang | 2024-07-01 | 2036-06-30 | Reasons: The earliest phases of the modern MP WWTW were originally constructed in 1975 to treat residential wastewater from the Mitchells Plain and Strandfontein catchment area so that it could be safely stored in maturation ponds and discharged into the surf zone of False Bay. This catchment has grown steadily over the past fifty years, necessitating several upgrades and capacity expansion projects. The Mitchells Plain Wastewater Treatment Works (WWTW) is located in Strandfontein, south-west of Mitchells Plain. Spine Roadtraverses the Works, and the treatment portion of the Works is located north of Spine Road, while the maturation ponds are located south of Spine Road, between Spine Road and Baden Powell Drive. The current Works is operating at capacity of 35Ml/d. The specific challenge is that the plant's current design capacity of 35 million litres per day (average dry weather flow) is already operating at over 80% utilisation, with inflows projected to exceed this limit by around 2032 due to steady urban growth. Much of the infrastructure—originally built in the 1970s and partially upgraded over time—is now old, unreliable, or out of service, leading to ineffective treatment processes, frequent equipment and electrical failures, and unsafe conditions for operational staff. Goal: The overarching goal of this project is to deliver a sustainable, long-term upgrade and/or operational enhancement program for the MP Wastewater Treatment Works (MP WWTW), ensuring it continues to provide reliable, compliant, safe, and environmentally responsible wastewater treatment services that support social and economic growth in the MP catchment area while aligning with national priorities for water security, public health, environmental protection, and regulatory compliance in South Africa. The project goals are framed as SMART objectives (Specific, Measurable, Achievable, Relevant, Time-bound) and focus on key desired outcomes over a 20-year horizon. These goals are designed to meet stakeholder expectations, including those of local authorities, regulatory bodies (e.g., Department of Water and Sanitation), communities, and environmental groups. The project seeks to address the following objectives: · Achieve reliable compliance in wastewater effluent quality for the next 20 years · Ensure safe and practical working conditions for operational personnel (>98% plant availability, 0 work-related injuries requiring medical attention) for the next 20 years · Provide adequate sanitation capacity to enable social and economic development within the MP catchment area for the next 20 years · Improve environmental sustainability (emissions to land, water, air) of the MP WWTW Comment/Notes: The project to upgrade and enhance the MP Wastewater Treatment Works (MP WWTW) will deliver substantial, multi-faceted benefits that directly address current operational, environmental, regulatory, and socio-economic challenges. By resolving issues such as non-compliance risks, capacity constraints, safety concerns, and environmental impacts, the project generates tangible value for the City of Cape Town, local communities, downstream ecosystems, industries, and end-users in the MP catchment area. By addressing the above challenges, this project will achieve the following benefits: · Improve the coastal environment (for marine ecosystem and residents) · Unlock economic opportunity through development in the catchment · Improve working conditions for City of Cape Town (CCT) personnel · Enable potential reuse of treated wastewater effluent in line with City’s 2019 Water Strategy
7 | City of Cape Town | C11.86060 | Philippi Collector Sewer | Reticulation | Philippi | 3365643146.64 | 1 EFF | IDP | Execution | In Exection |  | Immediate |  | Water & Santitation Directorate | Eesa Limbada | 2009-11-25 | 2028-02-02 | Reasons: The current Philippi Sewer is ageing and are prone to collapses and blockages. This is causing spillages which could also pose a heath risk. Collapses are putting a strain on the already short staffed operational depot. Goal: To ensure un-interrupted service delivery to the affected residents of Cape Town. A larger sewer will also create further d evelopment oppurtunites in the area. Reduce the current burden on the depot. Comment/Notes: Improved service delivery of the sewer network and the new sewer lines will create many more development oppurtunities in the Philippi and Schaapkraal area. The new pipeline will asisst in reducing the current maintenance costs.
8 | City of Cape Town | CPX.0036094 | Philippi Collect Sewer Ph2 | Reticulation | Philippi | 3054700124 | 4 NT USDG | IDP | Detailed Design | In progress |  | Medium term |  | Water & Santitation Directorate | Eesa Limbada | 2018-07-02 | 2031-12-31 | Reasons: The current Philippi Sewer is ageing and are prone to collapses and blockages. This is causing spillages which could also pose a heath risk. Collapses are putting a strain on the already short staffed operational depot. Goal: To ensure un-interrupted service delivery to the affected residents of Cape Town. A larger sewer will also create further development oppurtunites in the area. Reduce the current burden on the depot. Comment/Notes: Improved service delivery of the sewer network and the new sewer lines will create many more development oppurtunities in the Philippi and Schaapkraal area. The new pipeline will asisst in reducing the current maintenance costs.
9 | City of Cape Town | CPX.0026282 | Athlone WWTW-Capacity Extension-phase 2A | Wastewater | Athlone | 2973695376 | 1 EFF | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Anton Le Roux | 2023-10-02 | 2037-06-30 | Reasons: Variouswastewater treatment plants requiring upgrading and refurbishment to achievedischarge limits. Goal: Upgradeand refurbishment of infrastructure at wastewater works. Comment/Notes: Improved treatment capacity and performance. Unrestricted growth in catchment area.
10 | City of Cape Town | C13.86081 | Athlone WWTW-Capacity Extension-phase 1 | Wastewater | Athlone | 2852448982.15 | 1 EFF | IDP | Execution | In Exection |  | Immediate |  | Water & Santitation Directorate | Anton Le Roux | 2012-07-02 | 2031-12-31 | Reasons: Improve treatment capacity of existing infrastructure. Goal: Increase treatment capacity and improve the process. Comment/Notes: Treated effluent final product will be of higher quality. Re-use of product on sport fields and golf courses.
11 | City of Cape Town | CPX.0030014 | Athlone WWTW-Capacity Extension-phase 2B | Wastewater | Athlone | 2566873500 | 1 EFF | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Anton Le Roux | 2027-07-01 | 2041-06-30 | Reasons: This phase will complete the full additional treatment capacity of 50Ml/d. A 50Ml/d secondary treatment train will be co nstructed as well as the fitment of mechanical and electrical equipment to the tertiary disinfection train. Goal: To achieve wastewater treatment works discharge limits. Comment/Notes: This will allow for enough treatment capacity for unhindered growth in the catchment area with improved treatment capacity and performance.
12 | City of Cape Town | CPX.0007976 | BWAS-C2-C-Raw Water P/line-M'vlei WTP | Bulk Water | Muldersvlei | 2181900000 | 4 NT USDG | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Gavin George | 2010-07-01 | 2038-06-30 | Reasons: The purpose for this projects is to convey raw water from the Berg River dam to the the future Muldersvlei water treatment plant. Goal: The purpose for this projects is to convey raw water from the Berg River dam to the the future Muldersvlei water treatment plant. Comment/Notes: This project allows for existing raw water allocations to be utilised and increases the redundancy in the bulkwater supply system.
13 | City of Cape Town | CPX.0008041 | Bellville WWTW Extension | Wastewater | Bellville | 2156585443.25 | 1 EFF | IDP | Execution | In Exection |  | Immediate |  | Water & Santitation Directorate | Noluthando Sebezo | 2016-07-01 | 2027-06-30 | Reasons: Insufficient hydraulic capacity at WWTW. Goal: Upgrade of process to increase of hydraulic capacity Comment/Notes: Increased treatment capacity and extend the life of the treatment plant.
14 | City of Cape Town | CPX.0011318 | Bulk Retic Sewers in Milnerton Rehab | Reticulation | Milnerton | 1917119841.15 | 1 EFF | IDP | Execution | In Exection |  | Immediate |  | Water & Santitation Directorate | Philip Dorfling | 2017-07-03 | 2026-10-30 | Reasons: Following the condition assessment of Blaauwberg & Milnerton sewer infrastructure specific pipes were identified for testing and rehabilitation. Some of the infrastructure is approx. 40 yrs old and near collapsing. Goal: Rehabilitation of existing poor condition sewer infrastructure Comment/Notes: Avoid sewerage failures and avoidance of environmental pollution and related community issues
15 | City of Cape Town | CPX.0007981 | BWAS:Ph2:SpesBonaRes(300Ml)C6-C-VV-GG | Bulk Water | Spes Bona | 1890000000 | 4 NT USDG | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Gavin George | 2029-07-01 | 2040-12-31 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City#s water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Goal: The BWAS essentially consists of a 500M#/day water treatment plant (WTP), two 300M# bulk storage reservoirs, a raw water pipeline supplying water from the Berg River Scheme to the new WTP and pipelines conveying water from the WTP to the new reservoirs and into the existing bulk water supply system. The infrastructure components comprising the BWAS are: # 3 -500M#/day water treatment plant # 3 -300M# bulk storage reservoir # 6 -300M# transfer reservoir # 2 -30km pipeline from the existing Berg River Dam to WTP # 4 -13km pipeline from bulk storage reservoir to transfer reservoir #7 - 13km pipeline from the transfer reservoir to the existing Glen Garry Reservoir # 5 -A pumpstation and flow control installation Comment/Notes: The City's Bulk Water Supply System supplies water to Cape Town, as well as the neighbouring towns of Stellenbosch, Paarl and Wellington. Cape Town is a growing city with a resultant growth in the demand for water. The surrounding region is also experiencing similar growth and a resultant growth in water demand. While the implementation of water demand management by Cape Town and surrounding towns has been successful, the demand for water is expected to continue to grow into the future. # The Bulk Water Augmentation Scheme is required to increase the overall treatment, bulk conveyance and bulk storage capacity of the City's Bulk Water Supply System to ensure the future supply of water to Cape Town and surrounding towns, and to prevent the need for implementation of water restrictions in future due to inadequate capacity to supply peak period water demand. # The Bulk Water Augmentation Scheme will significantly increase the flexibility of operation of the Bulk Water Supply System, and also increase the security of supply of water to Cape Town.
16 | City of Cape Town | CPX.0007974 | BWAS-C3-C-Muldersvlei WTP (500Ml/day) | Bulk Water | Muldersvlei | 1839000000 | 4 NT USDG | IDP | Scoping | In progress |  | Medium term |  | Water & Santitation Directorate | Gavin George | 2010-07-01 | 2035-06-30 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City#s water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Goal: The BWAS essentially consists of a 500M#/day water treatment plant (WTP), two 300M# bulk storage reservoirs, a raw water pipeline supplying water from the Berg River Scheme to the new WTP and pipelines conveying water from the WTP to the new reservoirs and into the existing bulk water supply system. The infrastructure components comprising the BWAS are: # 3 -500M#/day water treatment plant # 3 -300M# bulk storage reservoir # 6 -300M# transfer reservoir # 2 -30km pipeline from the existing Berg River Dam to WTP # 4 -13km pipeline from bulk storage reservoir to transfer reservoir #7 - 13km pipeline from the transfer reservoir to the existing Glen Garry Reservoir # 5 -A pumpstation and flow control installation Comment/Notes: The City#s Bulk Water Supply System supplies water to Cape Town, as well as the neighbouring towns of Stellenbosch, Paarl and Wellington. Cape Town is a growing city with a resultant growth in the demand for water. The surrounding region is also experiencing similar growth and a resultant growth in water demand. While the implementation of water demand management by Cape Town and surrounding towns has been successful, the demand for water is expected to continue to grow into the future. # The Bulk Water Augmentation Scheme is required to increase the overall treatment, bulk conveyance and bulk storage capacity of the City#s Bulk Water Supply System to ensure the future supply of water to Cape Town and surrounding towns, and to prevent the need for implementation of water restrictions in future due to inadequate capacity to supply peak period water demand. # The Bulk Water Augmentation Scheme will significantly increase the flexibility of operation of the Bulk Water Supply System, and also increase the security of supply of water to Cape Town.
17 | City of Cape Town | CPX.0036297 | Bellville WWTW Inlet works construction | Wastewater | Bellville | 1825661109.6 | 1 EFF | IDP | Scoping | In progress |  | Medium term |  | Water & Santitation Directorate | DAVID MODIRI | 2026-07-01 | 2034-07-28 | Reasons: Bellville wastewater treatment works requiring upgrading of inlet works to achieve discharge limits. Goal: Upgrade and refurbishment of infrastructure at Bellville wastewater works. Comment/Notes: Improved treatment capacity and performance due to increased population in the catchment. More flow from the Reticulation Branch.
18 | City of Cape Town | C10.86033 | Zandvliet WWTW-Extension | Wastewater | Zandvliet | 1325390488 | 1 EFF | IDP | Screen | In progress |  | Immediate |  | Water & Santitation Directorate | Keith Fredrik Olsen | 2014-03-26 | 2024-06-30 | Reasons: Additional capacity required in the Zandvliet WTW catchment area. Goal: Extend the capacity of the works by 18Ml/d Comment/Notes: Will allow development in the area to continue.
19 | City of Cape Town | CPX.0029825 | Borcherds Quarry WWTW Phase II | Wastewater | Borcherds Quarry | 1163915264.1 | 4 NT USDG | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Hegans Marthinus | 2024-07-01 | 2036-06-30 | Reasons: Borchards Quarry upgrade and infrastructure refurbishment. Goal: Improvement in operation of the plant and ease of process systems. Comment/Notes: Benfeicial operation of the plant and the catchment of the Borchards Quarry WWTW
20 | City of Cape Town | C12.86075 | Northern Regional Sludge Facility | Wastewater | Muldersvlei | 1053347311.5 | 1 EFF | IDP | Scoping | In progress |  | Medium term |  | Water & Santitation Directorate | Mark Nicholas Marais | 2011-07-01 | 2034-06-30 | Reasons: A couple of reasons exist for the project: 1. To reduce the volume of sludges produced by the WWTPs 2. To convert the sludges to Biosolids of AIa quality which are pathogen free. 3. The by product will gas which can be used to generate electricity - to offset electricity consumption costs Goal: To complete the commissioning of a 'first for SA' plant that achieves : 1. To reduce the volume of sludges produced by the WWTPs 2. To convert the sludges to Biosolids of AIa quality which are pathogen free. 3. The by product will gas which can be used to generate electricity - to offset electricity consumption costs Comment/Notes: Lower waste, higher quality biosolids that can used as a fertiliser as well cost benefits of the Electricity production
21 | City of Cape Town | CPX.0007979 | BWAS:M'vlei WTP-SBR P/Line-13km C4-C | Bulk Water | Muldersvlei | 976500000 | 4 NT USDG | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Gavin George | 2030-07-01 | 2040-06-29 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City#s water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Goal: The BWAS essentially consists of a 500M#/day water treatment plant (WTP), two 300M# bulk storage reservoirs, a raw water pipeline supplying water from the Berg River Scheme to the new WTP and pipelines conveying water from the WTP to the new reservoirs and into the existing bulk water supply system. The infrastructure components comprising the BWAS are: # 3 -500M#/day water treatment plant # 3 -300M# bulk storage reservoir # 6 -300M# transfer reservoir # 2 -30km pipeline from the existing Berg River Dam to WTP # 4 -13km pipeline from bulk storage reservoir to transfer reservoir #7 - 13km pipeline from the transfer reservoir to the existing Glen Garry Reservoir # 5 -A pumpstation and flow control installation Comment/Notes: The City#s Bulk Water Supply System supplies water to Cape Town, as well as the neighbouring towns of Stellenbosch, Paarl and Wellington. Cape Town is a growing city with a resultant growth in the demand for water. The surrounding region is also experiencing similar growth and a resultant growth in water demand. While the implementation of water demand management by Cape Town and surrounding towns has been successful, the demand for water is expected to continue to grow into the future. # The Bulk Water Augmentation Scheme is required to increase the overall treatment, bulk conveyance and bulk storage capacity of the City#s Bulk Water Supply System to ensure the future supply of water to Cape Town and surrounding towns, and to prevent the need for implementation of water restrictions in future due to inadequate capacity to supply peak period water demand. # The Bulk Water Augmentation Scheme will significantly increase the flexibility of operation of the Bulk Water Supply System, and also increase the security of supply of water to Cape Town.
22 | City of Cape Town | CPX.0007984 | BWAS-C7-C-VV-GGPh3:SBR-GG P/Line-13.3km | Bulk Water | Muldersvlei | 954000000 | 4 NT USDG | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Gavin George | 2010-07-01 | 2037-06-30 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City#s water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Goal: The BWAS essentially consists of a 500M#/day water treatment plant (WTP), two 300M# bulk storage reservoirs, a raw water pipeline supplying water from the Berg River Scheme to the new WTP and pipelines conveying water from the WTP to the new reservoirs and into the existing bulk water supply system. The infrastructure components comprising the BWAS are: # 3 -500M#/day water treatment plant # 3 -300M# bulk storage reservoir # 6 -300M# transfer reservoir # 2 -30km pipeline from the existing Berg River Dam to WTP # 4 -13km pipeline from bulk storage reservoir to transfer reservoir #7 - 13km pipeline from the transfer reservoir to the existing Glen Garry Reservoir # 5 -A pumpstation and flow control installation This project item is for the construction of the -300M# bulk storage reservoir Comment/Notes: The City#s Bulk Water Supply System supplies water to Cape Town, as well as the neighbouring towns of Stellenbosch, Paarl and Wellington. Cape Town is a growing city with a resultant growth in the demand for water. The surrounding region is also experiencing similar growth and a resultant growth in water demand. While the implementation of water demand management by Cape Town and surrounding towns has been successful, the demand for water is expected to continue to grow into the future. # The Bulk Water Augmentation Scheme is required to increase the overall treatment, bulk conveyance and bulk storage capacity of the City#s Bulk Water Supply System to ensure the future supply of water to Cape Town and surrounding towns, and to prevent the need for implementation of water restrictions in future due to inadequate capacity to supply peak period water demand. # The Bulk Water Augmentation Scheme will significantly increase the flexibility of operation of the Bulk Water Supply System, and also increase the security of supply of water to Cape Town.
23 | City of Cape Town | CPX.0007930 | Zandvliet WWTW: Membrane Bio Reactor | Wastewater | Zandvliet | 894247622 | 4 NT USDG | IDP | Scoping | In progress |  | Immediate |  | Water & Santitation Directorate | Keith Fredrik Olsen | 2014-03-26 | 2022-06-30 | Reasons: To increase the capacity of the Zandlviet WWTW to improve service and capacity to the region and also support further development Goal: Increase daily Treatment capacity by 18Mlitres. Comment/Notes: Improved sewerage service to the community as well provide additional capacity for further development in the area.
24 | City of Cape Town | C12.86074 | Construction of new Head Office | Bulk Services | Bellville | 590062784 | 1 EFF | IDP | Execution | In Exection |  | Immediate |  | Water & Santitation Directorate | Berend Jager | 2018-01-15 | 2020-06-30 | Reasons: The fragmented state of office accommodation for the Water and Sanitation Department leads to duplication and the rationalisation of these splinter units into a single building will ensure long term cost savings to Council. Goal: The goal of the project is to centralise splinter units into a single office complex. It is intended to discontinue renting office space. Comment/Notes: The fragmented state of office accommodation for the Water and Sanitation Department will be addressed and long term cost savings to Council will result. The renting of office space will be discontinued.
25 | City of Cape Town | CPX.0030003 | Replacement of Membranes: Bellville WWTW | Wastewater | Bellville | 380000000 | 1 EFF | IDP | Screen | In progress |  | Medium term |  | Water & Santitation Directorate | DAVID MODIRI | 2025-10-01 | 2032-06-30 | Reasons: Bellville wastewater treatment plant requiring replacement of membranes. Goal: Planned Replacement of consumable/perishable membranes at the end of their lifespan. Comment/Notes: Restored treatment capacity and performance of the waste water treatment works.
26 | City of Cape Town | CPX.0042073 | Bulk Sewers in Milnerton Rehab Phase 2 | Reticulation | Milnerton | 372709142 | 1 EFF | IDP | Execution | In Exection |  | Immediate |  | Water & Santitation Directorate | Philip Dorfling | 2020-07-03 | 2028-08-31 | Reasons: Following the condition assessment of Blaauwberg & Milnerton sewer infrastructure specific pipes were identified for testing and rehabilitation. Some of the infrastructure is approx. 40 yrs old and near collapsing. Goal: Rehabilitation of existing poor condition sewer infrastructure Comment/Notes: Avoid sewerage failures and avoidance of environmental pollution and related community issues
27 | City of Cape Town | CPX.0015629 | Cape Flats WWTW-Biosolids Phase 2 | Wastewater | Cape Flats | 357000000 | 1 EFF: 2 | IDP | Scoping | In progress |  | Medium term |  | Water & Santitation Directorate | Mark Nicholas Marais | 2026-04-01 | 2033-10-01 | Reasons: Dewatered primary sludge is classified as hazardous waste and can only be disposed at Visserhok Landfill facility. National Policy has changed preventing the discharge of primary sludge at Visserhok landfill. This advanced sludge treatment will improve the quality of the sludge and dumping at landfill will no longer be required. Goal: To improve the sludge quality in order to meet National policy. Comment/Notes: Improved sludge quality and improved landfill site usage
28 | City of Cape Town | CPX.0003893 | OSEC (Electrolytic Chlorination Infr) | Bulk Water |  | 226868789.04 | 1 EFF | IDP | Conceptual Design | In progress |  | Immediate |  | Water & Santitation Directorate | Gavin George | 2014-02-03 | 2029-06-30 | Reasons: Existing gas chlorination is Hazardous water disinfection process. In order to provide a safer working environment for employees and the public, the gas chlorination systems needs to be replaced with an electrolytic chlorination system. Goal: '-To replace existing chlorine gas disinfection system with the EC system. This includes the site planning, design and construction of the facility - Increase safety on site - Reduce use of chlorine gas Comment/Notes: '- Will reduce the usage, and hencethe risk, by 25 tonnes of chlorine gas per annum. - The sites will be declassifiedas a major hazard installations. - This will significantlyimproving the safety of the employees and the public.
29 | City of Cape Town | CPX.0036372 | BWAS:Voelvlei P/L B PS - Windmeul 200MLD | Bulk Water | voelvlei | 187150000 | 1 EFF | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Tracy Wehr | 2031-07-01 | 2036-06-30 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City#s water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Goal: The BWAS essentially consists of a 500M#/day water treatment plant (WTP), two 300M# bulk storage reservoirs, a raw water pipeline supplying water from the Berg River Scheme to the new WTP and pipelines conveying water from the WTP to the new reservoirs and into the existing bulk water supply system. The infrastructure components comprising the BWAS are: # 3 -500M#/day water treatment plant # 3 -300M# bulk storage reservoir # 6 -300M# transfer reservoir # 2 -30km pipeline from the existing Berg River Dam to WTP # 4 -13km pipeline from bulk storage reservoir to transfer reservoir #7 - 13km pipeline from the transfer reservoir to the existing Glen Garry Reservoir # 5 -A pumpstation and flow control installation This project item is for the construction of the -300M# bulk storage reservoir Comment/Notes: The City#s Bulk Water Supply System supplies water to Cape Town, as well as the neighbouring towns of Stellenbosch, Paarl and Wellington. Cape Town is a growing city with a resultant growth in the demand for water. The surrounding region is also experiencing similar growth and a resultant growth in water demand. While the implementation of water demand management by Cape Town and surrounding towns has been successful, the demand for water is expected to continue to grow into the future. # The Bulk Water Augmentation Scheme is required to increase the overall treatment, bulk conveyance and bulk storage capacity of the City#s Bulk Water Supply System to ensure the future supply of water to Cape Town and surrounding towns, and to prevent the need for implementation of water restrictions in future due to inadequate capacity to supply peak period water demand. # The Bulk Water Augmentation Scheme will significantly increase the flexibility of operation of the Bulk Water Supply System, and also increase the security of supply of water to Cape Town.
30 | City of Cape Town | CPX.0009469 | Helderberg/Faure Scheme | Bulk Water | Helderberg/Faure | 167000000 | 1 EFF | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Andile Ngundze | 2023-07-01 | 2050-06-30 | Reasons: Helderberg/Faure Scheme comprising a bulk water pipeline to supply water from Faure WTP to the Helderberg Basin Goal: Helderberg/Faure Scheme comprising a bulk water pipeline to supply water from Faure WTP to the Helderberg Basin Comment/Notes: Provide potable water from Faure WTP to Helderberg Basin
31 | City of Cape Town | CPX.0016300 | Cape Flats WWTW - Biosolids | Wastewater | Cape Flats | 147996596.88 | 1 EFF: 2 | IDP | Conceptual Design | In progress |  | Immediate |  | Water & Santitation Directorate | Mark Nicholas Marais | 2019-06-01 | 2028-09-30 | Reasons: The primary reasons for the initiation of these projects are: 1) Policy is being revised to prohibit the discharging of primary sludge at landfill. 2) The secondary sludge is currently discharged on farmlands for soil conditioning. However the quality of the sludge prevents it from being used on land that yeilds food crops for human consumption. These farmlands are also becoming limited in their ability to take the quantities of sludge produced. 3) The City needs to reduce the quantity of sludge and increase the quality of sludge. (this can be done through advanced treatment) Goal: The goal of these projects is to construct a regional biosolids beneficiating facility at Cape Flats WWTW in the South with the aim to 1) reduce the quantity of biosolids 2) improve the quality of sludge through advanced treatment 3) import and treat the surrounding southern wastewater treatment works' sludge ,4) produce electricity from the methane generated in the treatment process and 5) treat the digester effluent through a netrient removal process to prohibit the overloading of the Cape Flats Wastewater Treatment Works. Comment/Notes: The benefits to the City will include, 1) the extended lifespan of existing solid waste landfill sites, 2) a valuable biosolid that has greater appeal and use allowing the City to discharge/ sell the final product, 3) electrical generation through utilising the methane production in the advanced treatment which will reduce the Branches electrical demand and operational expenses. With the energy recovery, it is estimated that the return payback period will be approximately 5-7 years. Furthermore with the reduction in slude volume, there will be a reduction in sludge trucking costs.
32 | City of Cape Town | CPX.0007986 | BWAS-C5-C-VV-GG Ph2: Pump Station | Bulk Water |  | 124800000 | 4 NT USDG | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Gavin George | 2033-07-01 | 2038-06-30 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City#s water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Goal: The BWAS essentially consists of a 500M#/day water treatment plant (WTP), two 300M# bulk storage reservoirs, a raw water pipeline supplying water from the Berg River Scheme to the new WTP and pipelines conveying water from the WTP to the new reservoirs and into the existing bulk water supply system. The infrastructure components comprising the BWAS are: # 3 -500M#/day water treatment plant # 3 -300M# bulk storage reservoir # 6 -300M# transfer reservoir # 2 -30km pipeline from the existing Berg River Dam to WTP # 4 -13km pipeline from bulk storage reservoir to transfer reservoir #7 - 13km pipeline from the transfer reservoir to the existing Glen Garry Reservoir # 5 -A pumpstation and flow control installation This project item is for the construction of the -300M# bulk storage reservoir Comment/Notes: The City#s Bulk Water Supply System supplies water to Cape Town, as well as the neighbouring towns of Stellenbosch, Paarl and Wellington. Cape Town is a growing city with a resultant growth in the demand for water. The surrounding region is also experiencing similar growth and a resultant growth in water demand. While the implementation of water demand management by Cape Town and surrounding towns has been successful, the demand for water is expected to continue to grow into the future. # The Bulk Water Augmentation Scheme is required to increase the overall treatment, bulk conveyance and bulk storage capacity of the City#s Bulk Water Supply System to ensure the future supply of water to Cape Town and surrounding towns, and to prevent the need for implementation of water restrictions in future due to inadequate capacity to supply peak period water demand. # The Bulk Water Augmentation Scheme will significantly increase the flexibility of operation of the Bulk Water Supply System, and also increase the security of supply of water to Cape Town.
33 | City of Cape Town | CPX.0005616 | Cape Flats Rehabilitation 18/19 | Reticulation | Cape Flats | 75000000 | 1 EFF | IDP | Scoping | In progress |  | Immediate |  | Water & Santitation Directorate | Abraham Smit | 2009-07-01 | 2019-06-28
34 | City of Cape Town | CPX.0015630 | Cape Flats WWTW Inlet works & rising mai | Wastewater | Cape Flats | 72000000 | 1 EFF | IDP | Conceptual Design | In progress |  | Medium term |  | Water & Santitation Directorate | Mark Nicholas Marais | 2021-10-14 | 2030-10-31 | Reasons: The existing inlet works at Cape Flats has reached its design lifespan. It is structurally compromised and unsafe. The mechanical equipment is constantly failing resulting in raw sewage overflowing into the neighbouring ponds. This is an environmental risk along with a City image risk. The facility is passed it lifespan and a new inlet works is required. Goal: To construct a new inlet works that provides safe working conditions and install new mechanical and electrical infrastructure. Comment/Notes: Working equipment, no sewage spillages, safe working environment.
35 | City of Cape Town | CPX.0011021 | Mitchells Plain WWTW-reuse PS extension | Wastewater | Mitchells Plain | 40000000 | 1 EFF | IDP | Scoping | In progress |  | Immediate |  | Water & Santitation Directorate | Ivy Masinga | 2020-10-01 | 2027-06-30 | Reasons: The Mitchell#s Plain Wastewater Treatment Works (WWTW) needs refurbishment and capacity expansion to accommodate expected growth in the catchment. It is anticipated the upgrade will provide an extra 20Ml/d capacity for the Works. The Mitchells Plain Wastewater Treatment Works (WWTW) is located in Strandfontein , south-west of Mitchells Plain. Spine Road traverses the Works, and the treatment portion of the Works is located north of Spine Road, while the maturation ponds are located south of Spine Road , between Spine Road and Baden Powell Drive. The Mitchells Plain WWTW was first commissioned in 1976 as a 5.5 Ml/d activated sludge works treating settled wastewater (Stage 1). A second activated sludge treatment module (Stage 2, 16 Ml/d) and the anaerobic digester installation (Stage 3) were commissioned 1980/81, increasing the Works capacity to 21.5 Ml/d. A third activated sludge treatment module (Stage 4, 16 Ml/d) was commissioned in 1995, increasing the Works capacity to 37.5 Ml/d. The Stage 1 treatment module was decommissioned when the Stage 4 module was commissioned, and the current Works capacity is approximately 35 Ml/d. The anaerobic digester installation is not in use, and both primary and activated sludges are separately mechanically dewatered and the resulting sludge cakes are disposed of offsite . The Works is currently licensed under a Water Use License issued by National DWS, however since the Works discharges directly onto a beach, an application for a Coastal Discharge Permit was submitted to National DFFE in 2019. No permit has been issued to date. Goal: It is anticipated that the capacity upgrade will provide an additional 15 to 20 Ml/d treatment capacity for the Mitchells Plain WWTW, either as one project, or in a phased manner should this be considered a better approach. The aforementioned shall be confirmed by the Cons ultant . The increased capacity is to be added by either refurbishing and upgrading (both capacity and process) the decommissioned Stage 1 treatment train and /or by increasing the capacity of the Stage 4 treatment Module as required. A completely new (Stage 5) treatment module is currently not envisaged, unless substantial reasoning re. capital cost process and treated effluent quality benefits can be provided. Comment/Notes: To treat wastewater to a better effluent quality with refurbishment of existing structures and provide more capacity.
36 | City of Cape Town | CPX.0007975 | BWAS:Raw Water P/line-M'vlei WTP C2-D&CS | Bulk Water | Muldersvlei | 39600000 | 4 NT USDG | IDP | Conceptual Design | In progress |  | Immediate |  | Water & Santitation Directorate | Gavin George | 2019-08-01 | 2023-06-30 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City's water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Goal: The BWAS essentially consists of a 500M#/day water treatment plant (WTP), two 300M# bulk storage reservoirs, a raw water pipeline supplying water from the Berg River Scheme to the new WTP and pipelines conveying water from the WTP to the new reservoirs and into the existing bulk water supply system. The infrastructure components comprising the BWAS are: # 3 -500M#/day water treatment plant # 3 -300M# bulk storage reservoir # 6 -300M# transfer reservoir # 2 -30km pipeline from the existing Berg River Dam to WTP # 4 -13km pipeline from bulk storage reservoir to transfer reservoir #7 - 13km pipeline from the transfer reservoir to the existing Glen Garry Reservoir # 5 -A pumpstation and flow control installation Comment/Notes: The City's Bulk Water Supply System supplies water to Cape Town, as well as the neighbouring towns of Stellenbosch, Paarl and Wellington. Cape Town is a growing city with a resultant growth in the demand for water. The surrounding region is also experiencing similar growth and a resultant growth in water demand. While the implementation of water demand management by Cape Town and surrounding towns has been successful, the demand for water is expected to continue to grow into the future. # The Bulk Water Augmentation Scheme is required to increase the overall treatment, bulk conveyance and bulk storage capacity of the City's Bulk Water Supply System to ensure the future supply of water to Cape Town and surrounding towns, and to prevent the need for implementation of water restrictions in future due to inadequate capacity to supply peak period water demand. # The Bulk Water Augmentation Scheme will significantly increase the flexibility of operation of the Bulk Water Supply System, and also increase the security of supply of water to Cape Town.
37 | City of Cape Town | CPX.0007973 | BWAS:Muldersvlei WTP 500Ml/day C3-D&CS | Bulk Water | Muldersvlei | 38400000 | 4 NT USDG | IDP | Conceptual Design | In progress |  | Medium term |  | Water & Santitation Directorate | Gavin George | 2019-07-01 | 2034-12-30 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City#s water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Goal: The BWAS essentially consists of a 500M#/day water treatment plant (WTP), two 300M# bulk storage reservoirs, a raw water pipeline supplying water from the Berg River Scheme to the new WTP and pipelines conveying water from the WTP to the new reservoirs and into the existing bulk water supply system. The infrastructure components comprising the BWAS are: # 3 -500M#/day water treatment plant # 3 -300M# bulk storage reservoir # 6 -300M# transfer reservoir # 2 -30km pipeline from the existing Berg River Dam to WTP # 4 -13km pipeline from bulk storage reservoir to transfer reservoir #7 - 13km pipeline from the transfer reservoir to the existing Glen Garry Reservoir # 5 -A pumpstation and flow control installation Comment/Notes: The City#s Bulk Water Supply System supplies water to Cape Town, as well as the neighbouring towns of Stellenbosch, Paarl and Wellington. Cape Town is a growing city with a resultant growth in the demand for water. The surrounding region is also experiencing similar growth and a resultant growth in water demand. While the implementation of water demand management by Cape Town and surrounding towns has been successful, the demand for water is expected to continue to grow into the future. # The Bulk Water Augmentation Scheme is required to increase the overall treatment, bulk conveyance and bulk storage capacity of the City#s Bulk Water Supply System to ensure the future supply of water to Cape Town and surrounding towns, and to prevent the need for implementation of water restrictions in future due to inadequate capacity to supply peak period water demand. # The Bulk Water Augmentation Scheme will significantly increase the flexibility of operation of the Bulk Water Supply System, and also increase the security of supply of water to Cape Town.
38 | City of Cape Town | CPX.0007989 | BWAS: Servitudes(C2&C4) | Bulk Water | Muldersvlei | 32400000 | 4 NT USDG | IDP | Conceptual Design | In progress |  | Immediate |  | Water & Santitation Directorate | Gavin George | 2010-07-01 | 2029-06-28 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City's water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Due to increasing water demands within the Cape Metropolitan Area (CMA), and with new raw water supplies that will become available upon completion of the Berg Water Project [BWAS Component 1], the City of Cape Town (CCT) proposes to implement new infrastructure to increase the CCT#s water treatment and bulk storage capacity and to increase the flexibility of the bulk water distribution network. This WBS has been established for securing of, and payment for BWAS pipelines servitudes. Goal: To register the required servitudes in preparation for the construction of the pipelines and supporting infrastructure in the BWAS programme. This is in aid to the delivery of the required pipelines guided by the Bulk Water Master Plan Comment/Notes: Protection of BWAS pipelines in perpetuity by way of servitudes. This is in aid of the BWAS programme benefits stemming from the Bulk Water Branch master plan. - I ncrease the CCT#s water bulk storage capacity - Enables more effective the flexibility in the bulk water distribution network - Enables some of the proposed Water Resilience schemes
39 | City of Cape Town | CPX.0007980 | BWAS:Ph2:SpesBonaRes(300Ml)C6-D&CS-VV-GG | Bulk Water | Spes Bona | 28053816 | 4 NT USDG | IDP | Conceptual Design | In progress |  | Immediate |  | Water & Santitation Directorate | Gavin George | 2010-07-01 | 2029-06-30 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City's water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Goal: This project is for the Design and Construction Supervision of the Spes Bona Reservoir (300 Ml). Comment/Notes: The City#s Bulk Water Supply System supplies water to Cape Town, as well as the neighbouring towns of Stellenbosch, Paarl and Wellington. Cape Town is a growing city with a resultant growth in the demand for water. The surrounding region is also experiencing similar growth and a resultant growth in water demand. While the implementation of water demand management by Cape Town and surrounding towns has been successful, the demand for water is expected to continue to grow into the future. # The Bulk Water Augmentation Scheme is required to increase the overall treatment, bulk conveyance and bulk storage capacity of the City#s Bulk Water Supply System to ensure the future supply of water to Cape Town and surrounding towns, and to prevent the need for implementation of water restrictions in future due to inadequate capacity to supply peak period water demand. # The Bulk Water Augmentation Scheme will significantly increase the flexibility of operation of the Bulk Water Supply System, and also increase the security of supply of water to Cape Town.
40 | City of Cape Town | CPX.0015800 | Upgrade clarifiers - Bellville WWTW PH2 | Wastewater | Bellville | 20000000 | 1 EFF | IDP | Scoping | In progress |  | Immediate |  | Water & Santitation Directorate | Keith Fredrik Olsen | 2022-07-01 | 2024-06-30
41 | City of Cape Town | CPX.0008886 | OSEC(Electrolytic Chlorination Infr) Ph2 | Bulk Water |  | 10600000 | 1 EFF | IDP | Conceptual Design | In progress |  | Long Term |  | Water & Santitation Directorate | Gavin George | 2023-01-03 | 2037-12-15 | Reasons: Existing gas chlorination is Hazardous water disinfection process. In order to provide a safer working environment for employees and the public, the gas chlorination systems needs to be replaced with an electrolytic chlorination system. Goal: '-To replace existing chlorine gas disinfection system with the EC system. This includes the site planning, design and construction of the facility - Increase safety on site - Reduce use of chlorine gas Comment/Notes: '- Will reduce the usage, and hence the risk, by 25 tonnes of chlorine gas per annum. - The sites will be declassified as a major hazard installations. - This will significantly improving the safety of the employees and the public.
42 | City of Cape Town | CPX.0008888 | OSEC(Electrolytic Chlorination Infr) Ph4 | Bulk Water | City wide | 10000000 | 1 EFF | IDP | Scoping | In progress |  | Medium term |  | Water & Santitation Directorate | Gavin George | 2026-01-19 | 2030-07-25 | Reasons: Existing gas chlorination is Hazardous water disinfection process. In order to provide a safer working environment for employees and the public, the gas chlorination systems needs to be replaced with an electrolytic chlorination system. Goal: '-To replace existing chlorine gas disinfection system with the EC system. This includes the site planning, design and construction of the facility - Increase safety on site - Reduce use of chlorine gas Comment/Notes: '- Will reduce the usage, and hencethe risk, by 25 tonnes of chlorine gas per annum. - The sites will be declassifiedas a major hazard installations. - This will significantlyimproving the safety of the employees and the public.
43 | City of Cape Town | C13.86002 | Upgrade clarifiers - Bellville WWTW | Wastewater | Bellville | 10000000 | 1 EFF | IDP | Scoping | In progress |  | Immediate |  | Water & Santitation Directorate | Keith Fredrik Olsen | 2012-07-03 | 2028-06-28 | Reasons: (Part of Project: CPX.0008041) Goal: (Part of Project: CPX.0008041) Comment/Notes: (Part of Project: CPX.0008041)
44 | City of Cape Town | CPX.0007977 | BWAS:M'vlei WTP-SBR P/Line-13km C4-D&CS | Bulk Water | Muldersvlei | 6400000 | 4 NT USDG | IDP | Screen | In progress |  | Medium term |  | Water & Santitation Directorate | Gavin George | 2019-08-01 | 2031-06-30 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City#s water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Goal: The BWAS essentially consists of a 500M#/day water treatment plant (WTP), two 300M# bulk storage reservoirs, a raw water pipeline supplying water from the Berg River Scheme to the new WTP and pipelines conveying water from the WTP to the new reservoirs and into the existing bulk water supply system. The infrastructure components comprising the BWAS are: # 3 -500M#/day water treatment plant # 3 -300M# bulk storage reservoir # 6 -300M# transfer reservoir # 2 -30km pipeline from the existing Berg River Dam to WTP # 4 -13km pipeline from bulk storage reservoir to transfer reservoir #7 - 13km pipeline from the transfer reservoir to the existing Glen Garry Reservoir # 5 -A pumpstation and flow control installation Comment/Notes: The City#s Bulk Water Supply System supplies water to Cape Town, as well as the neighbouring towns of Stellenbosch, Paarl and Wellington. Cape Town is a growing city with a resultant growth in the demand for water. The surrounding region is also experiencing similar growth and a resultant growth in water demand. While the implementation of water demand management by Cape Town and surrounding towns has been successful, the demand for water is expected to continue to grow into the future. # The Bulk Water Augmentation Scheme is required to increase the overall treatment, bulk conveyance and bulk storage capacity of the City#s Bulk Water Supply System to ensure the future supply of water to Cape Town and surrounding towns, and to prevent the need for implementation of water restrictions in future due to inadequate capacity to supply peak period water demand. # The Bulk Water Augmentation Scheme will significantly increase the flexibility of operation of the Bulk Water Supply System, and also increase the security of supply of water to Cape Town.
45 | City of Cape Town | CPX.0008887 | OSEC(Electrolytic Chlorination Infr) Ph3 | Bulk Water |  | 6000000 | 1 EFF | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Gavin George | 2024-07-01 | 2040-06-28 | Reasons: Existing gas chlorination is Hazardous water disinfection process. In order to provide a safer working environment for employees and the public, the gas chlorination systems needs to be replaced with an electrolytic chlorination system. Goal: '-To replace existing chlorine gas disinfection system with the EC system. This includes the site planning, design and construction of the facility - Increase safety on site - Reduce use of chlorine gas Comment/Notes: '- Will reduce the usage, and hencethe risk, by 25 tonnes of chlorine gas per annum. - The sites will be declassifiedas a major hazard installations. - This will significantlyimproving the safety of the employees and the public.
46 | City of Cape Town | CPX.0007983 | BWAS:Ph3:SBR-GG P/Line-13kmC7-D&CS-VV-GG | Bulk Water | Muldersvlei | 2400000 | 4 NT USDG | IDP | Feasibility | In progress |  | Medium term |  | Water & Santitation Directorate | Gavin George | 2019-07-01 | 2032-08-31 | Reasons: Cape Town is a growing city # due to population and economic growth, it continues to experience a resultant growth of water demand. This growth necessitates increasing the raw water resources available to the City, as well as increasing the treatment, storage and conveyance capacity of the City's water supply system to be able to continue supplying the growing water demand, particularly during peak demand periods during the hot dry summer months. Due to increasing water demands within the Cape Metropolitan Area (CMA), and with new raw water supplies that will become available upon completion of the Berg Water Project [BWAS Component 1], the City of Cape Town (CCT) proposes to implement new infrastructure to increase the CCT#s water treatment and bulk storage capacity and to increase the flexibility of the bulk water distribution network. Goal: The goal of this project in the BWAS programme is the provision of conveyance infrastructure to enable the transfer of water between the Voëlvlei WTW/Pipeline and Glen Garry reservoir. Objectives are as follows: - Construction of 300 M# Spes Bona Reservoir (transfer reservoir) in accordance with Bulk Water Master Plan item BLK-PT1 - Construction of a 13km 1 500mm DN pipeline from the Spes Bona Reservoir to the existing Glen Garry Reservoir (potable water pipeline) in accordance with Bulk Water Master Plan item [Component 7] [BLK-PT2] - Construction of a 3.3km 1 500mm DN pipeline from Voëlvlei Pipeline to Spes Bona Reservoir (potable water pipeline) [COMPLETE]. Comment/Notes: The benefits of this project stem from the Bulk Water Branch master plan and are summarized as follows: - Increase the CCT#s water bulk storage capacity - Enables more effective the flexibility in the bulk water distribution network - Enables some of the proposed Water Resilience schemes
47 | City of Cape Town | CPX.0004708 | Cape Flats Rehabilitation 15/16 | Reticulation | Cape Flats | 2000000 | 1 EFF | IDP | Scoping | In progress |  | Immediate |  | Water & Santitation Directorate | Albertus Johannes Louw | 2009-07-01 | 2019-06-28
48 | City of Cape Town | CPX.0005614 | Cape Flats Rehabilitation 16/17 | Reticulation | Cape Flats | 500000 | 1 EFF | IDP | Scoping | In progress |  | Immediate |  | Water & Santitation Directorate | Clyde Koen | 2009-07-01 | 2019-06-28
49 | City of Cape Town | CPX.0014006 | Desalination Location 2 | Bulk Water |  | 1757850000 | 1 EFF | IDP | Scoping | In progress |  | Long Term |  | Water & Santitation Directorate | Bradley Africa | 2018-07-01 | 2038-06-30 | Reasons: LongTerm Water Supply to City aligned to New Water Plan & City's Water Strategy Goal: Uninterrupted Water Provision to Cape Town City & resilience Comment/Notes: Uninterrupted Water Provision to Cape Town City & Resilience
50 | City of Cape Town | CPX.0013725 | Desalination Location 1 | Bulk Water | Paarden Eiland/Atlantis | 897364434 | 1 EFF | IDP | Conceptual Design | In progress |  | Medium term |  | Water & Santitation Directorate | Jan Malherbe | 2017-07-03 | 2032-06-30 | Reasons: LongTerm Water Supply to City aligned to New Water Plan & City's Water Strategy Goal: Uninterrupted Water Provision to Cape Town City & resilience Comment/Notes: Uninterrupted Water Provision to Cape Town City & resilience
51 | City of Cape Town | CPX.0019987 | AMI rollout programme | Customer Services (Water) | Citywide | 22869547116.78 | 1 EFF &4 NT UDFG | IDP | Execution | In progress |  | Medium term |  | Water & Santitation Directorate | Alexander Ncube | 2020-03-16 | 2030-07-01 | Reasons: The City Water Metering System is close to its end of life and a new solution that is more fit for purpose need to be installed. this will be more cost-effective, present substantially less operational challenges & ensure a substantial reduction in customer complaints. Goal: Failure Rate of AMI, no more than 0.5% of smart meters installed fail per calendar year. System Uptime, software applications should be online and accessible 99.5% of total time each month. Network Communication Services, 100% of all meters identified shall be covered by the AMI network, adequate encryption between endpoint and backend and with at least 15 year of operating lifespan. Daily Reads KPI, 99.5% or greater over 72 hours, 98% or greater over 48 hours, 95% or greater over 24 hours. Interval Reads KPI, a 98% or higher #hourly interval reads# success rate calculated monthly. At least 15 year operating lifespan. Comment/Notes: Revenue Enhancement Meter System Longevity Meter Reading Cost Reduction accuracy/reliable / regular readings Reduce meter malfunctions Plumbing loss detection increased consumption awareness improved customer engagement demand fore casting network leak detection hydraulic modelling calibration enhancements
52 | City of Cape Town | CPX.0038110 | AMI rollout programme Phase 2 | Customer Services (Water) | Citywide | 88828951554 | 1 EFF & 4 NT UDFG & 4 NT USDG | IDP | Screen | In progress |  | Long term |  | Water & Santitation Directorate | Jaco de Bruyn | 2023-06-08 | 2040-06-30 | Reasons: The City Water Metering System is close to its end of life and a new solution that is more fit for purpose need to be installed. this will be more cost-effective, present substantially less operational challenges & ensure a substantial reduction in customer complaints. Goal: Failure Rate of AMI, no more than 0.5% of smart meters installed fail per calendar year. System Uptime, software applications should be online and accessible 99.5% of total time each month. Network Communication Services, 100% of all meters identified shall be covered by the AMI network, adequate encryption between endpoint and backend and with at least 15 year of operating lifespan. Daily Reads KPI, 99.5% or greater over 72 hours, 98% or greater over 48 hours, 95% or greater over 24 hours. Interval Reads KPI, a 98% or higher #hourly interval reads# success rate calculated monthly. At least 15 year operating lifespan. Comment/Notes: Revenue Enhancement Meter System Longevity Meter Reading Cost Reduction accuracy/reliable / regular readings Reduce meter malfunctions Plumbing loss detection increased consumption awareness improved customer engagement demand fore casting network leak detection hydraulic modelling calibration enhancements
53 | City of Cape Town | CPX.0039258 | Upgrade of Rietvlei Bulk Sewer | Reticulation | Rietvlei | 253050000 | 1 EFF | IDP | Conceptual Design | In progress |  | Long term |  | Water & Santitation Directorate | Neville Jones | 2024-08-02 | 2032-06-30 | Reasons: To rehabilitate existing bulk sewer infrastructure that affects more than 20 thousand households. The pipeline is currently under strain due to population growth and ageing infrastructure. The alignment crosses sensitive areas, including the Table Bay Nature Reserve. As such, environmental compliance is central to this upgrade. The project is currently in the scoping stage with environmental screening already completed and authorisation processes underway. Goal: To rehabilitate 1000m of bulk sewer infrastructure to ensure that residents from Milnerton benefit. Ensure e nvironmental compliance Comment/Notes: The benifit will be that the residents of Milnerton can be assured that waste water service are delivered efficiently Long-term reliability and resilience of the pipeline minimising operational interventions
54 | City of Cape Town | CPX.0035915 | Rietvlei Pump Station and Rising Main | Reticulation | Rietvlei | 24621536874.2 | 1 EFF &4 NT UDFG & BICL | IDP | Execution | In progress |  | Medium term |  | Water & Santitation Directorate | Bianca Govender | 2021-10-25 | 2031-01-31 | Reasons: The Rietvlei pump station was commissioned in 1983 and serves an extended catchment of approximately 3000 ha which includes portions of Kuils River, Brackenfell, and Durbanville suburbs. As identified in the City#s Sewer Master Plan, the rapid development taking place in the Northern Suburbs calls for the upgrade of the Rietvlei pump station and rising main to the Bellville WWTW. Sewage is pumped along a DN450mm pipeline of approximate length 2315m to the Bellville WWTW. The pump station does not operate at an acceptable level of service. The pump station experiences regular pump breakdowns due to rags and solids in the raw sewage. In addition, the pump station cannot handle the current flows as regular spilling into the adjacent Kuils River is witnessed. Goal: The construction of a new pump station, sand trap and screening facility in order to accomodate the future ultimate peak flow of 1100 l/s. The project would include the construction of a 900 mm rising main from the new pump station to the WWTW. The pump station will consist of dedicated utility rooms for the MCC, generator and fuel storage. The existing pump station is to be decommisioned and backfilled once the new pump station is fully operational. Comment/Notes: The construction of a new pump station and rising main would hold the following benefits to the City of Cape Town and residents: Improving the public's health and living conditions; Enhanced quality of life; Social equity; Unlocking properties for residential development; Reduction of pollution to natural watercourses; Increased property values; Cost savings; Job creation; Improved business conditions; Enhanced public health; Environmental protection.

## LG Beaufort West Municipali
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance Required | Last Update Date
1 | Beaufort West | Central Karoo | Beaufort West: WWTW Pump Station: Reconstruction of Irrigation Pump Station at Waste Water Treatment Works | DWS | Beaufort West | 9711323.24 | MIG & CRR | DPIP2324/24 | Not registered, to be registered July 2025 | Not registered, to be registered July 2025 |  |  | MIG & CRR | Technical Services
2 | Beaufort West | Central Karoo | Nelspoort: WTW: Upgrading of aerator | DWS | Nelspoort | 18295336.32 | WSIG | DPIP2324/26 | Approved | Approved |  |  | WSIG
3 | Beaufort West | Central Karoo | Beaufort West: Various Areas: Phase3: New High Mast Lights | DMRE | Beaufort West | 7085229.41 | MIG& CRR | DPIP2324/27 | Project Splitted by MIG. To be registered as 4 projects. | Project Splitted by MIG. To be registered as 4 projects. |  |  | MIG& CRR
4 | Beaufort West | Central Karoo | Rev Fass Street (Kwa-Mandlenkosi): Upgrading of Gravel Roads | DOI | Beaufort West | 7260789.79 | MIG& CRR | DPIP2324/28 | Registered | Registered |  |  | MIG& CRR
5 | Beaufort West | Central Karoo | Blankenweg (Hillside): Upgrading of Gravel Roads | DOI | Beaufort West | 14132808.42 | MIG& CRR | DPIP2324/29 | Registered | Registered |  |  | MIG& CRR
6 | Beaufort West | Central Karoo | Murraysburg: Cemetery: Expansion of cemetery site | DFFE | Murraysburg | 6580000 | MIG& CRR | DPIP2324/30 | Registered | Registered |  |  | MIG& CRR | Human Settlements & Technical Services
7 | Beaufort West | Central Karoo | Merweville: Landfill: Specialised waste fleet (yellow plant) | DFFE | Merweville | 3600000 | MIG& CRR | DPIP2324/31 | To be registered in July 2026 | To be registered in July 2026 |  |  | MIG& CRR | Human Settlements & Technical Services
8 | Beaufort West | Central Karoo | Nelspoort: Landfill: Specialised waste fleet (yellow plant) | DFFE | Nelspoort | 4000000 | MIG& CRR | DPIP2324/32 | To be registered in July 2027 | To be registered in July 2027 |  |  | MIG& CRR | Human Settlements & Technical Services
9 | Beaufort West | Central Karoo | Merweville: Landfill: Upgrading of landfill site | DFFE | Merweville | 3600000 | MIG& CRR/ DFFE | DPIP2324/33 | To be registered in July 2026 | To be registered in July 2026 |  |  | MIG& CRR/ DFFE | Human Settlements & Technical Services
10 | Beaufort West | Central Karoo | Nelspoort: Landfill: Upgrading of landfill site | DFFE | Nelspoort | 4000000 | MIG& CRR/ DFFE | DPIP2324/34 | To be registered in July 2027 | To be registered in July 2027 |  |  | MIG& CRR/ DFFE | Human Settlements & Technical Services
11 | Beaufort West | Central Karoo | Upgrading of Vaalkoppies Landfill site | DFFE | Beaufort West | 15000000 | MIG & CRR/ DFFE | IDP 2022/2027 | Planning. Action Plan submitted to DEADP | Planning. Action Plan submitted to DEADP |  |  | MIG & CRR/ DFFE | Human Settlements & Technical Services
12 | Beaufort West | Central Karoo | Material Recovery Facility At Vaalkoppies Waste Disposal Site | DFFE | Beaufort West | 5000000 | MIG & CRR/ DFFE | IDP 2022/2027 | Planning | Planning |  |  | MIG & CRR/ DFFE | Human Settlements & Technical Services
13 | Beaufort West | Central Karoo | Upgrade Old Water Meters To Sts And Monitoring Of All Water Meters to Reduce Unaccounted For Water, Increase Income | DWS | Beaufort West | 20000000 | DWS/ DLG | IDP 2022/2027 | Existing Business Plan | Existing Business Plan |  |  | DWS/ DLG | Water Services
14 | Beaufort West | Central Karoo | Exploration and Augmentation of Aquifers in Beaufort West | DWS | Beaufort West | 5000000 | DWS/ DLG | IDP 2022/2027 | Existing Business Plan | Existing Business Plan |  |  | DWS/ DLG | Water Services
15 | Beaufort West | Central Karoo | Upgrading Of Deteriorating Water Reticulation Network | DWS | Beaufort West | 25000000 | DWS/ DLG | IDP 2022/2027 | Planning | Planning |  |  | DWS/ DLG | Water Services
16 | Beaufort West | Central Karoo | Upgrading of Beaufort West Waste Water Treatment Works | DWS | Beaufort West | 50000000 | WSIG | IDP 2022/2027 | Approved | Approved |  |  | WSIG | Water Services
17 | Beaufort West | Central Karoo | Social Housing: Upgrading Of Nurses Home | DoHS | Nelspoort | 1000000 |  | IDP 2022/2027 | Planning | Planning
18 | Beaufort West | Central Karoo | Installation Of Grid Tied Solar Systems For All Municipal Buildings And Pump Stations For A Total Of 1 Mva | DMRE | Beaufort West | 25000000 | DMRE / CRR | IDP 2022/2027 | Planning | Planning |  |  | DMRE / CRR
19 | Beaufort West | Central Karoo | Storm Water Master Plan And Implementation Plan | DOI | Beaufort West | 50000000 | MIG/ CRR | IDP 2022/2027 | Planning | Planning |  |  | MIG/ CRR | Technical Services
20 | Beaufort West | Central Karoo | 56km Of Gravel Roads In B/West. Mun. Areas | DOI | Beaufort West | 330000000 | MIG/ CRR | IDP 2022/2027 | Planning | Planning |  |  | MIG/ CRR | Technical Services
21 | Beaufort West | Central Karoo | Rehabilitation of 106km tar/paved Roads: Whole Municipal Area | DOI | All Towns | 160000000 | MIG/ CRR | IDP 2022/2027 | Planning | Planning |  |  | MIG/ CRR | Technical Services
22 | Beaufort West | Central Karoo | Upgrading Of Electricity Network In Industrial Area | DMRE | Beaufort West | 4000000 | DMRE / CRR | IDP 2022/2027 | Planning | Planning |  |  | DMRE / CRR | Electrical / Energy
23 | Beaufort West | Central Karoo | Upgrading Of Electricity Network In Lande Area | DMRE | Beaufort West | 8000000 | DMRE / CRR | IDP 2022/2027 | Planning | Planning |  |  | DMRE / CRR | Electrical / Energy
24 | Beaufort West | Central Karoo | Upgrading Of Electricity Network In Rustdene Area | DMRE | Beaufort West | 14000000 | DMRE / CRR | IDP 2022/2027 | Planning | Planning |  |  | DMRE / CRR | Electrical / Energy
25 | Beaufort West | Central Karoo | Upgrading Of Electricity Network In Hillside Area | DMRE | Beaufort West | 6000000 | DMRE / CRR | IDP 2022/2027 | Planning | Planning |  |  | DMRE / CRR | Electrical / Energy
26 | Beaufort West | Central Karoo | Upgrading Of Electricity Network In Essopville | DMRE | Beaufort West | 22000000 | DMRE / CRR | IDP 2022/2027 | Planning | Planning |  |  | DMRE / CRR | Electrical / Energy
27 | Beaufort West | Central Karoo | Upgrading Of Electricity Network In Essopville | DMRE | Beaufort West | 6000000 | DMRE / CRR | IDP 2022/2027 | Planning | Planning |  |  | DMRE / CRR | Electrical / Energy
28 | Beaufort West | Central Karoo | Upgrading Of Electricity Network In Essopville | DMRE | Beaufort West | 4500000 | DMRE / CRR | IDP 2022/2027 | Planning | Planning |  |  | DMRE / CRR | Electrical / Energy
29 | Beaufort West | Central Karoo | Upgrading Of Electricity Network In Nieuveld Park And Rustdene South Of Buitekant Street | DMRE | Beaufort West | 28000000 | DMRE / CRR | IDP 2022/2027 | Planning | Planning |  |  | DMRE / CRR | Electrical / Energy
30 | Beaufort West | Central Karoo | Upgrading Of Electricity Network In Murraysburg Historical Town | DMRE | Murraysburg | 8000000 | DMRE / CRR | IDP 2022/2027 | Planning | Planning |  |  | DMRE / CRR | Electrical / Energy
31 | Beaufort West | Central Karoo | Upgrading Of Electricity Network In Murraysburg Historical Town | DMRE | Murraysburg | 8000000 | DMRE / CRR | IDP 2022/2027 | Planning | Planning |  |  | DMRE / CRR | Electrical / Energy
32 | Beaufort West | Central Karoo | Nelspoort: Upgrade Sportsgrounds Phase 2 (Swimming Pool) | DCAS | Nelspoort | 3295000 | DCAS/ MIG/ CRR | IDP 2022/2027 | Existing Business Plan | Existing Business Plan |  |  | DCAS/ MIG/ CRR | Human Settlements & Technical Services
33 | Beaufort West | Central Karoo | Nelspoort: Upgrade Sportsgrounds Phase 3 (Clubhouse and Netball Courts) | DCAS | Nelspoort | 3472000 | DCAS/ MIG/ CRR | IDP 2022/2027 | Existing Business Plan | Existing Business Plan |  |  | DCAS/ MIG/ CRR | Human Settlements & Technical Services
34 | Beaufort West | Central Karoo | Upgrading of Amore Green Sport Field | DCAS | Beaufort West | 5000000 | DCAS/ MIG/ CRR | IDP 2022/2027 | Planning | Planning |  |  | DCAS/ MIG/ CRR | Human Settlements & Technical Services
35 | Beaufort West | Central Karoo | Upgrading of Murraysburg Sport Field 1 | DCAS | Murraysburg | 17000000 | DCAS/ MIG/ CRR | IDP 2022/2027 | Aplication Submitted | Aplication Submitted |  |  | DCAS/ MIG/ CRR | Human Settlements & Technical Services
36 | Beaufort West | Central Karoo | Upgrading of Murraysburg Sport Field 2 | DCAS | Murraysburg | 5000000 | DCAS/ MIG/ CRR | IDP 2022/2027 | Planning | Planning |  |  | DCAS/ MIG/ CRR | Human Settlements & Technical Services
37 | Beaufort West | Central Karoo | Upgrading of Murraysburg water supply lines | DWS | Murraysburg |  |  |  | Planning | Planning
38 | Beaufort West | Central Karoo | Installation of bulk water meter BW | DWS | Beaufort West |  |  |  | Planning | Planning
39 | Beaufort West | Central Karoo | Develop & Implement Revenue Strategy | NT, PT | Beaufort West |  |  |  | Planning | Planning
40 | Beaufort West | Central Karoo | Develop & Implement Water Resilience Policy | DWS | Beaufort West |  |  |  | Planning | Planning
41 | Beaufort West | Central Karoo | Develop & Implement Credit Control Policy | NT, PT | Beaufort West |  |  |  | Planning | Planning
42 | Beaufort West | Central Karoo | Repairs to Vandalised Switchgear for critical Boreholes | DWS | Beaufort West |  |  |  | Planning | Planning
43 | Beaufort West | Central Karoo | Purchase of Honey Sucker Truck Beaufort West | DWS | Beaufort West |  |  |  | Planning | Planning
44 | Beaufort West | Central Karoo | Old pipe replacement programme all towns | DWS | All Towns
45 | Beaufort West | Central Karoo | Develop & Implement Waster And Sanitation Infrastructure maintenance Rehabilitationplans | DWS | Beaufort West

## LG Bergriver Municipality
No | Municipality | District | Project Name | Sector | Location / Area | Priority | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assitance Required | Last Update Date
1 | Bergrivier Municipality | West Coast | Natural Spring Pipeline Replacement (Water Security) | Water Services | Redelinghuys | 7 | 15000000 | MIG & Co-contribution | IDP, WSDP & Water Master Plan | Feasibility/Business Case (EIA application) | Currently busy with EIA, whereafter design can be finanlised | EIA | Immediate | DWS, DEA&DP, MIG | Technical Services | Leon Janse van Rensburg | 2027-04-01 | 2028-03-01 | Start date depends on the EIA approval. | N/A
2 | Bergrivier Municipality | West Coast | Sewage Oxidation Ponds Upgrade / Septic Tank Eradication | Sanitation | Redelinghuys | 12 | 125000000 | WSIG/MIG/SIDAFF | IDP, WSDP and Sewer Masterplan | Concept/Problem definition | Currently busy with the compilation of Business plan | Funding | Short - Medium | DWS, DLG, SIDDAF | Technical Services | Leon Janse van Rensburg | 2031-09-01 | 2033-04-01 | Dependant on funding. The project entails the equipment of the town with a full waterbourne system. Currently 2 households shares a septic tank with a total volume of 2kl. | Possible funding. The intention is to apply through WSIG. Dependant on approval from DWS.
3 | Bergrivier Municipality | West Coast | Sewage Oxidation Ponds Upgrade / Septic Tank Eradication | Sanitation | Aurora | 13 | 95000000 | WSIG/MIG/SIDAFF | IDP, WSDP and Sewer Masterplan | Concept/Problem definition | Currently busy with the compilation of Business plan | Funding | Short - Medium | DWS, DLG, SIDDAF | Technical Services | Leon Janse van Rensburg | 2033-09-01 | 2035-04-01 | Dependant on funding. The project entails the equipment of the town with a full waterbourne system. Currently 2 households shares a septic tank with a total volume of 2kl. | Possible funding. The intention is to apply through WSIG. Dependant on approval from DWS.
4 | Bergrivier Municipality | West Coast | Aurora Water Treatment Works Upgrade & Borehole Refurbishment | Water Services | Aurora | 6 | 45000000 | WSIG/MIG/Own Contribution | IDP, WSDP & Water Master Plan | Concept/Problem definition | Currently busy with the compilation of Business plan | Funding | Short - Medium | DWS, DLG, SIDDAF | Technical Services | Leon Janse van Rensburg | 2028-09-01 | 2030-03-01 | Project Registered with MIG as a multiyear project. The contractor will be appointed over 3 financial years. | N/A
5 | Bergrivier Municipality | West Coast | Eendekuil WTW Upgrade & Additional Storage (0.4ML) | Water Services | Eendekuil | 4 | 35000000 | Largely own funding with WRG assistance | IDP, WSDP & Water Master Plan | Implementation | Currently busy with construction | Funding - awaiting 2026/2027 budget approval | Immediate | DWS, DLG | Technical Services | Leon Janse van Rensburg & Wikus Burger | 2026-02-01 | 2026-12-01 | Project funded by own funding due to it being urgent. This will unlock futher development and ensure adherence to SANS 241. | Possible counter funding. DLG Water Reseliance Grant provided R1mil.
6 | Bergrivier Municipality | West Coast | Piketberg WTW Sludge Thickener | Sanitation | Piketberg | 14 | 18000000 | MIG/WSIG | IDP, WSDP and Sewer Masterplan | Concept/Problem definition | Consultant to be appointed | Funding | Medium - Long term | DWS, DLG | Technical Services | Errol Witbooi | 2036-08-01 | 2037-02-01 | Project will assist in additional water to be re-used at the water treatment works.
7 | Bergrivier Municipality | West Coast | Piketberg WWTW Inlet Upgrade | Water Services | Piketberg | 8 | 15000000 | WSIG | IDP, WSDP & Water Master Plan | Concept/Problem definition | Consultant to be appointed | Funding | Medium - Long term | DWS | Technical Services | Errol Witbooi | 2034-08-01 | 2035-05-01 | Dependant on funding from WSIG. Business plan to be drafted.
8 | Bergrivier Municipality | West Coast | Velddrif Booster Pumpstation Upgrade | Water Services | Velddrif | 2 | 27000000 | Own Funding | IDP, WSDP & Water Master Plan | Feasibility/Business Case | Currently busy with the final clarifications and data collection prior to Final Design | Funding | Immediate |  | Technical Services | Leon Janse van Rensburg & Wikus Burger | 2028-02-01 | 2029-03-01 | This project will unlock economic development (Industrial, Hotels etc). The tender document and design will be concluded in June 2026. Completion date is established based on funding if approved by Council. | Any possible funding source to fast track the project
9 | Bergrivier Municipality | West Coast | Velddrif Wastewater Treatment Works Upgrade (2.7MLD to 4.5MLD) | Sanitation | Velddrif | 1 | 334000000 | RBIG/SIDAFF | IDP, WSDP and Sewer Masterplan | Concept/Problem definition | Submitted the RBIG Scoping report to DWS | Funding | Immediate | DWS, DLG, DEA&DP | Technical Services | Leon Janse van Rensburg & Wikus Burger | 2028-09-01 | 413547 | Design / Tender and specialist studies to be conlcuded in the 2025/2026 financial year. Council availed R10mill due to the criticality of the project. This project will unlock economic development (Industrial, Hotels etc) | Assistance with the fast tracking of the scoping report to commence with the next phase.
10 | Bergrivier Municipality | West Coast | Albatros Sewage Pumpstation Upgrade | Sanitation | Velddrif | 5 | 2500000 | Own Funding | IDP, WSDP and Sewer Masterplan | Implementation | Construction almost complete |  | Immediate |  | Technical Services | Leon Janse van Rensburg & Wikus Burger | 2026-02-01 | 2026-06-01 |  | Project funded from own funding with construction being concluded in June 2026.
11 | Bergrivier Municipality | West Coast | Pipe Replacement Programme (Noordhoek, Velddrif, Porterville, Piketberg) | Water Services | Municipal Wide | 9 | 40000000 over the next 3 years | MIG & Own funding | IDP, Pipe Replacement Plan | Implementation | Currently busy in Porterville | Funding | Short - Medium Term |  | Technical Services | Errol Witbooi | In progress | On going | Piketberg registered with MIG and to commence in the 2026/2027 financial year.
12 | Bergrivier Municipality | West Coast | Upgrade up bulk water pipeline from Vergelee reservoir to Velddrif | Water Services | Velddrif and Dwarskersbos | 10 | 70000000 | WSIG | WSDP & Water Master Plan | Concept/Problem definition | Consultant to be appointed | Funding | Short Term | WCDM, DWS | Technical Services | Errol Witbooi | 2028-09-01 | 2030-03-01 | Project forms part of the West Coast Master Plan to be concluded in 2030. Funding for this project is however a challenge at the moment.
13 | Bergrivier Municipality | West Coast | Upgrade up bulk water pipeline from Velddrif to Dwarskersbos | Water Services | Dwarskersbos | 10 | 15000000 | Own Funding | WSDP & Water Master Plan | Concept/Problem definition | Consultant to be appointed | Funding | Short Term | WCDM, DWS | Technical Services | Errol Witbooi | 2029-09-01 | 2030-11-01 | Project forms part of the West Coast Master Plan to be concluded in 2030. Funding for this project is however a challenge at the moment.
14 | Bergrivier Municipality | West Coast | Piketberg Bulk Electricity NMD Increase & HV Line Development | Energy | Piketberg | 11 | 5000000 | Own Funding | Electricity masterplan | Concept/Problem definition | Consultant appointed | Funding | Short Term | Eskom, DLG | Electrical Services | Jan Erasmus | 2028-07-01 | 2029-03-01 | Eskom can only upgrade the line from 2028 onwards. Funding will be made available from own funding.
15 | Bergrivier Municipality | West Coast | Velddrif HV Corridor & Substation Upgrade (66kV Ring Feeder) | Energy | Velddrif | 3 | 100000000 | Own Funding | Electricity masterplan | Concept/Problem definition | Consultant appointed | Funding | Medium - Long term | Eskom, DLG | Electrical Services | Jan Erasmus |  |  | Project is dependant on funding and planning from ESKOM's side. Its required of the municipality to issue a gaurantee of R18mil prior to the commencement of the project. Secondly, the upgrading of the feeder line will unlock economic development. | Any possible funding source to fast track the project. Escom can only upgrade the line to 12MVA in 2028 with the 15MVA not being confirmed.

## LG Breede Valley
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding source | Document source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | Last Update Date
1 | Breede Valley Municipality | Cape Winelands | Increase in storage capacity and yield of the Stettynskloof Dam | Water | Rawsonville (-33°50'16" ; 19°14'39") | 248500000 | Loans (Partially funded) | IDP / BVM Risk Strategy | Design | - Feasibility report complete - Geotechnical study and topographical survey ongoing - Consultation with authorities, public and stakeholder groups ongoing - Basic assessment report and specialist studies ongoing - Yield ananlysis ongoing - Council resolution C198/2025 approval of feasibility report and proposal to commence with detail design - Conceptual design initiation February 2026 | - Funding, Require support on RBIG grant application for 2027/28/29/30 FY - Current situation will only enable Agricultural supply until 2030 - Environmental approvals - Updated WUL required | Immediate | DEADP, DWS, DLG, PT | Civil Engineering Services | Z.Sulaiman | 2023-06-01 | 2031-01-01 | Project consist of three major components namely: -Hydro-power component - Access Road upgrade - Dam wall raising The timeines for the initiation of the procurement phase for the above mentioned components are as follows: -Hydro-power component : June 2026 - Access Road upgrade : October 2026 - Dam wall raising : February 2028 | 2026-04-17
2 | Breede Valley Municipality | Cape Winelands | Upgrade of De Doorns Water Treatment Plant | Water | De Doorns (-33°29'10" ; 19°40'00") | 85000000 | WSIG | IDP / BVM Risk Strategy | Procuremet | (1) Appointment of Consultants - 100% Completed. (2) Feasibility Study - 100% Completed (3) Preliminary Design Report - 100% Completed. (4) Final Design Report - 100% completed. (5) Procument (tendering) for Construction of the Works - 95% completed. (6) Construction ( site establishment and construction) of the Works - 0% completed. . (7) Procument (tendering) for Mechanical Works - 80% completed. | Funding - Latest tender results show a drastic increase in project costs both on the Civil and Structural works as well as on the Mechanical and Electrical works | Immediate | DWS, DLG | Civil Engineering Services | Z.Sulaiman | 2026-05-01 | 2028-06-01 | In order to accellerate the project, the department and consultant agreed to stagger the civil engineering services tender with the mechanical electrical tender. This will allow the appointment of a Civil contractor by May 2026. BV1160/2025 was advertised on the 28th of November 2025 Clarification meeting conducted on 08 December 2025 BVM aim to advertise the Mechanical and electrical tender by March 2026. | 2026-04-17
3 | Breede Valley Municipality | Cape Winelands | Upgrade of Touwsrivier Wastewater Treatment Plant | Sewer | Towsrivier (-33°20'42" ; 20°02'13") | 92500000 | MIG / Own funds (CRR) | IDP / BVM Risk Strategy | Implementation | Civil Works : 81% complete Mechanical and Electrical Works : 69.55% complete | - Contractor in penatlty period - Poor performance of consultant - Expired construction permit resulting in prohibition of the works for 51days. Dealing with claims | Immediate | - | Civil Engineering Services | Z.Sulaiman | 2024-05-23 | 2026-10-01 | - Civil contractor is in a penalty period '- Application for extention of existing permit denied as existing construction permit has expired, new application proposed for submission on 12 February 2026 - Expected completion date : September 2026 | 2026-04-17
4 | Breede Valley Municipality | Cape Winelands | Worcester Industrial Development | Water, sewer, roads, stormwater , electricity | Worcester (-33°37'44" ; 19°29'14") | TBC | Own funds (CRR) | IDP | Pre-feasibility / Design | - Conceptualization, specialist studies in process (EIA), - Finalization of the Site Development Plan | Environmental restrictions (- reduction in developable opportunities | Medium term | DEADP, DLG, PT | Civil Engineering Services | Z.Sulaiman | TBC | TBC | Funding required as to | 2026-04-17
5 | Breede Valley Municipality | Cape Winelands | Uitvlug Industrial Development | Water, sewer, roads, stormwater , electricity | Worcester (-33°39'17"; 19°25'36") | TBC | Own funds (CRR) | IDP | Pre-feasibility / Design | - Conceptualization, specialist studies in process (EIA), - Workshiopping of the Site Development Plan | Environmental restrictions (688 to1,363.2 ha offset area required) & development is dependent on the Eastern By-pass. | Medium term | DEADP, DLG, PT | Civil Engineering Services | Z.Sulaiman | TBC | TBC | - | 2026-04-17
6 | Breede Valley Municipality | Cape Winelands | Eastern By-Pass | Roads | Worcester () | Project not implemented by BVM LM | [6 empty] | DoI, DLG, PT | - | N/A | TBC | TBC | - | 2026-04-17
7 | Breede Valley Municipality | Cape Winelands | Western and Eastern By-Pass | Roads | Worcester () | Project not implemented by BVM LM | [6 empty] | DoI, DLG, PT | - | N/A | TBC | TBC | - | 2026-04-17

## LG Bitou Municipality
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Priority | Key Blockages / Constraints | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance Required | Last Update Date
1 | Bitou Municipality | Garden Route | Compile and circulate updated Water, Sewer, and Electrical Master Plans aligned with revised SDF & Capital Expenditure Framework. | Water, Sanitation & Energy | Bitou Municipality | 5000000 | Own, Grant & Donor |  | Concept / Problem definition | On-hold. Funding dependant | Immediate | Funding | DLG, Provincial Treasury | Engineering Services | Mr V Felton | 2026/2027 FY | 2027/2028 FY | The Municipality has been requested to make funding available to undertake the Water, Sanitation and Electrical master Plans in 2026/27 & 2027/28 FY. No funding was provided. |  | 2026-06-23
7 | Bitou Municipality | Garden Route | Bitou Bulk Water Supply Scheme - Wadrift Dam | Water | Bitou Municipality | 200000000 | Own, Grant & Donor |  | Feasibility | DWS provided funding to complete the Implementation Readiness Studies by June 2028 | Long term | Funding | DWS, DLG | Engineering Services | Mr V Felton | Funding Application – 2029/30. | N/A | DWS provided funding to complete the Implementation Readiness Studies in 2025 - 2028 |  | 2026-06-23
8 | Bitou Municipality | Garden Route | Upgrading of the Bulk Water Supply Pipeline From Plett WTP To Matjiesfontein Reservoir. Upgrading of the Bulk Water Supply Pipeline From N2 To Green Valley Green Valley Pump Station And Reservoir | Water | Plettenberg Bay, Keurbooms, Wittedrift and Green Valley | 285000000 | Own, Grant & Donor |  | Preliminary Design | Prelim Design completed and Final Basic Assessment Report was submitted. | Short term | Funding | DWS, DLG | Engineering Services | Mr V Felton | Funding Application – 2027/28 | N/A | The Municipality has made funding available to complete the Implementation Readiness Studies in the 2026/27 FY. |  | 2026-06-23
|  | Garden Route | Upgrading of the Bulk Water Infrastructure in the Greater Keurbooms Area | Water | Keurbooms | 50000000 | Own, Grant & Donor |  | Feasibility | Feasibility completed. On-hold | Long term | Funding | DWS, DLG | Engineering Services | Mr V Felton | Funding Application – 2027/28 | N/A | The Municipality has been requested to make funding available in 2027/28 FY to complete Prelim design and EIA in2027/28- 2028/29 |  | 2026-06-23
9 | Bitou Municipality | Garden Route | Upgrading of the Keurbooms River to Roodefontein Dam Raw Water Transfer Pipeline Assessment | Water | Bitou Municipality | 100000000 | Own, Grant & Donor |  | Design | Detailed design | Immediate | Funding | DWS, DLG | Engineering Services | Mr V Felton | Funding application - 2026/27. | N/A | The Municipality has made funding available to complete the detailed design in 2025/26. Funding is required for implementation. |  | 2026-06-23
9 | Bitou Municipality | Garden Route | Upgrading of the Bulk Water Supply to Kwanokuthula East (6.5 Ml reservoir and Bulk Pipelines) | Sanitation | Kwanokuthula | 100000000 | Own, Grant & Donor |  | Concept | Concept Design | Medium term | Funding | DWS, DLG | Engineering Services | Mr V Felton | Feasibility study planned for 2026/27 FY | N/A | Funding is required to undertake the feasibility study in 2026/27 and then additional funding will be required to complete the Implementation Readiness Studies. |  | 2026-06-23
10 | Bitou Municipality | Garden Route | Upgrading of the Bulk Water Supply to Kranshoek (7 Ml reservoir and Bulk Pipelines) | Water | Kranshoek | 100000000 | Own, Grant & Donor |  | Concept | Concept Design | Medium term | Funding | DWS, DLG | Engineering Services | Mr V Felton | Feasibility study planned for 2026/27 FY | N/A | Funding is required to undertake the feasibility study in 2026/27 and then additional funding will be required to complete the Implementation Readiness Studies. |  | 2026-06-23
11 | Bitou Municipality | Garden Route | Upgrading of the Ganse Vallei Wastewater Treatment Works | Sanitation | Bitou Municipality | 250000000 | Own, Grant & Donor |  | Design | Prelim Design and EIA | Immediate | Funding | DWS, DEADP, DLG | Engineering Services | Mr V Felton | Funding application - 2026/27. | N/A | The Municipality has made funding available to complete the detailed design in 2026/27. Funding is required for implementation. |  | 2026-06-23
12 | Bitou Municipality | Garden Route | Kwanokuthula Bulk Outfall Sewer, Rising Mains and Pumpstation | Sanitation | Kwanokuthula | 130,000,000 Phase 1 - 4 | Own, Grant & Donor |  | Design | Detailed Design Completed - Stage 1 - 4 | Immediate | Funding | DWS, DEADP, DLG | Engineering Services | Mr V Felton | Phase 1 implementation in 2026/27 - 2028/29 | N/A | The Municipality has made funding available to complete the detailed design in2025/26. Funding is required for implementation of Phase 2 - 5 |  | 2026-06-23
13 | Bitou Municipality | Garden Route | Green Valley Bulk Outfall Sewer, Rising Mains and Pumpstation | Sanitation | Plettenberg Bay, Keurbooms, Wittedrift and Green Valley | 125000000 | Own, Grant & Donor |  | Preliminary Design | Prelim Design completed and Final Basic Assessment Report was submitted. | Short term | Funding | DWS, DLG | Engineering Services | Mr V Felton | Funding Application – 2027/28 | N/A | The Municipality has made funding available to complete the Implementation Readiness Studies in the 2026/27 FY. |  | 2026-06-23
|  | Garden Route | Upgrading of the Bulk Sanitation Infrastructure in the Greater Keurbooms Area | Sanitation | Keurbooms | 50000000 | Own, Grant & Donor |  | Feasibility | Feasibility completed. On-hold | Long term | Funding | DWS, DLG | Engineering Services | Mr V Felton | Funding Application – 2027/28 | N/A | The Municipality has been requested to make funding available in 2027/28 FY to complete Prelim design and EIA in 2027/28- 2028/29 |  | 2026-06-23
14 | Bitou Municipality | Garden Route | Ladywood Outfall Sewer and Pumpstations | Sanitation | Ladywood | 35000000 | Own, Grant & Donor |  | Concept / Problem definition | On-hold | Long term | Funding | DWS, DEADP, DLG | Engineering Services | Mr V Felton | Feasibility study planned for 2026/27 FY | N/A | Funding is required to undertake the feasibility study in 2026/27 and then additional funding will be required to complete the Implementation Readiness Studies. |  | 2026-06-23
15 | Bitou Municipality | Garden Route | Kranshoek Outfall Sewer and Pumpstations | Sanitation | Kranshoek | 60000000 | Own, Grant & Donor |  | Concept / Problem definition | On-hold | Long term | Funding | DWS, DEADP, DLG | Engineering Services | Mr V Felton | Feasibility study planned for 2026/27 FY | N/A | Funding is required to undertake the feasibility study in 2026/27 and then additional funding will be required to complete the Implementation Readiness Studies. |  | 2026-06-23
16 | Bitou Municipality | Garden Route | Installation of new Transformer and Associated Infrastructure | Energy | Bitou Municipality | 45000000 | Own, Grant & Donor |  | Concept / Problem definition | On-hold | Long term | Funding | Eskom, DoI, DLG | Engineering Services | Mr V Felton | Feasibility study planned for 2026/27 FY | N/A | Funding is required to undertake the feasibility study in 2026/27 and then additional funding will be required to complete the Detailed design and Implementation. |  | 2026-06-23
17 | Bitou Municipality | Garden Route | Upgrading of Electrical Network | Energy | Bitou Municipality | 10000000 | Own, Grant & Donor |  | Concept / Problem definition | On-hold | Long term | Funding | Eskom, DoI, DLG | Engineering Services | Mr V Felton | Feasibility study planned for 2026/27 FY | N/A | Funding is required to undertake the feasibility study in 2026/27 and then additional funding will be required to complete the Detailed design and Implementation. |  | 2026-06-23
18 | Bitou Municipality | Garden Route | Upgrading of the Kwanokuthula Waste Transfer Station | Waste | Kwanokuthula | 55000000 | Own, Grant & Donor |  | Concept / Problem definition | On-hold | Long term | Funding | GRDM, DEADP, DLG | Community Services | Mr R Williams | Feasibility study planned for 2026/27 FY | N/A | Funding is required to undertake the feasibility study in 2026/27 and then additional funding will be required to complete the Detailed design and Implementation. |  | 2026-06-23

## LG Cape Agulhas
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Funding Source Document | Readiness Stage | Status / Progress | Key Blockages / Constraints | Rankings | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assitance Required | Last Update Date | Comments 18/06/2026
| Cape Agulhas Municipality | Overberg District | L'Agulhas - New Reservoir Ph2 | Water | Agulhas | 15980029.25 | CRR Possible WSIG | Master Plan | Design/Procurement Ready | Started | Funding | 1 | Immediate |  | W&S | B Neale | Start date confined by existing environmental constraints |  | Storage below 72 hours required for Lágulhas. Relocation of reservoir triggered revision to EIA. New site found to be in a mapped Critical Biodiversity Area 1 | Funding Enviro constraints |  | Still trying to identify possible environmental Off-Set area
| Cape Agulhas Municipality | Overberg District | Arniston - Upgrades to WWTW | Sewer | Arniston | 9600000 | CRR Possible MIG |  | Feasibility/Business Case | Not Started | Funding | 1 | Immediate |  | W&S | B Neale | Trying to apply for MIG funding |  | Urgent upgrades required to this dysfunctional WWTW. Also need assistance with licensing this WWTW | Funding Licensing |  | No clear start date. Funding & licensing remain a constraint
| Cape Agulhas Municipality | Overberg District | Bredasdorp - WWTW Upgrade | Sewer | Bredasdorp | 54307729.9 | CRR | Green Drop & License | Concept/Problem definition | Started | Funding | 1 | Immediate |  | W&S | B Neale | Commence in FY2026/27 |  | Urgent capacity upgrades needed to meet increased flows and to support planned new developments. Also need assistance with licensing this WWTW | Funding Licensing |  | No clear start date. Funding & licensing remain a constraint
| Cape Agulhas Municipality | Overberg District | Bredasdorp - Upgrade Vleikloof PS and Rising Main to WWTW | Water | Bredasdorp | 4400000 |  | Master Plan | Concept/Problem definition | Not Started | Funding | 1 | Immediate |  | W&S | B Neale | Project deferred |  | Currently insufficient capacity in supply line between the Vleikloof dam and the water treatment works, as well as from the water treatment works to the lower reservoir. | Funding |  | No budget available. Trying to explore alternative options
| Cape Agulhas Municipality | Overberg District | Bredasdorp - Eliminate Ou Meule Sewer PS | Sewer | Bredasdorp | 3050000 |  | Operational Issue | Concept/Problem definition | Not Started | Funding | 1 | Immediate |  | W&S | B Neale | Commence in FY2026/27 |  | Often experince overflows at this sewerage pump station. In order to address this ongoing problem we are looking at bypassing this pump station with a bulk gravity sewer to the WWTW | Funding |  | Envisaged start date for this project is in the first half of 2027
| Cape Agulhas Municipality | Overberg District | Napier - Upgrade WTW | Water | Napier | 2000000 |  | Operational Issue | Concept/Problem definition | Not Started | Funding | 1 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | Design capacity is 1,7ML/d, but functional constraints on the filtration side limit capacity to 1,2ML/d. | Funding |  | Small budget alocation in FY2026/27 for professional fees to commence with prelim design
| Cape Agulhas Municipality | Overberg District | Struisbaai - Water Infrastructure from New Boreholes | Water | Struisbaai | 11250965 |  |  | Concept/Problem definition | Not Started | Funding | 1 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | Should the drilling and development of two new boreholes in Struisbaai be found to be feasible, new infrastructure will be required to connect these boreholes with the existing water infrastructure. Construction of the required infrastructure will trigger various environmental triggers. | Funding Enviro constraints |  | No budget allocation in FY2026/27. Trying to explore alternative options
| Cape Agulhas Municipality | Overberg District | Struisbaai - Drilling & Testing New Boreholes | Water | Struisbaai | 3000000 |  |  | Pre-feasibility | Not Started | Funding | 1 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | The "Safe Wellfield Yield"of the existing aquifer has been reached and alternative water sources need to be found. Two new boreholes have been identified on a different aqifer in Struisbaai North. These sites need to be drilled and tested for yield and quality. Drilling and equipping these boreholes will trigger various environmental triggers. | Funding Enviro constraints |  | No budget allocation in FY2026/27. Trying to explore alternative options
| Cape Agulhas Municipality | Overberg District | Struisbaai-Equipping SB12 | Water | Struisbaai | 1800000 |  |  | Concept/Problem definition | Not Started | Funding | 1 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | This is an existing abandoned borehole that we are seeking to re-drill, test and equip to add more water to the system. | Funding |  | No clear start date as there is no budget allocation in FY2026/27. Looking to explore alternative options
| Cape Agulhas Municipality | Overberg District | Bredasdorp - Functional Capacity Constraints at WTW | Water | Bredasdorp | 7000000 |  | Operational Issue | Concept/Problem definition | Not Started | Funding | 2 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | WTW has a design capacity of 8ML/d, but there is a functional capacity constraint at the head of works that limits the capacity of plant to about 150m3 per hour, or 3,6ML/day (150x24=3,6ML/day). Exceeding this flow rate results in ‘floc’ carry-over, which affects the quality of water produced by the plant. | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | All Towns - Dedicated Rising Mains | Water | All Towns | 8600000 |  |  | Concept/Problem definition | Not Started | Funding | 2 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | Need additional rising mains from boreholes to meet increased raw water demands | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | Bredasdorp- Equip Boreholes and Supply Pipes | Water | Bredasdorp | 9600000 |  | Operational Issue | Concept/Problem definition | Not Started | Funding | 2 | Short Term |  | W&S | B Neale | Project deferred. Budget constraints |  | Need to develop two new boreholes that have been drilled, together with pipelines to WTW to meet raw water demands. The development of these boreholes will trigger various environmental triggers. | Funding Enviro constraints |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | Bredasdorp - Relocate Water Infrastructure in Watercourse | Water | Bredasdorp | 3600000 |  | Operational Issue | Concept/Problem definition | Not Started | Funding | 2 | Short Term |  | W&S | B Neale | Project deferred. Budget constraints |  | Rising main from WTW to main supply reservoir currently located in a watercourse which easily gets damaged when water starts flowing after heavy rains. When this occurs we are unable to pump water up to the main reservoir. | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | Struisbaai - Water Network Upgrade - Phase 1 (MP) PRJ-CStW-004 | Water | Struisbaai | 7137600 |  | Master Plan | Concept/Problem definition | Not Started | Funding | 2 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | These are upgrades to the supply netwrk from the reservoir and is required in order to support planned major developments in Struisbaai | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | All Towns - Replacement of Water Mains | Water | All Towns | 18000000 |  | Asset Management Plan | Concept/Problem definition | Not Started | Funding | 3 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | Need to replace aging AC pipes. Asset Management Plan, prepared by Zutari in 2021, clearly shows that by 2027 more than half of both the water and wastewater infrastructure will be in a “Very Poor” condition. | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | Arniston - Upper Level Reservoir Capacity Augmentation (MP) PRJ-CWW-001 | Water | Arniston | 6048000 |  | Master Plan | Concept/Problem definition | Not Started | Funding | 3 | Short Term |  | W&S | B Neale | Project deferred. Budget constraints |  | Additional storage required in Arniston to meet minimum 72 hours storage requirement, especially over peak holiday periods | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | Struisbaai-CBD Sewerage Reticulation | Sewer | Struisbaai | 30350000 |  | IDP | Concept/Problem definition | Not Started | Funding | 3 | Short Term |  | W&S | B Neale | Project deferred. Budget constraints |  | No waterborne sewers in the main residential and commercial areas of Struisbaai which is limiting economic activities and growth | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | L'Agulhas - Water Network Upgrade - Phase 1 (MP) PRJ-CLW-004 | Water | Agulhas | 1040400 |  | Master Plan | Concept/Problem definition | Not Started | Funding | 4 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | Upgrades required to supply network to support increased flows and address pressure issues | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | L`Agulhas - Water Demand Management: Implement L`Agulhas UL PRV 1 (MP) PRJ-CLW-005 | Water | Agulhas | 246000 |  | Master Plan | Concept/Problem definition | Not Started | Funding | 4 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | Pressure reducing valves required to address high pressures and reduce water losses | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | Bredasdorp - Water Demand Management: Implement Bredasdorp LL PRV (MP) PRJ-CBW-006 | Water | Bredasdorp | 1928400 |  | Master Plan | Concept/Problem definition | Not Started | Funding | 4 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | Pressure reducing valves required to address high pressures and reduce water losses | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | Bredasdorp - Water Demand Management: Implement Bredasdorp UL PRV 3 (MP) PRJ-CBW-007 | Water | Bredasdorp | 368400 |  | Master Plan | Concept/Problem definition | Not Started | Funding | 4 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | Pressure reducing valves required to address high pressures and reduce water losses | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | Napier - Water Demand Management: Implement Napier PRV Zone (MP) PRJ-CNW-006 | Water | Napier | 1603200 |  | Master Plan | Concept/Problem definition | Not Started | Funding | 4 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | Pressure reducing valves required to address high pressures and reduce water losses | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | Telemetry & SCADA | Water | All Towns | 2000000 |  | Operational Issue | Concept/Problem definition | Not Started | Funding | 2 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | Proper telemetry & SCADA system needed to manage water & sewerage networks and ensure compliance with licenses | Funding |  | No clear start date. Funding remains a constraint
| Cape Agulhas Municipality | Overberg District | Struisbaai - Water Demand Management: Implement Spookdraai PRV (MP) PRJ-CStW-007 | Water | Struisbaai | 775200 |  | Master Plan | Concept/Problem definition | Not Started | Funding | 4 | Immediate |  | W&S | B Neale | Project deferred. Budget constraints |  | Pressure reducing valves required to address high pressures and reduce water losses | Funding |  | No clear start date. Funding remains a constraint
203685924.15
[9 empty] | e.g. Concept/Problem definition, Pre-feasibility, Feasibility/Business Case, Deign/Procurement Ready, Implementation |  |  | 1- High 4 - Low | Immediate, Short, Medium and Long Term
[9 empty] | Concept/Problem definition |  |  |  | Immediate
[9 empty] | Pre-feasibility |  |  |  | Short Term
[9 empty] | Feasibility/Business Case |  |  |  | Medium Term
[9 empty] | Design/Procurement Ready |  |  |  | Long Term
Implementation

## LG Laingsburg
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance Required | Last Update Date
1 | Laingsburg Municipality | Central Karoo | Engage DWS regarding balancing groundwater supply with Floriskraal Dam options, and confirm feasibility / allocation considerations. | Water | Laingsburg | Unknown | Individual travel and accommodation budgets | Water Resiliance stratergy | Cocept | None | Floriskraal management body |  | DWS | Water Services | JX Komanisi | 2026-07-01 | 2027-06-30 |  | Facilitate and desktop concept proofing
2 | Laingsburg Municipality | Central Karoo | Develop rehabilitation programme for old boreholes and wellfield protection, including monitoring schedule and maintenance plan. | water | Laingsburg | 2500000 | WR funding | JG Afrika underground water management | Cocept | 10% JG Afrika report complete | funding | short to medium | DWS | Water Services | JX Komanisi | 2027-01-01 | 2028-06-01 |  | Funding and geohydroligy support
3 | Laingsburg Municipality | Central Karoo | Prepare WWTW & pump station upgrade phasing plan, aligned to future township establishment sequencing. | sanitation | Laingsburg | 48000000 | WSIG | Water and sanitation masterplan | complete; operational | operational | none | - | DWS | Sanitation & Technical Services | JX Komanisi | - | -
4 | Laingsburg Municipality | Central Karoo | Confirm scope and support requirements for Solar PV / energy resilience feasibility and tariff treatment option | Enegry | Laingsburg | 3000000 | ER funding | None | Conceprt | none | None | Long term | DMRE, Eskom | Electro-technical / Energy | JX Komanisi |  |  |  | Funding and or support with lead PSP
5 | Laingsburg Municipality | Central Karoo | Develop landfill capacity plan, including assessment of regional waste transfer and fleet support requirements | Waste Management | Laingsburg | 18000000 | MIG/Private investors | Concept/technical report | prefeasability | prefeasability complete | none | Medium term | CKDM, DEADP | Waste Management | J Mouton
6 | Laingsburg Municipality | Central Karoo | Progress Transnet depot land development planning (zoning, precinct planning, and catalytic use assessment). | Planning | Laingsburg | 70000 | DEADP | Funding Agreement | Implementation | 15% funding allocated | none | Short | PT | LED / Planning | J Mouton

## LG Cederberg
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required (Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assitance Required | Last Update Date
1 | Cederberg Municipality | West Coast | Citrusdal Water security (bulk water) (Elandskloof) | Water | Elandskloof | 9840000 | Unknown | USD cost estimate | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
2 | Cederberg Municipality | West Coast | Eradication of sewerage bucket systems in Elandskloof | Sanitation | Elandskloof | 17400000 | Unknown | USD cost estimate | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
3 | Cederberg Municipality | West Coast | Citrusdal main and residential road upgrade and rehabilitation | Roads & Stormwater | Citrusdal | 50000000 | MIG | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2026/27 | 2029/2030 |  | Funding/EIA/WULA | 2026-04-24
6 | Cederberg Municipality | West Coast | Citrusdal and Clanwilliam Informal Settlement: - All basic services in the informal settlements. | Water/Sanitation/Roads/Electricity | Citrusdal / Clanwilliam | 100000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
7 | Cederberg Municipality | West Coast | Clanwilliam- Roads- Development of a By-Pass to Industrial Area | Roads & Stormwater | Clanwilliam | 140000000 | NDPG/Other | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2026/2027 | 2027/2028 |  | Funding/EIA/WULA | 2026-04-24
8 | Cederberg Municipality | West Coast | Upgrade of Clanwilliam Main road. | Roads & Stormwater | Clanwilliam | 40000000 | MIG | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
9 | Cederberg Municipality | West Coast | Upgrading of Old Kaapse weg from Clanwiiliam to Algeria. | Roads & Stormwater | Clanwilliam | 140000000 | Other | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/28 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
10 | Cederberg Municipality | West Coast | Upgrade of all gravel streets in Clanwiiliam. | Roads & Stormwater | Clanwilliam | 87000000 | MIG | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2026/27 | 2028/29 |  | Funding/EIA/WULA | 2026-04-24
11 | Cederberg Municipality | West Coast | Upgrading of water network, installation of water pipeline, and stormwater upgrade in Crystal Waters. | Water | Clanwilliam | 20000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
13 | Cederberg Municipality | West Coast | Regional Water Treatment Works (Proposed water distribution network West and South- secure and sustain water for all Towns in Cederberg from Clanwilliam after the upgrade of the Dam Project). | Water | Clanwilliam | 1000000000 | RBIG/BFI | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2031/2032 |  | Funding/EIA/WULA | 2026-04-24
14 | Cederberg Municipality | West Coast | Replacement of asbestos water and sewage network pipelines. | Water/Sanitation | All Towns | 1000000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
15 | Cederberg Municipality | West Coast | Replacement of old and outdated Electricity network infrastructure. | Energy/Electricity | All Towns | 100000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
17 | Cederberg Municipality | West Coast | Lighting on Access roads at Citrusdal, Clanwilliam, Graafwater, Elands Bay and Lamberts Bay (Provincial Roads) | Energy/Electricity | All Towns | 25000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
19 | Cederberg Municipality | West Coast | Lack of Residential Housing development (Servicing of plots) | Human Settlement | All Towns | 100000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
20 | Cederberg Municipality | West Coast | Illegal connections to Water and Electricity (High Electricity and Water Losses) | Water/Electricity | All Towns | 100000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
21 | Cederberg Municipality | West Coast | Aging infrastructure Water, Sewage, Electricity and Roads | Water/Sanitation/Roads/Electricity | All Towns | 1000000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
22 | Cederberg Municipality | West Coast | Insufficient water storage in all towns | Water | All Towns | 500000 | WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
23 | Cederberg Municipality | West Coast | Upgrade of sports field in all towns. | Community Facility | All Towns | 150000000 | MIG | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2031/2032 |  | Funding/EIA/WULA | 2026-04-24
24 | Cederberg Municipality | West Coast | Rehabilitation of current waste sites in Cederberg Municipality (Waste reduction minimisation, recycling initiatives) | Solid Waste | All Towns | 180000000 | MIG | Master Plan/IDP | Pre-feasibility | Pre-feasibility | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
25 | Cederberg Municipality | West Coast | Roads / Sidewalks: Tar more roads, including divisional road 2180 and Erasmus Van Zyl Street. | Roads & Stormwater | Graafwater | 8000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
26 | Cederberg Municipality | West Coast | Upgrade to waterborne sewage | Sanitation | Graafwater | 15000000 | MIG | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
27 | Cederberg Municipality | West Coast | Assist with infrastructure at slipway for fishermen | Other | Elands Bay | 100000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
29 | Cederberg Municipality | West Coast | Upgrade the wastewater treatment works | Sanitation | Elands Bay | 50000000 | MIG/WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
30 | Cederberg Municipality | West Coast | Securing of bulk water (Desalination plant and Nortier) | Water | Lamberts Bay | 72500000 | MIG/WSIG | Master Plan/IDP | Feasibility/Business case | Feasibility/Business case | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
31 | Cederberg Municipality | West Coast | Upgrading of sewage network and upgrade of pump stations | Sanitation | Lamberts Bay | 35000000 | WSIG | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2026/2027 | 2027/2028 |  | Funding/EIA/WULA | 2026-04-24
32 | Cederberg Municipality | West Coast | Rehabilitation of all roads | Roads & Stormwater | Lamberts Bay | 20000000 | MIG | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/28 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
33 | Cederberg Municipality | West Coast | Package Plant for water and waste water plants | Water/Sanitation | Rural Areas | 18000000 | WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
34 | Cederberg Municipality | West Coast | Access roads Upgrades (Tarred) | Roads & Stormwater | Rural Areas | 50000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
35 | Cederberg Municipality | West Coast | Eradication of pit latrine systems | Sanitation | Rural Areas | 5000000 | WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
36 | Cederberg Municipality | West Coast | Electricity provision in all small towns. | Energy/Electricity | Rural Areas | 10000000 | Unknown | Master Plan/IDP | Concept/Problem definition | Concept/Problem definition | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
37 | Cederberg Municipality | West Coast | Lambert's Bay Desalination Plant Refurbushment, completion (outfall), solar energy | Water | Lamberts Bay | 70000000 | WSIG | Master Plan/IDP | Feasibility/Business case | Feasibility/Business case | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
38 | Cederberg Municipality | West Coast | Lambert's Bay Lamberst Bay Wellfield Development Phase 3 | Water | Lamberts Bay | 43000000 | RBIG/MIG | Master Plan/IDP | Implementation | Implementation | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
39 | Cederberg Municipality | West Coast | Citrusdal New 3ML Reservoir earmarked for Housing Development | Water | Citrusdal | 30000000 | RBIG/MIG | Master Plan/IDP | Design/Procurement Ready | Design/Procurement Ready | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2026/2027 | 2027/2028 |  | Funding/EIA/WULA | 2026-04-24
40 | Cederberg Municipality | West Coast | Paleisheuwel Refurbishment of delapidated reservoir | Water | Paleisheuwel | 500000 | DLG | Master Plan/IDP | Design/Procurement Ready | Design/Procurement Ready | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2025/2027 | 2026/2027 |  | Funding/EIA/WULA | 2026-04-24
41 | Cederberg Municipality | West Coast | Clanwilliam New 3ML Reservoir (WTW) | Water | Clanwilliam | 45000000 | RBIG/MIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2026/2027 | 2027/2028 |  | Funding/EIA/WULA | 2026-04-24
42 | Cederberg Municipality | West Coast | Clanwilliam Regional WTW (WTW, Bulk Distribution Pipelines West & South, Pumpstations, Storage) | Water | Clanwilliam | 35000000 | RBIG/MIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
43 | Cederberg Municipality | West Coast | Elands Bay Bulk Water Supply from Lambert Bay Desalination Plant | Water | Elands Bay | 250000000 | RBIG/MIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2029/2030 | 2030/2031 |  | Funding/EIA/WULA | 2026-04-24
44 | Cederberg Municipality | West Coast | Graafwater Upgrading of WTW Increase WTW Capacity | Water | Graafwater | Complete | Unknown | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2028/2029 | 2029/2030 |  | Funding/EIA/WULA | 2026-04-24
45 | Cederberg Municipality | West Coast | Wupperthal New Water Treatment Batch Plant | Water | Wupperthal | 7000000 | WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2029/2030 | 2031/2032 |  | Funding/EIA/WULA | 2026-04-24
46 | Cederberg Municipality | West Coast | Wupperthal New 1ML Reservoir | Water | Wupperthal | 1000000 | WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2029/2030 | 2030/2031 |  | Funding/EIA/WULA | 2026-04-24
47 | Cederberg Municipality | West Coast | Lambert's Bay Reservoirs Increase Reservoir Capacity (3ML) | Water | Lamberts Bay | Complete |  | Master Plan/IDP |  | 0 | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
48 | Cederberg Municipality | West Coast | Elands Bay: 3Ml reservoir. | Water | Elands Bay | Complete |  | Master Plan/IDP |  | 0 | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
49 | Cederberg Municipality | West Coast | Graafwater: 1.5Ml reservoir. | Water | Graafwater | Complete |  | Master Plan/IDP |  | 0 | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
50 | Cederberg Municipality | West Coast | Cederberg - Replacement of AC pipes | Water | All Towns | 15000000 | WSIG | Master Plan/IDP | Feasibility/Business Case | Feasibility/Business Case | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
51 | Cederberg Municipality | West Coast | Augmentation of Water Sources Citrusdal | Water | Citrusdal | Complete |  | Master Plan/IDP |  | 0 | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
52 | Cederberg Municipality | West Coast | Water Treatment Package Plants (Paleisheuwel, Leipoltville) | Water | Paleisheuwel/Leipoldtville | 15000000 | MIG/WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
53 | Cederberg Municipality | West Coast | Leipoldtville: Reservoir | Water | Leipoldtville | Complete |  | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
54 | Cederberg Municipality | West Coast | Elandskloof Water Provision (Bulk & Distribution) | Water | Elandskloof | 9840000 | MIG/WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2028/2029 | 2029/2030 |  | Funding/EIA/WULA | 2026-04-24
55 | Cederberg Municipality | West Coast | Elandskloof Sanitation Provision (Bulk & Distribution) | Sanitation | Elandskloof | 17500000 | MIG/WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
56 | Cederberg Municipality | West Coast | Elands Bay: Construction of WWTW | Sanitation | Elands Bay | 50000000 | MIG/WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2028/2029 | 2030/2031 |  | Funding/EIA/WULA | 2026-04-24
57 | Cederberg Municipality | West Coast | Clanwilliam Bulk sewer upgrade from Denne Street to WWTP | Sanitation | Clanwilliam | 5500000 | MIG | Master Plan/IDP | Feasibility/Business Case | Feasibility/Business Case | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
58 | Cederberg Municipality | West Coast | Citrusdal Decommission Heuwelsig Pump Station | Sanitation | Citrusdal | 500000 | Own funding | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2026/2027 | 2027/2028 |  | Funding/EIA/WULA | 2026-04-24
59 | Cederberg Municipality | West Coast | Lamberts Bay Upgrade Nuweland Pump Station and rising main | Sanitation | Lamberts Bay | 800000 | Own funding | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2026/2027 | 2027/2028 |  | Funding/EIA/WULA | 2026-04-24
60 | Cederberg Municipality | West Coast | Elands Bay Future PS upgrades (Elands Bay no. 1 & no. 2) | Sanitation | Elands Bay | 15000000 | MIG/WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
61 | Cederberg Municipality | West Coast | Graafwater New outfall sewers and PS with rising main | Sanitation | Graafwater | 10000000 | MIG/WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2029/2030 |  | Funding/EIA/WULA | 2026-04-24
62 | Cederberg Municipality | West Coast | Clanwilliam Wastewater Treatment Works (Capacity Upgrade) | Sanitation | Clanwilliam | 80000000 | MIG/WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2026/2027 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
64 | Cederberg Municipality | West Coast | Cederberg - Replacement of AC pipes | Sanitation | All Towns | 50000000 | WSIG | Master Plan/IDP | Feasibility/Business Case | Feasibility/Business Case | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2029/2030 |  | Funding/EIA/WULA | 2026-04-24
65 | Cederberg Municipality | West Coast | Elands Bay Upgrade of Bulk Sewer Outfall | Sanitation | Elands Bay | 15000000 | MIG/WSIG | Master Plan/IDP | Concept | Concept | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2028/29 | 2029/30 |  | Funding/EIA/WULA | 2026-04-24
66 | Cederberg Municipality | West Coast | Effluent distribution network for irrigation | Sanitation | All Towns | 10000000 | Unknown | Master Plan/IDP | Feasibility/Business Case | Feasibility/Business Case | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
69 | Cederberg Municipality | West Coast | Development of Transfer Station & Public Solid Waste Drop-off Facilities & Material Recovery Facilities (MRFs) | Solid waste | All Towns | 80000000 | MIG | Master Plan/IDP | Pre-feasibility | Pre-feasibility | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
70 | Cederberg Municipality | West Coast | Citrusdal Reconstruction and rehabilitation roads (Voortrekker & residential roads) | Roads & Stormwater | Citrusdal | 50000000 | MIG | Master Plan/IDP | Feasibility/Business Case | Feasibility/Business Case | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2026/2027 | 2029/2030 |  | Funding/EIA/WULA | 2026-04-24
71 | Cederberg Municipality | West Coast | Cederberg - Upgrade of gravel roads | Roads & Stormwater | All Towns | 500000000 | Unknown | Master Plan/IDP | Feasibility/Business Case | Feasibility/Business Case | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services |  |  |  | Funding/EIA/WULA | 2026-04-24
72 | Cederberg Municipality | West Coast | Clanwilliam Reconstruction and rehabilitation roads | Roads & Stormwater | Clanwilliam | 20000000 | MIG | Master Plan/IDP | Implementation | Implementation | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/28 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
74 | Cederberg Municipality | West Coast | Cederberg Stormwater Network Upgrade | Roads & Stormwater | All Towns | 10000000 | MIG | Master Plan/IDP | Feasibility/Business Case | Feasibility/Business Case | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/28 | 2028/2029 |  | Funding/EIA/WULA | 2026-04-24
78 | Cederberg Municipality | West Coast | Alternative Energy Sources Supply (Solar/Hydro/Wind) | Energy/Electricty | All Towns | 250000000 | INEP | Master Plan/IDP | Design/Procurement Ready | Design/Procurement Ready | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2031/2032 |  | Funding/EIA/WULA | 2026-04-24
79 | Cederberg Municipality | West Coast | Clanwilliam - Development of Government Precinct | Social | Clanwilliam | 200000000 | NDPG/Other | Master Plan/IDP | Feasibility/Business Case | Feasibility/Business Case | Funding/EIA/WULA | Immediate, Short, Medium and Long Term | SIDAFF/DEA&DP/DWS | Technical Services | Director Technical Services | 2027/2028 | 2031/2032 |  | Funding/EIA/WULA | 2026-04-24

## LG Drakenstein
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assitance Required | Last Update Date
1 | Drakenstein Municipality | Cape Winelands | Paarl WWTW Upgrade (completion of full scope) | Sanitation | Paarl | 600000000 | BFI, external loan, SIDAFF |  | Under construction with BFI funding. Completion of full scope is funding dependent. | Implementation | Funding | Immediate | DWS, DLG | Water & Sanitation | Joseph Barnard | Under construction | 2028/29 |  | Funding | 2026-04-01
2 | Drakenstein Municipality | Cape Winelands | Paarl Taxi Rank Upgrade | Transport | Paarl | 120000000 | Unfunded |  | Concept design | Planning | Funding | Medium | DLG, PT | Transport / Technical Services | Harry Liedeman | 2027/28 | 2030/31 |  | Funding | 2026-04-01
3 | Drakenstein Municipality | Cape Winelands | Paarl CBD Upgrade | Economic development | Paarl | 250000000 | Unfunded |  | Pre-feasibility | Planning | Funding | Long term | DLG, PT | Planning & Technical Services | Wayne Hendricks | 2027/28 | 2030/31 |  | Funding | 2026-04-01
4 | Drakenstein Municipality | Cape Winelands | Paarl South Class 3 Road (Southern Corridor) | Transport | Paarl | 300000000 | Unfunded |  | Pre-feasibility | Planning | Funding | Medium | DoI, DLG | Roads & Stormwater | Harry Liedeman | 2028/29 | 2032/33 |  | Funding | 2026-04-01
5 | Drakenstein Municipality | Cape Winelands | Upgrading of MR 189 (from N1 - Urban Edge) | Transport | Paarl | 400000000 | Unfunded |  | Pre-feasibility | Planning | Funding | Medium | DoI, DLG | Roads & Stormwater | Harry Liedeman | 2027/28 | 2029/30 |  | Funding | 2026-04-01
6 | Drakenstein Municipality | Cape Winelands | Upgrading of Berg River Boulevard (Optenhorst - R45) | Transport | Paarl | 240000000 | Unfunded |  | Pre-feasibility | Planning | Funding | Medium | DoI, DLG | Roads & Stormwater | Harry Liedeman | 2028/29 | 2030/31 |  | Funding | 2026-04-01
7 | Drakenstein Municipality | Cape Winelands | Bulk Sewer along MR 189 (Old Paarl) | Sanitation | Paarl | 150000000 | Unfunded |  | Pre-feasibility | Planning | Funding | Medium | DWS, DLG | Sanitation & Technical Services | Joseph Barnard | 2028/29 | 2030/32 |  | Funding | 2026-04-01
8 | Drakenstein Municipality | Cape Winelands | Bulk Sewer R301 to Carolina Road | Sanitation | Paarl | 60000000 | Unfunded |  | Pre-feasibility | Planning | Funding | Medium | DWS, DLG | Sanitation & Technical Services | Joseph Barnard | 2028/29 | 2030/32 |  | Funding | 2026-04-01
9 | Drakenstein Municipality | Cape Winelands | Extention of Wellington Landfill Site | Waste | Wellington | 180000000 | External Loan |  | Design | Planning | Funding | Immediate |  |  | Thys Serfontein | 2026/27 | 2029/30 |  | Funding | 2026-04-01
10 | Drakenstein Municipality | Cape Winelands | Upgrade of CBD existing 11kV ring feeds (Lady Grey / New Street Development) | Electricity | Paarl | 105000000 | Unfunded |  | Procument ready | Planning | Funding | Medium | Eskom, DLG | Electrical / Energy Services | Leon Laing | 2027/28 | 2028/29 |  | Funding | 2026-04-01
11 | Drakenstein Municipality | Cape Winelands | Upgrade of Dalweiding Substation | Electricity | Paarl | 70000000 | Unfunded |  | Procument ready | Phased implementation as funding becomes available | Funding | Medium | Eskom, DLG | Electrical / Energy Services | Leon Laing | 2026/27 | 2027/28 |  | Funding | 2026-04-01
12 | Drakenstein Municipality | Cape Winelands | Bulk Infrastructure to Unlock Development of N1 Corridor | Water & Sanitation | Paarl | 1901000000 | Unfunded |  | Pre-feasibility | Planning | Funding | Long term | DLG, PT | Water & Waste Water | Joseph Barnard | 2027/28 | 2031/32 |  | Funding | 2026-04-01

## LG Hessequa
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assitance Required | Last Update Date
1 | Hessequa Municipality | Garden Route | Upgrading of Hoofweg Stilbay | Public Works | Stillbay | R 50 million | TBC | Concept | Planning | Traffic flow | Medium and Long Term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
2 | Hessequa Municipality | Garden Route | Stilbaai: Water Bulk Water Upgrade | Water Services | Stillbay | R 40 million | TBC | Concept | Planning | n/a | Medium - Long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
3 | Hessequa Municipality | Garden Route | Heidelberg: Upgrade Duivenhoks WTW | Water Services | Heidelberg | R 50 million | DLG | concept | Planning | Housing / Private Development | Medium - Long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
4 | Hessequa Municipality | Garden Route | Witsand: Water Supply for township development | Water Services | Witsand | R 50 million | TBC | Concept | Planning | Private development | Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
5 | Hessequa Municipality | Garden Route | Riversdale: Upgrade WTW | Water Services | Riversdale | R 20 million | Loan | Concept | Planning | Population growth | Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
6 | Hessequa Municipality | Garden Route | Witsand: Water supply pipeline for town development | Water Services | Witsand | R 30 million | TBC | Concept | Planning | Population growth | Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
7 | Hessequa Municipality | Garden Route | Witsand: New Reservoir | Water Services | Witsand | R 15 million | TBC | Pre-feasibility | Planning | Private development | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
8 | Hessequa Municipality | Garden Route | Slangrivier: Upgrade pipe line, Heidelberg and Slangrivier. | Water Services | Slangrivier | R 20 million | TBC | Concept | Planning | Housing / Private Development | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
9 | Hessequa Municipality | Garden Route | Riversdale: New reservoir | Water Services | Riversdale | R 12 million | TBC | concept | Planning | Population growth | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
10 | Hessequa Municipality | Garden Route | Witsand: Parallel pipe reinforcement | Water Services | Witsand | R 15 million | CRR | Planning | Planning | n/a | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
11 | Hessequa Municipality | Garden Route | Riversdale: Main Pipe | Water Services | Riversdale | R 10 million | TBC | Concept | Planning | n/a | short term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
12 | Hessequa Municipality | Garden Route | Albertinia: 3Ml Reservoir | Water Services | Albertinia | R21 million | TBC | Concept | Planning | Future development | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
13 | Hessequa Municipality | Garden Route | Heidelberg - 2 Ml Reservoir | Water Services | Heidelberg | R 10 million | TBC | Concept | Planning | Population growth | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
14 | Hessequa Municipality | Garden Route | Stilbaai: 2Ml Reservoir | Water Services | Stillbay | R 20 million | Loans / Other Funding Sources | Concept | Planning | Private development | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
15 | Hessequa Municipality | Garden Route | Melkhoutfontein: Upgrade WTW | Water Services | Melkhoutfontein | R 10 million | TBC | Concept | Planning | n/a | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
16 | Hessequa Municipality | Garden Route | Gouritzmond: Upgrade WTW | Water Services | Gouritsmond | R 10 million | TBC | Concept | Planning | n/a | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
17 | Hessequa Municipality | Garden Route | Gouritsmond: 0.4Ml Reservoir | Water Services | Gouritsmond | R 5 million | TBC | Concept | Planning | n/a | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
18 | Hessequa Municipality | Garden Route | Albertinia: Colour remove plant | Water Services | Albertinia | R 10 million | TBC | Concept | Planning | n/a | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
19 | Hessequa Municipality | Garden Route | Melkhoutfontein: 0.2Ml Reservoir | Water Services | Melkhoutfontein | R2,5 million | TBC | Concept | Planning | Housing / Private Development | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
20 | Hessequa Municipality | Garden Route | Melkhoutfontein: Pump station | Water Services | Melkhoutfontein | R 5 million | TBC | Concept | Planning | n/a | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
21 | Hessequa Municipality | Garden Route | New Bulk Infrastructure - Resource Korentepoort yield study | Water Services | Riversdale | R 30 million | TBC | Concept | Planning | Housing / Private Development / Population growth | Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
22 | Hessequa Municipality | Garden Route | Heidelberg: Parallel Pipe Reinforcement | Water Services | Heidelberg | R 32 million | TBC | Concept | Planning | n/a | Short - Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
23 | Hessequa Municipality | Garden Route | Witsand: Chlorination equipment | Water Services | Witsand | R 34 million | TBC | Concept | Planning | n/a | Medium - long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
24 | Hessequa Municipality | Garden Route | UPGRADE BULK SEW LINE AND PUMPSTAT H/B | Sanitation Services | Heidelberg | R 2,5 million | TBC | Concept | Planning | network capacity | Short - Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
25 | Hessequa Municipality | Garden Route | New 2ML Reservoir, Bulk Water Main and Borehole P/S - SB | Water Services | Stillbay | R 10 million | TBC | Concept | Planning | developments / capacity | Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
26 | Hessequa Municipality | Garden Route | Material Recovery Facility | Solid Waste Management | Hessequa | R 30 million | TBC | Concept | Planning | n/a | Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
27 | Hessequa Municipality | Garden Route | ENERGY EFFICIENCY & DEMAND SIDE LOAD MAN | Electricity Services | Hessequa | R 4 million | EEDSM Grant | Concept | Planning | Housing Projects | Short - Medium term | yes | Technical Services | Silent Chikamhi |  |  |  | yes
28 | Hessequa Municipality | Garden Route | NEW WATER TREATMENT WORKS HB (Bloekombom dam lining) | Water Services | Heidelberg | R 34 million | Department of Infrastructure & Municipal CRR | Concept | Planning | Housing / Future developments | Short - Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
29 | Hessequa Municipality | Garden Route | Ring feed Aloeridge Bali 11kV RD | Electrical Services | Riversdale | R 3,5 million | Loans | Concept | Planning | n/a | medium | yes | Technical Services | Silent Chikamhi |  |  |  | yes
30 | Hessequa Municipality | Garden Route | Chlorination tank, Clarifier and Sand beddings (Albertinia WWTW) | Sanitation Services | Albertinia | R 10 million | MIG | Concept | Planning | n/a | medium | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
31 | Hessequa Municipality | Garden Route | Riversdale water Demand Management and Update of Hessequa water Master Plan (phase 1) | Water Services | Riversdale | R 1,6 million | Proposed FY 25/26 Mun W Grant | Concept | Procurement | Housing / Private Development / Population growth | Immediate | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2026-06-30 |  | yes
32 | Hessequa Municipality | Garden Route | New Reticulation system - Albertinia | Water Services | Albertinia | R 30 million | CRR | Concept | Planning | Network capacity | Short - Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2030-06-30 |  | yes
33 | Hessequa Municipality | Garden Route | New Reticulation system - Heidelberg | Water Services | Heidelberg | R 2 million | CRR | Concept | Planning | Network capacity | Short term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2029-06-30 |  | yes
34 | Hessequa Municipality | Garden Route | Upgrading of water infrastructure - Heidelberg | Water Services | Heidelberg | R 5 million | CRR /Loan | Concept | Planning | Network capacity | Short -medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2029-06-30 |  | yes
35 | Hessequa Municipality | Garden Route | Upgrading of Water Network | Water Services | Riversdale | R 10 million | MIG | Concept | Planning | Network capacity | Short - Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2029-06-30 |  | yes
36 | Hessequa Municipality | Garden Route | Refurbishment & Groundwater Investigation: Water Treatment Works | Water Services | Albertinia | R 4,1 million | TBC | Concept | Planning | Housing / Private Development / Population growth | Short - Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2029-06-30 |  | yes
37 | Hessequa Municipality | Garden Route | Equipment and connection of boreholes existing water networks in the Hessequa Municipal Area | Water Services | Hessequa | R 3,5 million | TBC | Concept | Planning | Housing / Private Development / Population growth | Short - Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2028-06-30 |  | yes
38 | Hessequa Municipality | Garden Route | Upgrading of water treatment work | Water Services | Albertinia | R 10 million | TBC | Concept | Planning | Housing / Private Development / Population growth | Medium - Long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
39 | Hessequa Municipality | Garden Route | Construction of additional dam, reedbed and irrigation system | Sanitation Services | Gouritsmond | R 1 million | CRR /Loan | Concept | Planning | Population growth | Medium - Long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2027-06-30 |  | yes
40 | Hessequa Municipality | Garden Route | Upgrading of water infrastructure | Water Services | Heidelberg | R 5 million | CRR/ Other sources to be obtain | Concept | Planning | Network capacity | Medium - Long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2029-06-30 |  | yes
41 | Hessequa Municipality | Garden Route | Installation of water reticulation erf 22 -R/D | Water Services | Riversdale | R 2 million | CRR | Concept | Planning | Private Development | Short -medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2027-06-30 |  | yes
42 | Hessequa Municipality | Garden Route | Refurbishment of the Water Treatment Works (ponds) | Water Services | Riversdale | R 3 million | CRR / other | Concept | Planning | Population growth / Future Development | Medium - Long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC |  | yes
43 | Hessequa Municipality | Garden Route | Spring protection zoning for the Jongensfontein Water Supply | Water Services | Jongensfontein | R 3 million | CRR | Concept | Planning | n/a | Short -medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2029-06-30 |  | yes
44 | Hessequa Municipality | Garden Route | Well-interference and groundwater modelling for Albertinia Wellfield | Water Services | Albertinia | R 1 million | Others | Concept | Planning | n/a | Medium - Long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC depending of approval of funds |  | yes
45 | Hessequa Municipality | Garden Route | Groundwater management plan – General Implementation (Albertinia, Gouritzmond, Melkhoutfontein, Jongensfontein, Vermaaklikheid, Witsand and Stilbaai) | Water Services | Hessequa | R 0,4 million | DLG | Concept | Planning | n/a | Immediate | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC by DLG |  | yes
46 | Hessequa Municipality | Garden Route | WULA applications – General Implementation (Albertinia, Gouritzmond, Melkhoutfontein, Jongensfontein, Vermaaklikheid, Witsand and Stilbaai) | Water Services | Hessequa | R 1 million | DLG | Concept | Planning | n/a | Immediate | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC by DLG |  | yes
47 | Hessequa Municipality | Garden Route | Riversdale Waste Water Treatment Works | Sanitation Services | Riversdale | R 15,5 million | MIG | Concept | Planning | Housing / Private development / Population growth | Short team | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2027-06-30 |  | yes
48 | Hessequa Municipality | Garden Route | Conducting EIA and WULA study for the new boreholes in Witsand | Water Services | Witsand | R 0,5 million | CRR | Implementation | In process | Private Development | Medium to long term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2026-06-30 |  | yes
49 | Hessequa Municipality | Garden Route | Replace of old asbestos pipes | Water Services | Riversdale | R 30 million | CRR and Other of funding need to be sourced | Concept | Planning | Network capacity | Short - medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC, depending of the availability of funds |  | yes
50 | Hessequa Municipality | Garden Route | Construction of new 1 ML Reservoir | Water Services | Jongensfontein | R 9 million | CRR | Concept | Planning | Private Development | Short term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2027-06-30 |  | yes
51 | Hessequa Municipality | Garden Route | Construction of 3 ML Water Treatment Plant with associated reticulation | Water Services | Heidelberg | R 32 million | Department of Public Infrastructure | Concept | Planning | Housing / Private development / Population growth | Short term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | 2028-06-30 |  | yes
52 | Hessequa Municipality | Garden Route | Construction of a 2ML Reservoir,Pumpstation, 35km bulk water main | Water Services | Witsand | R 60 million | TBC | Concept | Planning | Future development | Medium term | yes | Technical Services | Rhuschan Manho/Shahida Kennedy |  | TBC , depeding on the availability of funds |  | yes

## LG George
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required (Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance Required | Last Update Date
1 | George Municipality | Garden Route | Confirm WWTW capacity upgrade phasing and compliance roadmap. | Sanitation | George Municipal Area | TBC | Municipal own funding | Master plan | Master plan report | Completed | None | Low | DWS, DEADP, DLG | Wastewater Services | Melanie |  |  |  | None
2 | George Municipality | Garden Route | Submit housing-linked bulk infrastructure rollout plan for Syferfontein | [9 empty] | DHS, DLG, Provincial Treasury | Human Settlements & Technical Services
3 | George Municipality | Garden Route | Submit housing-linked bulk infrastructure rollout plan for Thembalethu | [6 empty] | UISP Areas 1, 3,4, 5, 6, 8 Bulk infrastructure in place. Once this programme restarts effort will be applied to put other infrastructure in place. The emergency IBS project at "Old All-Brick" area was stopped by informal dwellers HS to resolve this to allow project to proceed. |  |  |  | Human Settlements & Technical Services
4 | George Municipality | Garden Route | Submit housing-linked bulk infrastructure rollout plan for Pacaltsdorp | [10 empty] | Human Settlements & Technical Services
5 | George Municipality | Garden Route | Submit housing-linked bulk infrastructure rollout plan for Wilderness. | [10 empty] | Human Settlements & Technical Services
6 | George Municipality | Garden Route | Confirm substation firm-capacity plan (Herold’s Bay) and NMD application timeline for Wilderness. | [9 empty] | Eskom, DLG | Electro-technical | D. Greeff
7 | George Municipality | Garden Route | Develop interim plan for solid waste transfer post-Gwaing landfill closure. | [9 empty] | GRDM, DEADP | Waste Management
8 |  |  | Railway line- Transporting waste to Mossel Bay.
9 | George Municipality | Garden Route | Investigate and propose builders’ rubble management solution (crusher procurement/alternative disposal site). | [9 empty] | GRDM, Department of Infrastructure, DEADP | Waste Management
10 | George Municipality | Garden Route | Align local catalytic projects (water augmentation, energy resilience, bulk services) with district and provincial catalytic programme submissions. | [9 empty] | GRDM, DLG, Provincial Treasury | All relevant departments | D. Greeff
11 | George Municipality | Garden Route | Add George’s pending permits (EIAs, WULAs, NMD approvals) to the district-wide permitting unblocker list. | Water, Sanitation, Roads& Stormwater | George; Uniondale; Haarlem | >R1 000 000 000 | IUDG & Municipal own counter funding | Concept & viability design reports | Concept & Viability stage | Dividing work in work packages to start roll-out to have impact in various areas, | Funding, Environmental and WULA approvals | High | DLG, DEADP, Eskom, DWS, BOCMA & DFFE | Technical Services | Melanie / Adrian | 2025-07-01 | 2035-06-30 | Roll out of pipe replacement (water and sewer) in line with Pipe Replacement Programme and Stormwater and road upgrades in approved Stormwater master plans in all areas of George, Haarlem and Uniondale. Consultants appointed and investigations underway. Small work packages to roll-out as identified. | Fast track of support to BOCMA (currently 9 months instead of promulgated 3 months); DEADP (BAR approx 6 months) and additional Implementation Funding to support roll-out in the various areas. Standardised guidelines required from DFFE as each project is evaluated and approved differently with varying timelines and cost impacts. | 2026-06-24
12 | George Municipality | Garden Route | Provide updated datasets (water demand modelling, housing growth areas, electricity load forecasts) to the JDMA secretariat repository. | Various | George; Uniondale; Haarlem |  | Municipal own funding | Master plans, MSDF, IDP | N/A | Civil Engineering: information available but level of information required to be stated by DLG with motivation |  | Low | GRDM (JDMA Secretariat), DLG | Planning & Technical | Melanie |  |  | Detail of information required by DLG (JDMA) to be motivated. |  | 2026-06-30
13 | George Municipality | Garden Route | WRF Upgrade (Cost: R690 m; Status: Concept design, NEMA & WUL process; Planned completion: 2031/32) | Water | George | 690000000 | Loan | Concept & viability design report | Concept & viability stage | Finalisation of concept design. WUL process to commence. | Funding | High | DWS, DLG | Infrastructure Planning | Melanie |  |  |  | Funding to support PPP
14 | George Municipality | Garden Route | Uniondale, Haarlem & George GW (Hydrogeological exploration only) | Water | George Municipal Area | 57000000 | Loan | Bulk raw water resource study | Desktop assessments | Field investigations to commence. | Funding | High | DWS, DLG | Infrastructure Planning | Melanie |  |  |  | Funding for implementation
15 | George Municipality | Garden Route | Uniondale & Haarlem GW (production) | Water | George Municipal Area | 46000000 | None | N/A | N/A | Subject to outcome of exploration phase | Funding | High | DWS, DLG | Infrastructure Planning | Melanie |  |  | Estimate for production | Funding required post completion of exploration phase for implementation
16 | George Municipality | Garden Route | Digital water meter installation | Water | George Municipal Area | 360000000 | None | N/A | N/A | Installation of digital water meters installed on water new/upgraded infrastructure. No funding for retrospective upgrades | Funding | High | DWS, DLG | Water Services | Deon
17 | George Municipality | Garden Route | Upgrade bulk water pipeline to Wilderness | Water | Wilderness | 23000000 | Loan | Inception report | Concept & viability design stage | Investigations underway to develop / inform concept & viability design development | Funding | High | DWS, DLG | Infrastructure Planning | Melanie |  |  |  | Funding for implementation
18 | George Municipality | Garden Route | New Potable Water Storage Reservoir | Water | George | 121900000 | Loan | Concept & viability design report | Concept & viability design stage | Detail design development underway. NEMA processes underway | Funding | Medium | DWS, DLG | Infrastructure Planning | Melanie |  |  |  | Funding for implementation
19 | George Municipality | Garden Route | Garden Route Dam Raw Water PS 1 upgrade | Water | George | 74750000 | Loan | Concept & viability design report | Concept & viability design stage | Finalisation of concept design. NEMA process underway | Funding | Medium | DWS, DLG | Infrastructure Planning | Melanie |  |  |  | Funding for implementation
20 | George Municipality | Garden Route | Uniondale 500kL reservoir & associated pipelines - phase 1 | Water | Uniondale | 63250000 | Loan | Detail design | Tender documentation | Tender documentation developed | Funding | High | DWS, DLG | Project Management Unit | Adrian | 2027-07-01 | 2029-06-30 | Approvals and tender document in place. Funding cuts due to BFI insurance needs have elayed roll-out by one year. | Funding for Implementation required. | 2026-06-24
21 | George Municipality | Garden Route | Gwaing WWTW - Extend Capacity 10,0 ml | Sanitation | George | 1184500000 | Loan | Concept & viability design report | Detail design | Detail design finalisation & NEMA/WUL authorisations in final stages | Funding | High | DWS, DEADP, DLG | Infrastructure Planning | Melanie |  |  |  | Counter funding to support BFI application
22 | George Municipality | Garden Route | Thembalethu Eastern Bulk Sewer Upgrade | Sanitation | Thembalethu, George | 290000000 | IUDG & Municipal own counter funding | Concept & viability design report | Concept & viability design stage | Detail design development & NEMA/WUL authorisations in final stages | Funding | High | DWS, DEADP, DLG | Infrastructure Planning | Melanie | 2025-07-01 | 2035-06-30 | Pipeline EA expected in April 2026 and Pumpstation in August 2026. No funding available to implement project. | Funding for Implementation required. | 2026-05-14
23 | George Municipality | Garden Route | George Biosolids Beneficiation Facility | Sanitation | George | 270250000 | Loan | Concept & viability design report | Concept & viability design stage | Detail design development underway | Funding | High | DWS, DEADP, DLG | Infrastructure Planning | Melanie |  |  |  | Counter funding to support BFI application
24 | George Municipality | Garden Route | Herolds Bay Bulk Sewer Upgrade | Sanitation | Herold's Bay, George | 120750000 | Loan | Detail design | Detail design | Tender documentation development to follow NEMA process underway. | Funding | Medium | DWS, DEADP, DLG | Infrastructure Planning | Melanie |  |  |  | Funding for implementation
25 | George Municipality | Garden Route | Thembalethu Sewer Pump Station 6 | Sanitation | Thembalethu, George | 95000000 | IUDG & Municipal own counter funding | Tender document | Construction | Construction | None | High | DWS, DEADP, DLG | Project Management Unit | Adrian | 2025-01-06 | 2027-01-21 | Construction underway. Some additional work has been identified for a new robust pipe bridge and damage to access road requires rehabilitation. This will require a second phase to the project. | Funding for implementation for extra works. | 2026-06-24
26 | George Municipality | Garden Route | Herolds Bay WWTW Upgrade | Sanitation | Herold's Bay, George | 172500000 | Loan funding | Concept & viability design report | Concept & viability design report | Offshore discharge feasibility assessments underway to inform decision making for detail design development. | Funding | High | DWS, DEADP, DLG | Infrastructure Planning | Melanie |  |  |  | Funding for implementation
27 | George Municipality | Garden Route | Pacaltsdorp Sewer PS3 upgrade and associated pipelines | Sanitation | Pacaltsdorp, George | 184000000 | Loan | PS: Detail design Pipelines: Tender document | PS: Tender document development Pipelines: Construction | PS: Tender document development Pipelines: Construction | Funding | High | DWS, DEADP, DLG | Project Management Unit | Adrian | 2025-07-01 | 2029-06-30 | Ph1 completed; Ph2 (Earthworks) to be advertised towards August /September 2026 and Ph3 pumpstation upgrade will follow once funding secured. Approvals in place. | Funding for Implementation required. | 2026-06-24
28 | George Municipality | Garden Route | Eden, Skaapkop & Meul PS | Sanitation | George | 141800000 | RBIG & municipal counter funding | Tender document | Construction | Construction underway | None | Low | DWS, DEADP, DLG | Project Management Unit | Kosie
29 | George Municipality | Garden Route | Rand Str & Rosedale Main Road Extension | Roads & Stormwater | George | 690000000 | Loan / Municipal own funding | Concept & viability design report | Concept & viability design report | Detail design development underway. NEMA / WUL processes underway | Funding | High | DoI, DLG, GRDM | Infrastructure Planning | Melanie |  |  |  | Funding for project development
30 | George Municipality | Garden Route | Upgrade Nelson Mandela Boulevard | Roads & Stormwater | Thembalethu, George | 230000000 | Loan, Municipal Own funding + NDPG | Concept & viability design report | Concept & viability design | Concept & viability design underway | Funding Encroachments into road reserve | Medium | DoI, DLG, GRDM | Infrastructure Planning | Melanie |  |  |  | Funding for project development & dealing with encroachments
31 | George Municipality | Garden Route | Upgrade George South Stormwater | Stormwater | George | 347300000 | Loan funding | Concept & viability design | Concept & viability design | Detail design development underway | Funding | High | DoI, DLG, GRDM | Infrastructure Planning | Melanie | 2026-07-01 | 2030-06-30 | Urgent flood response needed; Phase 1 completed. | Funding for implementation | 2026-05-14
32 | George Municipality | Garden Route | GIPTN Infrastructure Programme (Roads Rehabilitation, Terminals, Transfer Locations, Bus Stops, Sidewalks, etc.) | Roads & Stormwater | George | 6793000000 | PTNG/BFI | Concept & viability design | Concept & viability design | Programme is in varies stages | Funding | High | DoI, DLG, GRDM | Roads & Stormwater | Ryno | 2026-07-01 | 2034-07-01 | The infrastructure programme is required to support and enable the effective operation of the public transport system (Go George). | The PTNG grant is in the process of being phased out. Therefore, alternative funding for implementation is required. | 2026-05-14
32 | George Municipality | Garden Route | Go George Depot | Roads & Stormwater | George | 527000000 | PTNG/BFI | Detail design report | Tender documentation/Construction | Detail design development underway | Funding | High | DoI, DLG, GRDM | Roads & Stormwater | Ryno | 2026-07-01 | 2028-09-01 | The Go George Depot needs to be developed on municipal property to enable, support, and accommodate the operational requirements of the public transport system.. | The PTNG grant is in the process of being phased out. Therefore, alternative funding for implementation is required. | 2026-05-14
33 | George Municipality | Garden Route | York Street widening | Roads & Stormwater | George | 130000000 | Proclaimed road 80% Province 20% Municipality | Concept & viability design report | Concept & viability design report | Detail design development to commence 2026/27 | Funding | High | DoI, DLG, GRDM | Roads & Stormwater | Lionel |  |  |  | Funding for implementation
34 | George Municipality | Garden Route | Compost facility – Finalisation of the compost facility platforms | [9 empty] | DEADP, DLG, GRDM | Waste Management
35 | George Municipality | Garden Route | New ramp at the Waste Transfer Station – Construction of a ramp at the Waste Transfer Station, and procurement of bulky waste crushers | [9 empty] | DEADP, DLG, GRDM | Waste Management
36 | George Municipality | Garden Route | New landfill site – Construction of a landfill site for builders rubble | [9 empty] | DEADP, DLG, GRDM | Waste Management
37 | George Municipality | Garden Route | Rehabilitation of Gwaing WDF – Rehabilitation of the Gwaing WDF and S24G remediation process | [9 empty] | DEADP, DLG, GRDM | Waste Management
38 | George Municipality | Garden Route | Extension and refurbishment of the Waste Transfer Station | [9 empty] | DEADP, DLG, GRDM | Waste Management
39 | George Municipality | Garden Route | Material recovery facility (MRF) – Build a MRF on Erf 464 | [9 empty] | DEADP, DLG, GRDM | Waste Management
40 | George Municipality | Garden Route | Mini transfer stations – Building of mini transfer station at the residential areas | [9 empty] | DEADP, DLG, GRDM | Waste Management
Note on G29: user: Construction - R124 285 922.14 Cons Fees - R16 843 177.34 OHS - R609 169.91 Total - R141 738 269.39 Rounded to R141 800 000

## LG Kannaland
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance Required | Last Update Date
1 | Kannaland Municipality | Garden Route | Confirm prioritised water security interventions (bulk storage, raw water augmentation, boreholes) and align to MIG/WSIG funding options. | Water | All Wards | Operational Budget | MIG/WSIG | Integrated Development Plan (IDP) 2022–2027 | Concept | In Progress with assistance from MISA and JG Afrika. | Lack of raw water storage in leading to prolonged Level 4 restrictions | Short term | DWS, DLG, GRDM | Water Services | Manager: Demand Management & Purification | 2026-07-01 | 2027-06-30 | Critical to unlock MIG funding for future FYs. | Technical alignment for MIG/WSIG funding. | 2026-06-24
2 | Kannaland Municipality | Garden Route | Submit sanitation and wastewater upgrade programme (WWTW capacity and reticulation upgrades) with compliance risks highlighted. | Sanitation | All Wards | Operational Budget | MIG | Integrated Development Plan (IDP) 2022–2027 | Pre-feasibility | Completed. | Oxidation ponds and WWTW facilities nearing maximum capacity. | Short term | DWS, DEADP, DLG | Sanitation | Manager: Demand Management & Purification | 2026-07-01 | 2027-06-30 | Green Drop compliance risk high. | Green Drop compliance auditing. | 2026-06-24
3 | Kannaland Municipality | Garden Route | Confirm priority electricity strengthening and metering interventions, including Eskom interface matters. | Electricity | All Wards | R 30,000,000 | INEP | Integrated Development Plan (IDP) 2022–2027 | Implementation | Construction 95%. Landis+Gyr. | Aging substations and Eskom interface points requiring urgent strengthening. | Long term | Eskom, DLG | Electro-technical | Manager: Electrical and Mechanical Services | 2025-03-01 | 2028-06-30 | Focused on revenue protection. | Eskom interface and tarrif mediation | 2026-06-24
4 | Kannaland Municipality | Garden Route | Submit roads and stormwater priority list for rural access roads and drainage upgrades, with sequencing. | Roads | All Wards | R 45,000,000 | MIG | Integrated Development Plan (IDP) 2022–2027 | Pre-feasibility | MIG application submitted to DLG. Awaiting pre-appraissal. | Insufficient operational budget for full-scale resealing, limiting interventions to reactive pothole repairs. | Short term, Medium term | DLG, MISA, CoGTA | Roads & Stormwater | Director: Infrastructure Services | 2026-08-01 | 2029-06-30 | Prioritizing road and stormwater upgrades & rehabilitation. | Grant application support. | 2026-06-24
5 | Kannaland Municipality | Garden Route | Add Kannaland permitting blockages (WULAs/EIAs/Eskom) to the district-wide permitting unblocker list. | Planning | All Wards | N/A | Operational | Integrated Development Plan (IDP) 2022–2027 | N/A | Ongoing. WULA delays escalated to Prov. Treasury. | Aging substations and Eskom interface points requiring urgent strengthening. | Long term | DLG, DEADP, DWS, Eskom, GRDM | Infrastructure Services / Planning | Manager: PMU | 2026-01-01 | 2028-06-30 | Monthly tracking required. | Regulatory streamlining with NERSA. | 2026-06-24
6 | Kannaland Municipality | Garden Route | Upgrading of oxidation ponds phase 3 | Sanitation | Zoar | R 4,000,000 | MIG | Integrated Development Plan (IDP) 2022–2027 | Implementation | Construction 85%. Contractor on site (Fundisani). | Oxidation ponds and WWTW facilities nearing maximum capacity. | Medium term | DWS, DEADP, DLG | Sanitation | Director: Infrastructure Services | 2025-07-01 | 2026-06-30 | Critical for housing development unlock. | Environmental compliance oversight. | 2026-06-24
7 | Kannaland Municipality | Garden Route | Construction of a new wastewater treatment plant | Sanitation | Calitzdorp | R 48,240,638 | WSIG | Integrated Development Plan (IDP) 2022–2027 | Planning | R1,500,000 approved for 2026/27 FY for professional fees. 2027/28 FY implementation. | High capital requirements for new WWTW in Calitzdorp | Long term | DWS, DEADP, DLG | Sanitation | Director: Infrastructure Services | 2026-01-01 | 2026-08-30 | Multi-year project. Funding in published DoRA for multiple financial years. | Multi-year capital funding security. | 2026-06-24
8 | Kannaland Municipality | Garden Route | Upgrading of sanitation network in Ladismith | Sanitation | Ladismith | R 35,000,000 | MIG/WSIG | Integrated Development Plan (IDP) 2022–2027 | Feasibility | Planning. Ageing AC pipes causing frequent blockages. | Older sections of the Ladismith network require significant rehabilitation before they can be integrated with the new infrastructure to avoid blockages. Dedicated water network lines to the cheese factories will form part of application. | Medium term | DWS, DEADP, DLG | Sanitation | Manager: PMU | 2026-10-01 | 2029-06-30 | Phased replacement approach. | Technical report assistance. | 2026-06-24
9 | Kannaland Municipality | Garden Route | Construction of a new wastewater treatment plant | Sanitation | Vanwyksdorp | R 45,000,000 | WSIG / MIG | Integrated Development Plan (IDP) 2022–2027 | Pre-Feasibility | Ongoing WSIG application. | High capital requirements for new WWTW in Vanwyksdorp | Long term | DWS, DEADP, DLG | Sanitation | Manager: PMU | 2027-01-01 | 2028-06-30 | Current facility over capacity. | Site allocation and EIA support. | 2026-06-24
10 | Kannaland Municipality | Garden Route | Upgrading of sanitation network in Vanwyksdorp | Sanitation | Vanwyksdorp | R 15,000,000 | WSIG / MIG | Integrated Development Plan (IDP) 2022–2027 | Implementation | Ongoing. | Older sections of the Vanwyksdorp network require significant rehabilitation before they can be integrated with the new infrastructure to avoid blockages. | Medium term | DWS, DEADP, DLG | Sanitation | Manager: PMU | 2027-03-01 | 2028-06-30 | Upgrading of critical pump lines. | Emergency procurement clearance. | 2026-06-24
11 | Kannaland Municipality | Garden Route | Upgrading and refurbishment of Ladismith wastewater treatment works phase 3 | Sanitation | Ladismith | R 5,100,000 | WSIG | Integrated Development Plan (IDP) 2022–2027 | Litigation | Project stalled due to disputes bewteen Contractor & Municipality. | Oxidation ponds and WWTW facilities nearing maximum capacity. | Medium term | DWS, DEADP, DLG | Sanitation | Manager: PMU | 2024-07-01 | 2028-06-30 | Mechanical equipment replacement focus. | Project in litigation phase. | 2026-06-24
12 | Kannaland Municipality | Garden Route | Pothole repairs (All wards) | Roads | All Wards | R 2,500,000 | Operational | Integrated Development Plan (IDP) 2022–2027 | Implementation | Phased pothole repair project implemented. R300,000 to be spend by 30 June 2026. | Insufficient operational budget for full-scale resealing, limiting interventions to reactive pothole repairs. | Short term, Medium term | DLG, GRDM | Road Services | Manager: Civil Services | 2026-03-01 | 2029-06-30 | Pothole repairs. | Budget augmentation for materials. | 2026-06-24
13 | Kannaland Municipality | Garden Route | Smart meter project managed and financed by National Treasury | Energy | Ladismith/Calitzdorp | R30,000,000 | Nat. Treasury | Integrated Development Plan (IDP) 2022–2027 | Implementation | Procurement. Service provider appointment imminent. | Aging substations and Eskom interface points requiring urgent strengthening. | Long term | Eskom, DLG, National Treasury | Electro-technical | Manager: Electro-technical | 2025-10-01 | 2026-08-30 | Focus on top 100 consumers & tampering. | Revenue protection strategy alignment. | 2026-06-24
14 | Kannaland Municipality | Garden Route | Upgrading of water treatment works phase 2 | Water | Calitzdorp | R 3,700,000 | WRG | Integrated Development Plan (IDP) 2022–2027 | Implementation | Construction 80%. Contractor on site. WRG - planned completion 30 June 2026. | Recent bids have come in significantly higher than the R 3.7 million estimate, requiring a budget reprioritization or a reduction in scope to stay within the WRG allocation. | Medium term | DWS, DLG | Water Services | Manager: PMU | 2026-01-01 | 2026-08-30 | Improving final water quality (Blue Drop). | Blue Drop water quality verification. | 2026-06-24
15 | Kannaland Municipality | Garden Route | Construction of a new raw water storage facility in Zoar | Water | Zoar | R 22,000,000 | RBIG / WSIG | Integrated Development Plan (IDP) 2022–2027 | Feasibility | BP submitted to WSIG. | High public pressure and the ongoing need for water shedding/tankering create a high-stress environment for contractors and municipal staff on-site. | Long term | DWS, DLG | Water Services | Manager: PMU | 2026-10-01 | 2030-06-30 | Drought mitigation priority. | Fast-track technical report approval. | 2026-06-24
16 | Kannaland Municipality | Garden Route | Upgrade of raw water supply line from Tierkloof to WTW in Zoar | Water | Zoar | R 10,000,000 | RBIG / WSIG | Integrated Development Plan (IDP) 2022–2027 | Planning | BP submitted to WSIG. | Given the ongoing infrastructure crisis, sourcing high-density polyethylene (HDPE) or similar materials at current market rates (R 10,000,000 estimate) is susceptible to price volatility. | Medium term | DWS, DLG | Water Services | Manager: PMU | 2027-07-01 | 2028-06-30 | Reducing water losses in bulk line. | Wayleave and servitude negotiations. | 2026-06-24
17 | Kannaland Municipality | Garden Route | Upgrading of bulk water supply to Stanley reservoir | Water | Vanwyksdorp | R 5,000,000 | WSIG | Integrated Development Plan (IDP) 2022–2027 | Planning | Ongoing. | The Department of Water and Sanitation (DWS) requires a comprehensive "Technical Report" for bulk upgrades. Current staff capacity constraints are delaying the finalization of this document. | Long term | DWS, DLG | Water Services | Manager: PMU | 2026-08-01 | 2028-03-31 | Water capacity upgrade. | WSIG funding prioritisation. | 2026-06-24
18 | Kannaland Municipality | Garden Route | Construction of a new raw water storage facility in Vanwyksdorp | Water | Vanwyksdorp | R 15,000,000 | RBIG / WSIG | Integrated Development Plan (IDP) 2022–2027 | Planning | Ongoing. | Identifying a site with the correct elevation for gravity-fed distribution while ensuring stable geotechnical conditions is a primary hurdle in the current planning phase. | Long term | DWS, DLG | Water Services | Manager: PMU | 2026-09-01 | 2029-06-30 | Long-term water security. | Engineering design review. | 2026-06-24
19 | Kannaland Municipality | Garden Route | Deep borehole project in Calitzdorp Ph2 | Water | Calitzdorp | R 22,000,000 | WSIG | Integrated Development Plan (IDP) 2022–2027 | Planning | R1,500,000 approved for 2026/27 FY for professional fees. 2027/28 FY implementation. | The primary challenge is the uncertainty of ground water yields. Over-extraction in the Calitzdorp area could lead to the "drying up" of existing private boreholes, creating community friction. | Medium term, Long term | DWS, DLG | Water Services | Manager: PMU | 2026-07-01 | 2029-06-30 | Emergency augmentation source. | Geohydrological study report. | 2026-06-24
20 | Kannaland Municipality | Garden Route | Replacement of Asbestos Cement Water Network | Water | Calitzdorp | R 33,250,000 | RBIG / WSIG | Integrated Development Plan (IDP) 2022–2027 | Planning | BP submitted to WSIG. | Deteriorated AC pipes causing high non-revenue water losses. | Medium term, Long term | DWS, DLG | Water Services | Manager: PMU | 2026-07-01 | 2028-06-30 | Replacement of the aged network to reduce water losses and improve service delivery reliability. | Long-term asset management planning. | 2026-06-24
21 | Kannaland Municipality | Garden Route | Construction of 5ML Bulk Storage Reservoir | Water | Ladismith | R 51,750,000 | RBIG / WSIG | Integrated Development Plan (IDP) 2022–2027 | Planning | Ongoing. | As this project is currently in the "Planning" phase, the primary bottleneck is the finalization of the Technical Report (TR) for DWS approval, which is hindered by the current vacancy rates in our senior engineering posts. | Medium term, Long term | DWS, DLG | Water Services | Manager: PMU | 2026-03-01 | 2029-06-30 | Augmenting terminal storage capacity from less than 24 hours to approximately 48 hours of supply to meet national standards and reduce system fragility. | Technical alignment with WSDP. | 2026-06-24

## LG Knysna
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Support Required ( Sector Depts / SIDAFF) | Priority | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance Required | Last Update Date (March 2026)
1 | Knysna Municipality | Garden Route | Kruisvallei Dam Development |  | Knysna Area- Upper Reaches of Jnysna River |  |  |  | Design / Procurement Preparation (Transitioning toward Implementation) | Foundation Phase: Foundation drilling has been completed and the project is currently awaiting the final analysis of the geological/material investigation results. Funding: | Site feasibility and environmental requirements still to be confirmed, including potential EIA processes. Specialist technical and social reports outstanding, with stakeholder engagement required (particularly with affected farmers). Final confirmation of material suitability, costing estimates, and founding conditions of the dam wall still required before progressing to implementation. | DWS, DLG |  | Water Services | Project managed by Rhoydon Parry (Manager: Water & Wastewater) with PMU support from Mpumie Nzuzo. |  |  | The foundation drilling component was funded through the Municipal Infrastructure Grant (MIG). The construction of the larger dam wall is proposed to be funded through the Regional Bulk Infrastructure Grant (RBIG). Prerequisite Requirements: Before progressing to the next stage, the following must be completed: Specialist technical reports Social impact considerations Stakeholder engagement (particularly with affected farmers) Environmental Impact Assessment (EIA) processes Environmental Authorisation: Engagement with the Western Cape Department of Environmental Affairs and Development Planning (DEADP) is required to determine whether the site is environmentally feasible and suitable for the proposed dam development. Costing Considerations: Cost estimates will depend on: Suitability of construction materials Founding conditions of the dam wall Final engineering design requirements | MIG application support, coordination with DEADP on EIA feasibility; | We still need the support for the activities to stream line the project
2 | Knysna Municipality | Garden Route | Karatara Bulk Water Supply | [5 empty] | Feasibility / Business Case Submitted – Awaiting Funding Approval | The project is currently undergoing MIG registration and approval processes. The MIG funding application has been submitted. | Awaiting MIG funding approval. | DWS, DLG |  | Water Services |  |  |  | The project has completed the e-Value system stage and is now progressing to the physical evaluation phase as part of the MIG assessment process. | Support with MIG registration and approval process; coordination with sector departments where required. | It was refered back from by DWS for further design and detailing of scope of works.Will need assistence to excelerate project.
3 | Knysna Municipality | Garden Route | Upgrade Of Rheenendal Bulk Water Supply | [6 empty] | Current Status: The project is currently under construction with an estimated construction duration of approximately 10 months. | None identified – project under construction. | DWS, DLG |  | Water Services |  |  |  | Project Cost: The estimated project value is approximately R31 million (noted as R16 million and R15 million components). Funding source to be confrimed. | None Noted. | Need a technical specialised to investigate the Rheenendal Waste Water Treatment Works. Plant don't condirm to the license standards
4 | Knysna Municipality | Garden Route | Windheuwel Waste Water Treatment Plant | [6 empty] | Current Status: Consultants have been appointed to undertake preliminary design work for the proposed wastewater treatment plant. The development is planned across four erven. A pre-feasibility study has already been completed, which indicated that the estimated cost of the project is significantly high. | Key Challenges / Constraints: Land ownership/legal issues relating to identified erven; high project cost and disaster funding approval pending. | DWS, DEADP, DLG |  | Sanitation |  |  |  | Project Concept: The intention of the project is to treat wastewater to a suitable standard so that the treated effluent can be pumped to the dam, improving water availability in the area. Disaster Declaration: The project has been declared as part of a disaster intervention, and the municipality is currently awaiting national approval to proceed with the necessary funding and implementation processes. | Facilitation of disaster funding processes; coordination with national departments | We will nee the support of all the key departments. This must be fast track asap
5 | Knysna Municipality | Garden Route | Upgrade Of Knysna Cbd Sewer Network | [6 empty] | CBD sewer upgrade project; partial MIG funding received (±R8m of ±R40m project); first phase completed near waterfront pump station; further upgrades required but constrained by funding and challenging construction conditions. | Several technical challenges were highlighted during implementation: Construction required work approximately 4 metres below ground level. The area has a high groundwater table (around 300mm below surface) which complicates excavation and construction. Dewatering and safety requirements significantly increase construction costs. Concrete encasement of existing bulk sewer pipes created challenges when attempting trenchless installation methods. Directional drilling attempts failed due to the combination of soil conditions and groundwater levels, making it difficult to maintain the required gradient. These factors have significantly increased construction costs and complexity | DWS, DEADP, DLG |  | Sanitation |  |  |  | The estimated project value is approximately R40 million, however only about R8 million was approved through MIG, which allowed the municipality to complete only a limited portion of the required upgrades. Knysna Municipality- MUNICIPAL … The initial phase of the project included upgrades near the waterfront entrance and associated pump station, including installation of a 750mm road crossing pipeline and portions of a 600mm sewer line. Project Context Although the infrastructure is located within the CBD (which is not classified as an indigent area), the sewer system serves the broader Knysna population and supports the local economy, as the CBD functions as a service centre for surrounding communities. | MIG team to engage with municipality to review and repackage business plan and assess potential MIG funding for remaining phases. | The MIG contibution will be very small, therefor we must explore WSIG/ RBIG/ MWIG etc
6 | Knysna Municipality | Garden Route | Upgrade Of Various Sewer Pumpstations | [6 empty] | Current Status: A condition assessment study is planned for the entire fleet of sewer pump stations (approximately 113 pump stations). The purpose of the study is to assess the condition of the pump stations and prioritise those requiring upgrading or rehabilitation. | Funding for condition assessment study not yet secured. | DWS, DEADP, DLG |  | Sanitation |  |  |  | The municipality intends to undertake a detailed condition assessment of approximately 113 sewer pump stations to determine asset condition and prioritise upgrades. The assessment will inform a phased rehabilitation programme.Concept notes currently being developed by Pegasys to package the project for potential funding. | Engage with Pegasys regarding potential funding opportunities for the condition assessment study and provide guidance where required. | We need asssistance in moving forward
7 | Knysna Municipality | Garden Route | Integrated Waste To Energy Plant At Knysna Waste Water Treatment Plant | [6 empty] | Current Status: The project is currently at an early stage (around pre-feasibility) and is considered a large-scale initiative. It forms part of broader discussions around waste-to-energy solutions linked to wastewater treatment processes. | Early pre-feasibility stage; concept development and funding still to be confirmed. | DWS, DEADP, DLG |  | Sanitation |  |  |  | Project Coordination: The Community Services Directorate is also involved in this initiative from a waste management perspective, particularly regarding waste disposal and potential energy generation opportunities. Concept Development: It was noted during the meeting that Pegasys may be reviewing this project together with another initiative, and concept notes are reportedly being developed to package these projects and explore potential funding opportunities. This information still needs to be confirmed | Engage with Pegasys to confirm the status of the concept notes being developed for the waste-to-energy initiative. Provide coordination support where required between the municipality and relevant stakeholders involved in the project. Assist with identifying or facilitating potential funding opportunities once the concept notes are finalised. | We need asssistance in moving forward
8 | Knysna Municipality | Garden Route | Upgrade Of George Rex Drive | [6 empty] | Current Status: The project is included in the municipality’s capital expenditure (CapEx) budget over the MTREF period. George Rex Drive is a municipal road and serves as a key arterial route, supporting both tourism and local traffic movement. | Funding challenges due to municipal road classification, despite the road serving wider commuter and tourism traffic. | DoI, DLG |  | Roads & Stormwater |  |  |  | Project Context: Previous funding applications to provincial and national departments were unsuccessful, as the road is classified as a municipal street. Although the road is located in a relatively affluent area, it serves a broader community, including residents from surrounding areas. Funding Considerations: The municipality indicated interest in exploring a Municipal Infrastructure Grant (MIG) application, recognising that the road functions as an important service route for the wider Knysna area. | MIG team to engage with municipality to assess potential MIG eligibility and provide guidance on application process. | We need also engaements with Province for assistence.
9 | Knysna Municipality | Garden Route | Rehabilitation And Resurfacing Of Main Street | [6 empty] | The municipal section of Main Street forms part of the N2 corridor through Knysna and carries significant regional through-traffic. The municipality is currently assessing the road rehabilitation requirements and exploring potential funding options. | Funding Challenges: The municipality indicated that no funding support has been received from SANRAL or the Province for the municipal section of the route, despite the road serving regional traffic passing through the town. | DoI, DLG |  | Roads & Stormwater |  |  |  | Current Situation: The N2 corridor passes through Knysna, with different sections managed by different authorities. A portion of the route is under SANRAL, while a section through the town centre is the responsibility of the municipality. This municipal section carries significant through-traffic, including traffic originating from the SANRAL-managed N2, effectively serving regional and commuter traffic moving through Knysna. | Engage with Carl October to explore funding options and advise on potential grant funding (e.g., public transport infrastructure grants). | The Municipality is in contact with Mr October
10 | Knysna Municipality | Garden Route | Salt River Road Rehabilitation | [6 empty] | Salt River Road is a main arterial route serving residential and tourism areas and hosts the Samola Hill Climb event. The road surface requires rehabilitation and resurfacing. | Funding constraints as the municipal section of the route falls between SANRAL-managed sections but currently receives no funding support from SANRAL or the Province. | DoI, DLG |  | Roads & Stormwater |  |  |  | Salt River Road is a main arterial route that serves residential and tourism areas. The road is also associated with the Samola Hill Climb event, which attracts national and international participants and spectators. Project Context: The road previously formed part of the district road network, but responsibility was later transferred to the municipality, resulting in additional maintenance and rehabilitation responsibilities for the municipality. The municipality indicated that the road surface condition is deteriorating, and resurfacing is required, particularly in the section where the hill climb event takes place. It was noted that a fatality occurred during the event in the previous year, highlighting concerns about the road condition. | Engage with Carl October and relevant stakeholders to explore potential funding opportunities. | The Municipality is in contact with Mr October
11 | Knysna Municipality | Garden Route | Knysna Main Intake Substation | [8 empty] | Eskom, DLG |  | Electrical technical |  |  |  | Current Status: The Knysna Main Intake Substation project has been approved under the Integrated National Electrification Programme (INEP). The project is currently under construction, and a contractor has been appointed to undertake the works. Implementation Period: The project will be implemented over a three-year period, with construction phased due to funding constraints and INEP allocation conditions. | None identified at this stage. | None identified at this stage.
12 | Knysna Municipality | Garden Route | Knysna 10Mva 22/11Kv: Construction Of New Khayalethu Substation & Upgrade Of Bongani Substation | [6 empty] | Limited project details available; municipality to provide additional information. | Further project information required from municipality. | Eskom, DLG |  | Electrical technical |  |  |  | Construction of new Khayalethu substation and upgrade of Bongani substation; further project details to be provided by the municipality. | None identified at this stage. | None identified at this stage.
13 | Knysna Municipality | Garden Route | 11Kv: Construction Of New Cormorant Substation, Construction Of New Luthango Substation, Upgrading Of Dedicated Supply To Smutsville And Strengthen Ring To Centre Point In Smutsville And Sedgehill In Sedgefield | [6 empty] | Electricity network strengthening programme including new substations and supply upgrades. | Detailed project information still to be confirmed by municipality. | Eskom, DLG |  | Electrical technical |  |  |  | Electricity network strengthening projects including new substations and supply upgrades in Smutsville and Sedgefield; further information to be provided by the municipality. | None identified at this stage. | None identified at this stage.

## LG Langeberg
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance Required | Last Update Date
1 | Langeberg Municipality | Cape Winelands | Bonnievale WTW upgrades | Water | Bonnievale | 150659767 | MIG | Water Master Plan | Tender stage | Phase 1 - Tender Stage |  | Immediate | DWS, DLG | Civil Engineering | C Posthumus | 5-Jun-26 (Phase 1) | Phase 1 Completion 2027/03/05 Over all 2030/04/30 | Phase 1 out for tender. Phase 2 the detail design has to be done to determine actual cost |  | 2026-06-23
2 | Langeberg Municipality | Cape Winelands | Dassieshoek Dam wall lifting project (Robertson) | Water | Robertson | 17000000 | DLG, WSIG | IDP | Feasibility | Detail Design, EIA, Hydrology study | EIA, Approval of Hydrology study, Funding | Immediate | DWS, DLG | Civil Engineering | C Posthumus | 2025-07-01 | 2028-06-30 | Project started and currently in design fase, EIA and Hydrology study. Detail design and tender to be completed to finalise final cost | Need funding for construction. | 2026-06-23
3 | Langeberg Municipality | Cape Winelands | McGregor WTP upgrades | Water | McGregor | 55233555 | MIG | IDP. MIG | Construction | Construction |  | Immediate | DWS, DLG | Civil Engineering | N Albertyn | 2025-07-01 | 2028-06-30 | Project in construction |  | 2026-06-23
| Langeberg Municipality | Cape Winelands | Bonnievale bulk water upgrade | Water | Bonnievale | 70000000 | MIG | Master Plan | Feasibility | Feasibility, Master Plan | Funding | Short | DWS, DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2029-06-30 | Need to start fwith detail design and tender documentation | Need funding for design and tender documentation | 2026-06-23
4 | Langeberg Municipality | Cape Winelands | Bonnievale South bulk water supply to new Uitsig Reservoir | Water | Bonnievale | 45000000 |  | Water Master Plan | Feasibility | Feasibility | Funding | Short | DWS, DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2029-06-30 | Need to start fwith detail design and tender documentation | Need funding for design and tender documentation | 2026-06-23
5 | Langeberg Municipality | Cape Winelands | Bulk wastewater upgrades at Bonnievale WWTW | Sewerage | Bonnievale | 50000000 | MIG | IDP. WSDP | Concept | Concept | Funding | Short | DWS, DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2029-06-30 | Need to start fwith detail design and tender documentation | Need funding to start with detail design | 2026-06-23
6 | Langeberg Municipality | Cape Winelands | Bulk wastewater upgrades at Ashton WWTW | Sewerage | Ashton | 140000000 | MIG | IDP. WSDP | Concept | Concept | Funding | Short | DWS, DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2029-06-30 | Need to start fwith detail design and tender documentation | Need funding to start with detail design | 2026-06-23
7 | Langeberg Municipality | Cape Winelands | McGregor bulk upgrades and new wastewater treatment plant | Sewerage | McGregor | 150000000 | MIG | WSDP | Concept | Concept | Funding | Short | DWS, DLG | Civil Engineering | C Posthumus | 2026-07-01 | 2029-06-30 | Need to start with detail design and tender documentation | Need funding to start with detail design | 2026-06-23
8 | Langeberg Municipality | Cape Winelands | Robertson road rehabilitation programme | Roads | Robertson | 100000000 | DLG | IDP, RPMS | Feasibility | Feasibility | Funding | Short | DoI, DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2030-06-30 | This is a roling project and funding is required to upgrade all roads in Langeberg Municiplaity | Need funding on an annual basis | 2026-06-23
9 | Langeberg Municipality | Cape Winelands | Montagu road rehabilitation programme | Roads | Montagu | 80000000 | DLG | IDP, RPMS | Feasibility | Feasibility | Funding | Short | DoI, DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2030-06-30 | This is a roling project and funding is required to upgrade all roads in Langeberg Municiplaity | Need funding on an annual basis | 2026-06-23
| Langeberg Municipality | Cape Winelands | Ashton road rehabilitation programme | Roads | Ashton | 50000000 | DLG | IDP, RPMS | Feasibility | Feasibility | Funding | Short | DoI, DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2030-06-30 | This is a roling project and funding is required to upgrade all roads in Langeberg Municiplaity | Need funding on an annual basis | 2026-06-23
| Langeberg Municipality | Cape Winelands | Bonnievale road rehabilitation programme | Roads | Bonnievale | 70000000 | DLG | IDP, RPMS | Feasibility | Feasibility | Funding | Short | DoI, DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2030-06-30 | This is a roling project and funding is required to upgrade all roads in Langeberg Municiplaity | Need funding on an annual basis | 2026-06-23
| Langeberg Municipality | Cape Winelands | McGregor road rehabilitation programme | Roads | McGregor | 50000000 | DLG | IDP, RPMS | Feasibility | Feasibility | Funding | Short | DoI, DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2030-06-30 | This is a roling project and funding is required to upgrade all roads in Langeberg Municiplaity | Need funding on an annual basis | 2026-06-23
10 | Langeberg Municipality | Cape Winelands | Robertson stormwater upgrading programme | Stormwater | Robertson | 50000000 | DLG | IDP | Concept | Concept | Funding | Short | DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2030-06-30 | Stormwater master Plan has to be updated | Need funding on an annual basis | 2026-06-23
11 | Langeberg Municipality | Cape Winelands | Montagu stormwater upgrading programme | Stormwater | Montagu | 50000000 | DLG | IDP | Concept | Concept | Funding | Short | DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2030-06-30 | Stormwater master Plan has to be updated | Need funding on an annual basis | 2026-06-23
| Langeberg Municipality | Cape Winelands | Ashton stormwater upgrading programme | Stormwater | Ashton | 30000000 | DLG | IDP | Concept | Concept | Funding | Medium | DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2030-06-30 | Stormwater master Plan has to be updated | Need funding on an annual basis | 2026-06-23
| Langeberg Municipality | Cape Winelands | Bonnievale stormwater upgrading programme | Stormwater | Bonnievale | 30000000 | DLG | IDP | Concept | Concept | Funding | Medium | DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2030-06-30 | Stormwater master Plan has to be updated | Need funding on an annual basis | 2026-06-23
| Langeberg Municipality | Cape Winelands | McGregor stormwater upgrading programme | Stormwater | McGregor | 10000000 | DLG | IDP | Concept | Concept | Funding | Medium | DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2030-06-30 | Stormwater master Plan has to be updated | Need funding on an annual basis | 2026-06-23
| Langeberg Municipality | Cape Winelands | Water and sewer SCADA | Water and Sewer | All Towns | 4000000 | DLG | IDP | Feasibility | Feasibility | Funding | Short | DLG | Civil Engineering | C Posthumus | 2027-07-01 | 2030-06-30 | SCADE system needs upgrade | Need funding | 2026-06-23
12 | Langeberg Municipality | Cape Winelands | SCADA system and smart meters programme | Electrical | All Towns | 1000000 | CRR | Master Plan | Feasibility | Feasibility | Funding | Short | DLG, Eskom | Electrical / Energy Services | D Louwrens | 2027-07-01 | 2027-06-30 | Scada for demand management and control | Need funding | 2026-04-20
13 | Langeberg Municipality | Cape Winelands | Upgrade of Muscadel Substation and associated electrical infrastructure | Electrical | Montagu | 7000000 | DLG | Master Plan | Feasibility | Feasibility | Funding | Short | Eskom, DLG | Electrical / Energy Services | D Louwrens | 2027-07-01 | 2027-06-30 | Replace or upgrade old infrastructure | Need funding | 2026-04-20
14 | Langeberg Municipality | Cape Winelands | Closure, decommissioning and rehabilitation of McGregor Waste Disposal Facility (WDF) | Waste Management | McGregor | 40000000 | MIG | CLOSURE AND REHABILITATION REPORT | Concept | Concept | Funding | Immediate | DEADP, DLG | Solid Waste Management | G. Slingers | 2029-07-01 | 2030-06-30 | This site was issued with a closure licence. The closure licence required rehabilitation commencement within five (5) years from the licence issue date of 12 May 2015 Decommissioning must, therefore, have commenced on or before 12 May 2020. However, the Langeberg Municipality applied to the Department of Environmental Affairs & Development Planning (DEA&DP) to vary the licence and postpone the commencement date. The Municipality officially submitted that they plan to commence rehabilitation construction in 2030 and achieve completion in 2033. | Need funding for design and tender documentation | 2026-04-20
15 | Langeberg Municipality | Cape Winelands | Upgrade of Robertson Transfer Station and procurement of waste containers | Waste Management | Robertson | 15000000 | MIG | IDP | Concept | Concept | Funding | Medium | DEADP, DLG | Solid Waste Management | G. Slingers | 2027-07-01 | 2028-06-30 | Begin technical specification development and tender documentation. | Need funding for design and tender documentation | 2026-04-20
16 | Langeberg Municipality | Cape Winelands | Extension of Ashton Materials Recovery Facility (MRF) | Waste Management | Ashton | 10000000 | MIG | IDP | Concept | Concept | Funding | Medium | DEADP, DLG | Solid Waste Management | G. Slingers | 2028-07-01 | 2029-06-30 | Begin technical specification development and tender documentation. | Need funding for design and tender documentation | 2026-04-20

## LG Mossel Bay
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Support Required ( Sector Depts / SIDAFF) | Priority | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance | Last Update Date
1 | Mossel Bay Municipality | Garden Route | Louis Fourie Corridor: Upgrading of Water Storage / Bulk Supply |  | Louis Four Corridor | 150000000 | TBC | Water Master plan | Funding, environmental approval, planning and implementation required | Identified |  | DWS, DEADP, DLG | High | Water Services | H Schoeman | 2027-07-01 | 2030-06-30 |  | BFI Application and redtape reduction
2 | Mossel Bay Municipality | Garden Route | Louis Fourie Corridor: Establishment of Water network |  | Louis Four Corridor | 75000000 | TBC | Precint develpoment Plan | Funding, environmental approval, planning and implementation required | Identified |  | DWS, DEADP, DLG | High | Water Services | H Schoeman | 2027-07-01 | 2030-06-30 |  | BFI Application and redtape reduction
3 | Mossel Bay Municipality | Garden Route | Louis Fourie Corridor: Establishment of Sewer Network |  | Louis Four Corridor | 100000000 | TBC | Precint develpoment Plan | Funding, environmental approval, planning and implementation required | Identified |  | DWS, DEADP, DLG | High | Sanitation | H Schoeman | 2027-07-01 | 2030-06-30 |  | BFI Application and redtape reduction
4 | Mossel Bay Municipality | Garden Route | Alwyndal: Construction of New bulk Sewer Line |  | Alwyndal | 40000000 | TBC | Sewer master plan | Funding needed for environmental approval, planning and implementation | Identified |  | DWS, DEADP, DLG | High | Sanitation | E Louw | 2027-01-15 | 2029-06-30 |  | Funding and redtape reduction
5 | Mossel Bay Municipality | Garden Route | Capacity increase of Sandhoogte WTW |  | Great Brak / Alwyndal | 300000000 | WSIG (TBC) | Water Master | Concept and Viability | WIP | Funding | DWS, DLG, DEADP | High | Water Services | V Tshantshana | 2026-07-01 | 2029-06-01 |  | Funding and redtape reduction
6 | Mossel Bay Municipality | Garden Route | Upgrading of Regional Plant Waste Water Treatment Works |  | Hartenbos / Alwyndal | 250000000 | TBC | Sewage Master Plan | Consultant been appointed | WIP | Funding | DWS, DEADP, DLG | High | Sanitation | V Tshantshana | 2026-07-01 | 2029-06-01 |  | Funding and Redtape Reduction
7 | Mossel Bay Municipality | Garden Route | Confirm electricity load growth management and coordination steps with Eskom. |  | Mossel Bay | 500000 | CRR | Masterplan | Revsion of masterplan will be complete by Jun 2027.This will include discussions with Eskom | Not started |  | Eskom, DoI, DLG | High | Electrical technical | P.Harmse | 2026-07-01 | 2027-06-30 | Eskom needs to be aware of the impact of the Louis Fourie Corridor Project on the required capacity for Mossel Bay. Constriants such as the Proteus-Duinzicht lines must be addressed.
8 | Mossel Bay Municipality | Garden Route | Upgrade 66/11kV Intake Substation |  | Mossel Bay | 120000000 | CRR (Phase 1) | Masterplan | Contractor has been appointed for first phase of construction. | Contractor appointed (Phase 1) | Funding | Eskom | Medium | Electrical technical | P.Harmse | 2026-07-01 | 2029-06-30
9 | Mossel Bay Municipality | Garden Route | Electrification |  | KwaNonqaba | 40000000 | INEP grant |  | Continuous implementation | In progress | Funding | DEE | High | Electrical technical | R.van Zyl | 2026-07-01 | 2029-06-30
10 | Mossel Bay Municipality | Garden Route | Saunders Substation: 2nd 10MVA transformer |  | Louis Fourie Corridor areas | 30000000 | TBC | Masterplan & Precinct Development Plan | Funding, planning and implementation required | Not started | Funding | DoI, DLG | Medium | Electrical technical | M.Olivier | 2027-07-01 | 2030-06-30 | Related to capacity for Louis Fourie Corridor project
11 | Mossel Bay Municipality | Garden Route | Upgrade 66kV overhead line from Intake Substation to Saunders Substation |  | Mossel Bay | 30000000 | TBC | Masterplan & Precinct Development Plan | Funding, planning and implementation required | Not started | Funding | DoI, DLG | Medium | Electrical technical | M.Olivier | 2027-07-01 | 2030-06-30 | Related to capacity for Louis Fourie Corridor project
12 | Mossel Bay Municipality | Garden Route | Replace 3 x 10MVA transformers at Ockert Bothma Substation with 3 x 20MVA units |  | Louis Fourie Corridor areas | 80000000 | TBC | Masterplan & Precinct Development Plan | Funding, planning and implementation required | Not started | Funding | Eskom, DoI, DLG | Medium | Electrical technical | M.Olivier | 2027-07-01 | 2030-06-30 | Related to capacity for Louis Fourie Corridor project
13 | Mossel Bay Municipality | Garden Route | Saunders Substation: 3rd 10MVA transformer |  | Louis Fourie Corridor areas | 40000000 | TBC | Masterplan & Precinct Development Plan | Funding, planning and implementation required | Not started | Funding | DoI, DLG | Medium | Electrical technical | M.Olivier | 2027-07-01 | 2030-06-30 | Related to capacity for Louis Fourie Corridor project
14 | Mossel Bay Municipality | Garden Route | New 11kV overhead line from Mossdustria to Aalwyndal |  | Aalwyndal | 20000000 | TBC | Masterplan | Funding, environmental approval, planning and implementation required | Not started | Funding | Eskom, DoI, DLG | Medium | Electrical technical | M.Olivier | 2027-07-01 | 2030-06-30 | Related to capacity for Aalwyndal precinct
15 | Mossel Bay Municipality | Garden Route | Rebuild and Extend 11kV Line Bothma to South Sub |  | Louis Fourie Corridor areas | 10000000 | CRR | Masterplan | First phase of construction planned to start in 2026/27 | Planning | Funding | Wayleave- WCG roads | High | Electrical technical | M.Olivier | 2027-07-01 | 2030-06-30 | Related to capacity for Louis Fourie Corridor project
16 | Mossel Bay Municipality | Garden Route | Roads & SW for The Louis Fourie Corridor Plan – Apiesdoring to Danabaai / Flora to Crotz and Intersection plus SW |  | Asla Park /Heiderand/ Danabaai | 200000000 | CRR/BFI/Loan | Roads Master Plan | Planning stage | Work In progress | Funding & Environmental challenges | DoI, DLG, GRDM | High | Roads & Stormwater | Jean Cox | 05/10/2026 | 30/06/2029 |  | Funding
17 | Mossel Bay Municipality | Garden Route | Roads & SW for Aalwyndal, the necessary road upgrades, and adding the new N2 interchange at Mayixhale |  | Aalwyndal | 200000000 | CRR/BFI/Loan | Roads Master Plan | Planning stage | Work In progress | Funding & Environmental challenges | DoI, DLG, GRDM | High | Roads & Stormwater | Jean Cox | 05/10/2027 | 30/06/2030 |  | Funding
18 | Mossel Bay Municipality | Garden Route | Roads master plan - complete the Danabaai link road to N2 with interchange |  | Danabaai/ MossDustria | 120000000 | CRR/BFI/Loan | Roads Master Plan | Planning stage | Work In progress | Funding & Environmental challenges | DoI, DLG, GRDM | High | Roads & Stormwater | Jean Cox | 05/10/2027 | 30/06/2030 |  | Funding
19 | Mossel Bay Municipality | Garden Route | Doubling Mayixhale Road to accommodate the future Traffic Volumes |  | KwaNonqaba | 200000000 | TBC | Roads Master Plan | Planning stage | Work In progress | Funding, Social Issues, Land Issues | DoI, DLG, GRDM | High | Roads & Stormwater | Jean Cox |  |  |  | Funding
20 | Mossel Bay Municipality | Garden Route | SW Masterplan for CBD - SW bottlenecks, replacing old pipes |  | Mossel Bay CBD | 80000000 | TBC | CBD Stormwater Master Plan | Planning stage | Work In progress | Funding | DoI, DLG, GRDM | High | Roads & Stormwater | Jean Cox |  |  |  | Funding
21 | Mossel Bay Municipality | Garden Route | Rehab beach outlets - storm surges damage outlets – retreat, rebuild or fix |  | From Glentana to Dana Bay | 50000000 | TBC | Stormwater Outlet Assessment Report | Planning stage | Work In progress | Funding, Environmental, Land Issues | DoI, DLG, GRDM | High | Roads & Stormwater | Jean Cox |  |  |  | Funding
22 | Mossel Bay Municipality | Garden Route | Roads masterplan - Wassenaar N2 Culvert linking to TR33/1 Louis Fourie Rd |  | Hartenbos | 150000000 | TBC | Roads Master Plan | Planning stage | Work In progress | Funding, Town Panning Issues, Land Use Issues, Environmental Issues, Roads Authority | DoI, DLG, GRDM | High | Roads & Stormwater | Jean Cox |  |  |  | Funding
23 | Mossel Bay Municipality | Garden Route | Roads Master Plan - a second access road for Monte Christo area |  | Hartenbos Northe | 50000000 | TBC | Roads Master Plan | Planning stage | Work In progress | Funding, Town Panning Issues, Land Use Issues, Environmental Issues, Roads Authority | DoI, DLG, GRDM | High | Roads & Stormwater | Jean Cox |  |  |  | Funding
24 | Mossel Bay Municipality | Garden Route | The Island Bridge - complete new H4 treated wooden beams, planks, and handrails |  | Great Brak River/The Island | 5000000 | CRR | Bridge Investigation Report | Planning stage | Work In progress | Funding, Environmental Issues | DoI, DLG, GRDM | High | Roads & Stormwater | Jean Cox |  |  |  | Funding

## LG Matzikama
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assitance Required
1 | Matzikama Municipality | West Coast | Upgrade of Lutzville Water Treatment Works | Water | Lutzville | 30000000 | MIG / WSIG | 5-year Projects List 10 April 2026; Water Resilience Implementation Plan | Concept / Design | Existing WTW beyond design life and capacity limits | Funding constraints | Immediate / Short Term | DLG, DWS | Technical Services |  | 2026/27 | 2028/29 | New pressure filters, refurbishment and upgrade of existing filters, pipework, chlorination system, pumpstation, buildings and structures. | Yes
2 | Matzikama Municipality | West Coast | Lutzville West Raw Water Dam and Water Treatment Works Refurbishment & Upgrade | Water | Lutzville West | 27000000 | MIG / Dept Land Reform and Rural Development | Priority Project List 2023; 5-year Projects List | Concept / Design | Ageing infrastructure and raw water storage deficiency | Funding constraints | Immediate / Short Term | DLG, DWS | Technical Services |  | 2026/27 | 2028/29 | New Raw water Dam, refurbishment of existing dam and upgrade of WTW, new booster PS, and associated pipework. | Yes
3 | Matzikama Municipality | West Coast | Upgrade of bulk pump line from Vredendal to Vanrhynsdorp | Water | Municipal Wide | 500000000 | SIDIFF | 5-year Projects List 10 April 2026; Water Resilience Implementation Plan | Conceptual | Ageing infrastructure and service failures identified | Funding constraints & infrastructure backlogs | Immediate / Short Term | DLG, DWS | Technical Services |  | 2026/27 | 2028/29 | Priority catalytic project to secure bulk water conveyance to Vanrhynsdorp | Yes
4 | Matzikama Municipality | West Coast | Bulk Water from the Clanwilliam Water Scheme Conveyance to Bitterfontein | Water | Municipal Wide | 400000000 | SIDIFF | 5-year Projects List 10 April 2026; Catalytic Projects Framework | Conceptual/ Feasibility | Greenfields- Existing water source is Groundwater. Groundwater effected by drought. Alternative water source for resilience | Funding constraints/ design complexity/ private land access/ environmental approval/ remote location | Long Term | DLG, DWS | Technical Services |  | 2030/31 | 2035/36 | Catalytic project to secure bulk water conveyance to Bitterfontein to unlocks mining and regional economic opportunities. | Yes
5 | Matzikama Municipality | West Coast | Vredendal Water Treatment Works Major Expansion and Refurbishment | Water | Vredendal | 80000000 | MWKG (Main) / various | Water Resilience Implementation Plan; 5-year Projects List | Conceptual | Existing capacity constraints | Funding constraints; design complexity | Short Term | DLG, DWS | Technical Services |  | 2028/29 | 2029/30 | Upgrade capacity from 8 ML/day to 20 ML/day and refurbish sand filters, New reservoir and upgrade Pumpstation | Yes
6 | Matzikama Municipality | West Coast | Construction of New Raw Water Storage Dams in Vredendal | Water | Vredendal | 100000000 | WSIG/ Dept of Human Settlements | 5-year Projects List 10 April 2026; Water Resilience Implementation Plan | Conceptual | No raw water storage buffer for peak demand and drought periods | Funding constraints; environmental approvals | Medium Term | DLG, DWS | Technical Services |  | 2029/30 | 2031/32 | New raw water dam to increase resilience and refurbish existing dams | Yes
7 | Matzikama Municipality | West Coast | Vanrhynsdorp Bulk Water Infrastructure Upgrade (Internal Networks & Reservoirs) | Water | Vanrhynsdorp | 28000000 | WSIG / MIG | 5-year Projects List 10 April 2026 | Conceptual | Internal distribution network ageing and undersized | Funding constraints | Short Term | DLG, DWS | Technical Services |  | 2028/29 | 2029/30 | Includes repair works at existing reservoir and internal reticulation upgrades | Yes
8 | Matzikama Municipality | West Coast | Vredendal North New Dedicated Bulk Water Pipeline & Pump Station Upgrade | Water | Vredendal North | 40000000 | WSIG / MIG | Water Resilience Implementation Plan; Priority Project List 2023 | Conceptual | Lack of dedicated bulk supply to Vredendal North reservoir | Funding constraints | Medium Term | DLG, DWS | Technical Services |  | 2028/29 | 2030/31 | New dedicated rising main from PS to reservoir and improve pressure and reliability for human settlements | Yes
9 | Matzikama Municipality | West Coast | Strandfontein Desalination (Reverse Osmosis) Plant Commissioning | Water | Strandfontein | 10000000 | MIG / WSIG | Priority Project List 2023; Water Resilience Implementation Plan | Construction- Stopped due to funding shortage | Plant incomplete due to funding gap; coastal drought vulnerability | Funding constraints | Medium Term | DLG, DWS | Technical Services |  | 2028/29 | 2029/30 | Complete commissioning of existing RO plant to secure water supply and improve resilience for Strandfontein and Doringbaai water supply system. | Yes
10 | Matzikama Municipality | West Coast | Klawer Water Supply Augmentation Programme | Water | Klawer | 25000000 | MIG / WSIG / Mun Intervention Grant/ MWRG | 5-year Projects List 10 April 2026; Water Resilience Implementation Plan | Various (Conceptual to Implementation) | Multiple small projects (reservoir, boreholes, pump stations) need coordination | Funding constraints and project packaging | Medium Term | DLG, DWS, Technical Services | Technical Services |  | 2025/26 | 2027/28 | Bundle of Klawer high‑level reservoir, equipping of boreholes, pump station refurbishment and pipe upgrades | Yes
11 | Matzikama Municipality | West Coast | Ebenhaezer–Strandfontein–Doringbaai Bulk Water Supply System Upgrade | Water | Ebenhaezer, Strandfontein, Doringbaai | 300000000 | IHSDS (Dept of Human Settlements) / MIG | Water Resilience Implementation Plan; 5-year Projects List | Conceptual | Inadequate pipeline capacity to coastal towns | Funding constraints | Medium Term | DLG, DWS | Technical Services |  | 2027/28 | 2029/30 | Upgrade Ebenhaezer WTW including pumpstation and replace bulk pipeline from Strandfontein to Doringbaai | Yes
12 | Matzikama Municipality | West Coast | Matzikama Regional Groundwater Development and Augmentation Programme | Water | Multiple towns (Papendorp Vredendal, Vanrhynsdorp, Lutzville etc.) | 80000000 | MWRG / DLG Geohydrology Programme / MIG/ WSIG | Water Resilience Implementation Plan; 5-year Projects List | Conceptual / Ongoing exploration | Over‑reliance on surface water; many borefields need development | Funding constraints; geohydrological uncertainty | Short to Medium Term | DLG, DWS, Geohydrology specialists | Technical Services |  | 2028/29 | 2030/31 | Aggregation of all major borehole development projects (Papendorp, Vredendal, Vanrhynsdorp, Lutzville, etc.) into one catalytic programme | Yes
13 | Matzikama Municipality | West Coast | Vanrhynsdorp Sewer Infrastructure and Network Upgrade | Sanitation | Vanrhynsdorp | 98000000 | WSIG / MIG | 5-year Projects List 10 April 2026 | Conceptual | Severe sewer network deterioration and capacity limitations | Funding constraints | Medium Term | DLG, DWS | Technical Services |  | 2028/29 | 2030/31 | New sewer network in Vanrhynsdorp and refurbishment and upgrade of the waste water treatment works | Yes
14 | Matzikama Municipality | West Coast | Waterborne Sewer Systems for DMA Areas | Sanitation | Municipal Wide (DMA areas) | 70000000 | WSIG / MIG | 5-year Projects List 10 April 2026 | Conceptual | Current sanitation systems inadequate for future housing and densification | Funding constraints; bulk infrastructure planning | Medium / Long Term | DLG, DWS, Human Settlements | Technical Services |  | 2029/30 | 2032/33 | Replace VIP toilets with waterborne sewer reticulation in previous District Municipal Area | Yes
15 | Matzikama Municipality | West Coast | Vredendal North Wastewater Treatment Works Upgrade | Sanitation | Vredendal North | 90000000 | MIG / WSIG | Priority Project List 2023; 5-year Projects List | Conceptual/Design | WwTW overloaded and non‑compliant | Funding constraints | Short Term | DLG, DWS | Technical Services |  | 2028/29 | 2030/31 | Refurbish and upgrade Waste Water Treatment Works to meet Green Drop standards and accommodate population growth | Yes
16 | Matzikama Municipality | West Coast | Ebenhaeser Sewer Infrastructure and Network Upgrade | Sanitation | Ebenhaeser | 45000000 | MIG / WSIG | 5-year Projects List 10 April 2026 | Conceptual/Design | Aging sewer network with frequent blockages | Funding constraints | Long Term | DLG, DWS | Technical Services |  | 2028/29 | 2030/31 | New sewer network in Ebenhaeser and refurbishment and upgrade of the waste water treatment works | Yes
17 | Matzikama Municipality | West Coast | Lutzville Sewer Network Upgrade | Sanitation | Lutzville | 56000000 | MIG / WSIG | 5-year Projects List 10 April 2026 | Conceptual | Existing network deteriorated and undersized | Funding constraints | Immediate to Short Term | DLG, DWS | Technical Services |  | 2027/28 | 2030/31 | Upgrade of sewer reticulation in Lutzville and refurbishment and upgrade of the waste water treatment works | Yes
18 | Matzikama Municipality | West Coast | Kliprand Brine Treatment Facility & Associated WWTW Infrastructure | Sanitation | Kliprand | 8000000 | WSIG / Rural Development | 5-year Projects List 10 April 2026; Water Resilience Implementation Plan | Conceptual | No brine treatment | Funding constraints/ remote location/ environemental approval | Short Term | DLG, DWS | Technical Services |  | 2028/29 | 2027/28 | Brine treatment to enable safe wastewater disposal | Yes
19 | Matzikama Municipality | West Coast | Infrastructure Development for Human Settlement Projects (All Wards) | Multi-Sector / Human Settlements | All wards | 250000000 | MIG / Human Settlements / USDG | 5-year Projects List 10 April 2026 | Conceptual | Bulk infrastructure not in place to support planned housing projects | Funding constraints and inter‑governmental coordination | Medium to Long Term | DLG, Human Settlements, DWS | Technical Services / LED |  | 2029/30 | 2032/33 | Catalytic bulk services (roads, water, sewer) to unlock housing delivery across all wards | Yes
20 | Matzikama Municipality | West Coast | Municipal Roads Rehabilitation and Upgrading Programme | Transport | Municipal Wide | TBD (∼R340 000 000) | Provincial / MIG / Own Revenue | 5-year Projects List 10 April 2026 | Conceptual / Identification | Surfaced roads deteriorating and proclaimed provincial roads in poor condition | Funding model limitations | Medium to Long Term | DLG, DPWI, Provincial Roads | Technical Services |  | 2025/26 onwards | 2045/46 | Long‑term programme to gradually refurbish all municipal and provincial proclaimed roads; exact cost to be determined by detailed assessment | Yes
21 | Matzikama Municipality | West Coast | Matzikama Water Conservation and Demand Management (WCDM) Programme | Water | Municipal Wide | 300000000 | WSIG / Own Revenue / MIG | 5-year Projects List; Water Resilience Implementation Plan; Priority Project List | Various (Concept to Implementation) | High water losses (physical and commercial) jeopardising supply | Funding constraints and institutional capacity | Immediate to Short Term | DLG, DWS | Technical Services |  | 2026/27 | 2029/30 | Combines AC pipe replacement (R15m) Vredendal WCWDM (R60.5m) telemetry upgrades meter replacement and revenue enhancement | Yes
22 | Matzikama Municipality | West Coast | Bitterfontein–Nuwerus–Rietpoort Water Security Project | Water | Bitterfontein, Nuwerus, Molsvlei, Rietpoort | 30000000 | WSIG / MIG | Water Resilience Implementation Plan; Priority Project List | Conceptual | Water supply deficits and over‑reliance on ageing boreholes | Funding constraints; geohydrological investigations | Medium / Long Term | DLG, DWS | Technical Services |  | 2027/28 | 2032/33 | Includes drilling additional boreholes borehole refurbishment pump station repairs and possible interconnection for the southern settlements | Yes

## LG Oudtshoorn
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Support Required ( Sector Depts / SIDAFF) | Priority | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance Required | Last Update Date (June 2026)
1 | Oudtshoorn | Garden Route | Sewerage Network Infrastructure (Oudtshoorn) | Sanitation | Oudtshoorn | 50000000 | TBC | WSDP | In intialialization Stage | In intialialization Stage | Aging pitch-fiber pipes frequently cause blockages and environmental hazards. |  | Yes | Water & Sanitation | Director: Infrastructure |  | Phased over 3 years |  |  | 25/06/2026
2 | Oudtshoorn | Garden Route | Upgrading Oudtshoorn Wastewater Treatment Works (WWTW) | Sanitation | Oudtshoorn | 120000000 | TBC | WSDP | In intialialization Stage | In intialialization Stage | Existing WWTW is nearing capacity. |  | Yes | Water & Sanitation | Director: Infrastructure |  | 2 years |  |  | 25/06/2027
3 | Oudtshoorn | Garden Route | Increase Hydraulic Capacity – East & West Bank Collector Sewers | Sanitation |  | 55000000 | TBC | WSDP | In intialialization Stage | In intialialization Stage | Existing lines lack capacity for peak flows, causing overflows. |  | Yes | Water & Sanitation | Director: Infrastructure |  | 2 years |  |  | 25/06/2028
4 | Oudtshoorn | Garden Route | Vandal-Proofing of Sewer Networks | Sanitation |  | 30000000 | TBC | WSDP | In intialialization Stage | In intialialization Stage | Blockages due to dumped waste cause service disruptions. |  | Yes | Water & Sanitation | Director: Infrastructure |  | Phased over 3 years |  |  | 25/06/2029
5 | Oudtshoorn | Garden Route | Upgrading Oudtshoorn WTW | Sanitation | Oudtshoorn | 120000000 | TBC | WSDP | In intialialization Stage | In intialialization Stage | Raw water quality deteriorates during heavy rainfall. |  | Yes | Water & Sanitation | Director: Infrastructure |  | 4–5 years from initiation |  |  | 25/06/2030
6 | Oudtshoorn | Garden Route | Upgrading De Rust Wastewater Treatment Works (WWTW) | Sanitation | De Rust | 10000000 | TBC | WSDP | In intialialization Stage | In intialialization Stage | Current system has limited capacity and no formal inlet works. |  | Yes | Water & Sanitation | Director: Infrastructure |  | 1–2 years |  |  | 25/06/2031
7 | Oudtshoorn | Garden Route | Security Fencing at De Rust and Oudtshoorn Wastewater Treatment Works | Sanitation | De Rust | 10000000 | TBC | WSDP | Implementation ready | Pre-feasibility | Sites lack adequate fencing, posing risks of vandalism and theft. |  | Yes | Water & Sanitation | Director: Infrastructure |  | 1–2 years |  |  | 25/06/2032
8 | Oudtshoorn | Garden Route | Blossoms Wellfield Phase 1B | Water | Blossoms | 50000000 | RBIG/BFI | WSDP | In intialialization Stage | In intialialization Stage | Blossoms Wellfield Phase 1B |  | Yes | Water & Sanitation | Director: Infrastructure | 2030/31 |  | Increases groundwater supply capacity to improve drought resilience and reduce reliance on surface water sources. |  | 25/06/2033
9 | Oudtshoorn | Garden Route | Blossoms Wellfield Phase 2 | Water | Blossoms | 150000000 | RBIG/BFI | WSDP Revision 4 - July 2025 WSDP Executive Summary 2023 Rev 00 | In intialialization Stage | In intialialization Stage | Blossoms Wellfield Phase 2 |  | Yes | Water & Sanitation | Director: Infrastructure | 2029/30 |  | Further expands sustainable groundwater abstraction to support growing demand in Oudtshoorn and surrounding areas. |  | 25/06/2034
10 | Oudtshoorn | Garden Route | Blossoms Wellfield Phase 3 | Water | Blossoms | 250000000 | RBIG/BFI |  | In intialialization Stage | In intialialization Stage | Blossoms Wellfield Phase 3 |  | Yes | Water & Sanitation | Director: Infrastructure | 2029/30 |  | Completes full development of the Blossoms wellfield to secure long-term groundwater supply for the municipal system. |  | 25/06/2035
11 | Oudtshoorn | Garden Route | Klein Karoo Rural Water Supply Scheme: Refurbishment of network, resrevoirs & pump stations | Water | Klein Karoo | 25000000 | WSIG | WSDP Executive Summary 2023 Rev 00 | In intialialization Stage | In intialialization Stage | KKRWSS: Refurbishment of network, resrevoirs & pump stations |  | Yes | Water & Sanitation | Director: Infrastructure | 2027/28 |  | Improves reliability and efficiency of the regional bulk supply scheme serving Dysselsdorp, De Rust and rural users |  | 25/06/2036
12 | Oudtshoorn | Garden Route | KKRWSS: Meter replacement | Water | Klein Karoo | 60000000 | WSIG |  | In intialialization Stage | In intialialization Stage | Replacement of old water meters with Smart (prepaid) meters - Tackle non-revenue water issue |  | Yes | Water & Sanitation | Director: Infrastructure | 2027/28 |  | Reduces non-revenue water and improves billing accuracy, demand management and financial sustainability of the water service. |  | 25/06/2037
13 | Oudtshoorn | Garden Route | AC Pipe replacement | Water | Oudtshoorn | 148810700 | Own funding/Loans/WSIG | List of Priority Projects 2023 (October 2025) | In intialialization Stage | In intialialization Stage | Replacement of AC pipes in Old towns Oudtshoorn and De Rust |  | Yes | Water & Sanitation | Director: Infrastructure | 2026/27 |  | Replaces ageing asbestos cement pipes reducing leaks and bursts in Oudtshoorn and De Rust. |  | 25/06/2038
| Oudtshoorn | Garden Route | AC Pipe replacement | Water | Oudtshoorn | 147689300 | MIG | List of Priority Projects 2023 (October 2025) | In intialialization Stage | In intialialization Stage | Replacement of AC pipes in previous disadvantaged areas |  | Yes | Water & Sanitation | Director: Infrastructure | 2031/32 |  | Improves reliability of water services and addresses historical infrastructure backlogs in vulnerable communities. |  | 25/06/2039
| Oudtshoorn | Garden Route | Invasive Plant Eradication | Water | Oudtshoorn | 2000000 | Currently Unfunded | Priority Projects Excel File October 2025 | In intialialization Stage | In intialialization Stage | Invasive plant management in the dam catchment area |  | Yes | Water & Sanitation | Director: Infrastructure | 2031/32 |  | Improves runoff and groundwater recharge by reducing invasive vegetation in the Raubenheimer dam catchment. |  | 25/06/2040
| Oudtshoorn | Garden Route | Bulk Supply Line from Koos Raubenheimer dam | Water | Koos Raubenheimer | 300000000 | RBIG | Priority Projects Excel File October 2025 | In intialialization Stage | In intialialization Stage | Investigate possible upgrading of bulk supply lines from Koos Raubenheimer dam |  | Yes | Water & Sanitation | Director: Infrastructure | 2031/32 |  | increase and ensure conveyance capacity from the main dam to ensure reliable supply during peak demand |  | 25/06/2041
| Oudtshoorn | Garden Route | WTW at Koos Raubenheimerdam | Water | Koos Raubenheimer | 120000000 | RBIG | Priority Projects Excel File October 2025 | In intialialization Stage | In intialialization Stage | Upgrade the WTW for treatment of high turbidity water at Koos Raubenheimerdam |  | Yes | Water & Sanitation | Director: Infrastructure | 2027/28 |  | Ensures treatment capacity during high turbidity events, protecting drinking water quality and supply reliability. |  | 25/06/2042
| Oudtshoorn | Garden Route | Water to Rural Areas | Water | Oudtshoorn | 30000000 | Currently Unfunded | Project List from Willem November 2025 | In intialialization Stage | In intialialization Stage | Supply of water to rural areas currently not serviced by networks to reduce delivery of water by tankers |  | Yes | Water & Sanitation | Director: Infrastructure | 2031/32 |  | xtends reticulated supply to rural communities and reduces costly tanker deliveries. |  | 25/06/2043
| Oudtshoorn | Garden Route | Rust & Vrede Pipeline | Water | Dysselsdorp & De Rust | 140000000 | WSIG | WSDP Revision 4 - July 2025 WSDP Executive Summary 2023 Rev 00 | In intialialization Stage | In intialialization Stage | Pipeline to supply water from the Rust & Vrede Waterfall to Dysselsdorp WTW for distribution to KKRWSS, Dysselsdorp and De Rust |  | Yes | Water & Sanitation | Director: Infrastructure | 2031/32 |  | Improves distribution efficiency by transferring existing water to Dysselsdorp WTW for supply to KKRWSS and De Rust. |  | 25/06/2044
| Oudtshoorn | Garden Route | Tributary CC Dam (Kombuis) | Water | Kombuis | 450000000 | RBIG | Project List from Willem November 2025 | In intialialization Stage | In intialialization Stage | Building of a dam in the Kombuis valley to augment the Raubenheimer Dam and secure long-term surface water storage |  | Yes | Water & Sanitation | Director: Infrastructure | 2029/30 |  | Increases surface water storage capacity to secure long-term supply and improve drought resilience. |  | 25/06/2045
| Oudtshoorn | Garden Route | Backup power for boreholes on KKRWSS and WWTW and De Rust WTW | Water | De Rust | 30000000 | Currently Unfunded | List of Priority Projects 2023 (October 2025) | In intialialization Stage | In intialialization Stage | Second phase of providing back-up power to the KKRWSS boreholes as well as for the WWTW's and De Rust WTW |  | Yes | Water & Sanitation | Director: Infrastructure | TBC |  | Ensures continuous water supply during electricity outages and protects critical water infrastructure operations. |  | 25/06/2046
| Oudtshoorn | Garden Route | Water Demand Management - Bulk Infrastructure | Water | Oudtshoorn | 5000000 | Currently Unfunded | Water Resilience Funding Consolidation - March 2025 | In intialialization Stage | In intialialization Stage | Water Demand Management - Bulk Infrastructure |  | Yes | Water & Sanitation | Director: Infrastructure | TBC |  | Reduces water losses and optimises use of limited water resources through improved bulk system control. |  | 25/06/2047
| Oudtshoorn | Garden Route | Updating of the Master Plan | Water | Oudtshoorn | 4000000 | Currently Unfunded |  | In intialialization Stage | In intialialization Stage | Review and update Water Master Plan |  | Yes | Water & Sanitation | Director: Infrastructure | TBC |  | Provides updated planning framework to guide future infrastructure investment and secure long-term water security. |  | 25/06/2048
| Oudtshoorn | Garden Route | Upgrading De Rust Chlorination Station | Water | De Rust | 2000000 | Currently Unfunded | Infrastructure Needs for Oudtshoorn | In intialialization Stage | In intialialization Stage | Modernize chlorination system to ensure effective disinfection of drinking water. |  | Yes | Water & Sanitation | Director: Infrastructure | 2027/28 |  | Ensures compliant disinfection and protects public health through reliable drinking water treatment. |  | 25/06/2049

## LG Overstrand
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance Required | Last Update Date
1 | Overstrand Municipality | Overberg District | Hermanus Sea water desalination plant | Water | Hermanus | Capex R350m | Operational | IDP Options analysis Feasibility study | Planning | Planning in progress Transactional Advisors appointed EIA, Sea water abstraction and discharge permits, contracting options, funding sources, etc | Access to land in the Hermanus New Harbour. Funding for this project, possible RBIG, WSIG and/or MIG. | Short term | Urgent assistance required to unlock land from the National DPW in the Hermanus New Harbour for this project. We require funding for this project, possible RBIG, WSIG and/or MIG. | Infrastructure Services | Hanre Blignaut | Construction start July 2027 | 2028-06-01 | We secured funding for the preparation phase of this project from DBSA/Water Project Office. | Please facilitate/ intervene to gain access to land in the Hermanus New Harbour. | 2026-06-24
2 | Overstrand Municipality | Overberg District | Bulk Electrical Infrastructure, New 66kV substation for the Hermanus Area. | Electricity | Hermanus | R120m | INEP R10m HSDG BICL R50m Municipal | IDP Detail design report Tender Document | Ready to Tender pending funding | Tender Document ready for advertising | The project is not fully funded yet | Short term | Require more funding from INEP and DOI Human Settlements | Infrastructure Services | George Lotter | Construction start July 2027 | 2029-06-01 | Bulk Electrical Infrastructure to provide for growing demand in the Hermanus Industrial Area, Hermanus New Harbour Area and the Hermanus Schulphoek housing project (4000 housing opportunities) | Funding | 2026-06-24
3 | Overstrand Municipality | Overberg District | Hawston Waste Water Treatment Plant refurbish, upgrade and extension. | Sewerage | Hawston | R100m | R16m MIG R34m Municipal | IDP Detail design report | Planning | EIA in progress Tender documents being prepared | Funding required (WSIG application not approved) | Short term | Funding | Infrastructure Services | Hanre Blignaut | Construction start September 2027 | 2029-06-01 |  | Funding | 2026-06-24
4 | Overstrand Municipality | Overberg District | Refurbishment of Water Reticulation Network | Water | Overstrand wide | R500m | R12m Municipal R135m SIDAFF | IDP | Planning | SIDAFF phase 1, 2a and 2b |  | Short term and ongoing |  | Infrastructure Services | Hanre Blignaut | Construction start July 2027 | 2030-06-01 | We are relying heavily on the SIDDAF funding for these two projects and |  | 2026-06-24
5 | Overstrand Municipality | Overberg District | Extension of Sewer Networks | Sewerage | Hawston Kleinmon, Gansbaai Hermanus | R500m | R45m SIDAFF R3m Municipal | IDP | Planning | SIDAFF phase 1, 2a and 2b |  | Short term and ongoing |  | Infrastructure Services | Hanre Blignaut | Construction start Aug 2027 | 2030-06-01 |  |  | 2026-06-24
6 | Overstrand Municipality | Overberg District | Hermanus Schulphoek housing project, bulk services roads, sewer, water, stormwater | Housing | Hermanus | R500m | UISP/HSDG | IDP | Planning | EIA in progress |  | Medium and Long Term |  | Infrastructure Services | Dennis Hendriks | Construction start Jan 2028 |  |  |  | 2026-06-24
7 | Overstrand Municipality | Overberg District | Greater Hermanus Priority Human Settlement Housing Development | Housing | Greater Hermanus Area | R120m | HSDG | IDP Development Framework | Planning | Prelim planning being done |  | Medium and Long Term |  | Infrastructure Services | Dennis Hendriks | Construction start July 2028 |  |  |  | 2026-06-24
8 | Overstrand Municipality | Overberg District | Upgrade Hermanus Taxi Rank (Central Transport Hub) | Transport | Greater Hermanus Area | R45m |  | IDP Development Framework | Planning | Prelim planning done | Funding | Short Term | Funding | Infrastructure Services | Dennis Hendriks | Construction start July 2028 |  |  |  | 2026-06-24
9 | Overstrand Municipality | Overberg District | Hermanus Parallel Road (Sandbaai to Onrus) | Transport | Greater Hermanus Area | R35m |  | IDP | Planning | Prelim planning done | Funding | Short Term | Funding | Infrastructure Services | Dennis Hendriks | Construction start July 2028 |  |  |  | 2026-06-24
10 | Overstrand Municipality | Overberg District | Implementation of NMT Master Plan | Transport | Overstrand wide | R50m |  | IDP NMD Master Plan | Planning | Prelim planning done | Funding | Short Term | Funding | Infrastructure Services | Dennis Hendriks | Construction start July 2028 |  |  |  | 2026-06-24
11 | Overstrand Municipality | Overberg District | Development of ECDs | Social Development | Kleinmond Masakhane Pearly Beach |  |  | IDP | The Department of Rural Development and Land Reform approved three Early Childwood Development (ECD) facilities in the Overstrand at a total cost of R10,5m. The MoU was signed in 2019. To date the facilities have not been constructed. There is still a great need for these facilities in the three communities. |  |  |  |  | Infrastructure Services | Dennis Hendriks |  |  |  | Please facilitate/ intervene to ensure that construction of these the facilities go ahead. | 2026-06-24
12 | Overstrand Municipality | Overberg District | Organic Waste Diversion Targets for the Western Cape | Waste | Overstrand wide |  |  | Waste Disposal Licence | The most resent permit for the operation of the Gansbaai Waste Disposal Facility includes the following requirement: "16,5,2 …... meet these targets for diversion of organic waste …. to reach a 50% diversion rate by 2022 and 100% by 2027" . This requirement is only applicable in the Western Cape, the national norm is 50%. We are already at 52% diversion. The required target of 100% diversion is not practical, affordable or achievable, especially for small towns. |  |  |  |  | Infrastructure Services | Hanre Blignaut |  |  |  | Please take the matter up with the DEADP and request that the national norm of 50% be applied in the Western Cape. | 2026-06-24

## LG Prince Albert
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Readiness Stage | Status / Progress | Key Blockages / Constraints | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Contact Details of Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | Last Update Date
1 | Prince Albert Municipality | Central Karoo | Finalise Phase 3 implementation plan for Newton Park, Welgemoed and Bitterwater - water & sewer upgrade (network, meters, reticulation) | DWS: WSIG | Leeu Gamka | 42000000 | Phase 1- Package Plant Complete: Phase 2 - Reservoir and Pump station. (Pump station was omitted)- Reservoir is complete: Phase 3- Funding approved, R11m -allocated for FY26/27.Preplanning | Funding approved | None | DWS, DLG, MISA | Technical Services | Ashley America | ashley@pamun.gov.za | 2026-06-01 | 2028-06-01 | Funding has been approved for the completion of Ph3- R42 mil gazettedfor FY26/27;27/28 and FY28/29 | 2026-04-01
2 | Prince Albert Municipality | Central Karoo | Klaarstroom Water Supply System | DWS: WSIG | Klaarstroom | 70000000 | The project is at the planning stage | No funding has been committed | There is not surface dam in Klaarstroom, Witrivier might be the solution. | DWS, DLG, MISA | Technical Services | Ashley America | ashley@pamun.gov.za | 2026-02-01 | 2030-06-01 | The project has not yet been captured, but there is a need for water supply and surface water in Klaarstroom. The project to be incl. on the revised and updated Master Plan for the next IDP Planning Cycle 2027-2031 | 2026-02-01
3 | Prince Albert Municipality | Central Karoo | Confirm funding pathway for Raw Water Dam construction, based on completed feasibility. | DWS: RBIG/WSIG | Prince Albert | 110000000 | Feasibility study report complete. | Funding not approved yet | The project must be submitted to DLG as one of the project that can be motivated as the bankable project. | DWS, PT, DLG | Water Services / Municipal Manager | Ashley America | ashley@pamun.gov.za | 2027-06-01 | 2029-06-01 | Stakeholders Meeting has been initiated. | 2025-07-01
4 | Prince Albert Municipality | Central Karoo | Engage CKDM & DLG on regional landfill & yellow fleet shared service model. | DLG / DoI | Prince Albert | 100000000 | 5 Yellow fleet for waste has been pucharced on Municipal Side, using MIG and Own Funding. (Compactor Truck, TLB, Front Loader, Tipper Truck and Dozer) | No funding has been committed | No formal discussions has taken place yet, to determine the cost of regional landfill site and the operational costs. The PALM has conducted a high level estimate through its strategic planning process to develop a new disposal cel - R22mil. | CKDM, DoI, DLG | Waste & Roads | Municipal Manger/Technical Services | ashley@pamun.gov.za / thys@pamun.gov.za | 2023-06-01 | 2028-06-01 | Engagement should be initiated between CKDM and local municipalities, No SLA has been signed on the yellow fleed with DoI. The PALM to investigate developing of a new Waste Disposal Cell at the Farm Treintjies Rivier. | 2025-08-01
5 | Prince Albert Municipality | Central Karoo | Develop septic-to-waterborne conversion strategy for priority neighborhoods | DWS: WSIG | Prince Albert | 63700283 | Feasibility study report complete. | Funding not approved yet | Funding steam is required for implemetation of this project, either WISG or RBIG | DWS, DEADP, DLG | Sanitation | Ashley America | ashley@pamun.gov.za | 2028-06-01 | 2030-07-01 | Report Complete, we need to submit application for funding. Will be submitted for WSIG for the new funding cycle 2028 | 2024-02-01
6 | Prince Albert Municipality | Central Karoo | Prepare electrical network upgrade plan and identify priority feeder/substation interventions | INEP | Prince Albert | 12760000 | Concept stage of the project | No Funding | No funding stream has been identified for this project. | Eskom, DLG | Electrical technical | Thembisile Tukani | thembisile@paman.gov.za | 2026-01-01 | 2028-06-01 | There is a need to develop a detailed network assessment report with revised figures, the figures provided are mainly for ground transformers, pole transformer and Mini Sub-stations. | 2024-06-01
7 | Prince Albert Municipality | Central Karoo | Initiate Solar PV / Energy Resilience feasibility in partnership with Laingsburg. | DLG | Prince Albert | 170000000 | Feasibility study report complete on the side of Prince Albert. NoI submitted to DEADP along with application for EMpr exclusion ito GN 4558 | No Funding | No funding stream has been identified for this project. | DMRE, GreenCape, DLG, DEADP, MISA | Energy | Ashley America/ Bruce Ingram and Zolile | ashley@pamun.gov.za / zolile@pamun.gov.za / bruce.ingram@pm.me | 2023-06-01 | 2030-06-01 | The last initiative was the one of investors summit. MISA Electrical Engineer requested to provide assistance in developing Request for Proposals. DEAP intervention required to finalise EMpr. | 2025-09-01
8 | Prince Albert Municipality | Central Karoo | Review and update development charges & capital contribution policy to support housing pipeline | DEAF | Prince Albert | 30000 | Draft policy has been developed, we are awaiting on department for further assistance and advise. | Only admin support | Confirmation of DEAF to send the official that can assist the municipality. | DEADP, DLG, PT | Planning & Finance | Ms Vele and Zolile | zolile@pamun.gov.za / mvele@pamun.gov.za | 2023-06-01 | 2026-06-01 | Advise of not implemeting Capital Contribution on small municipalities and those who has 60% of households being indigent. | 04 & 05 Nov 2025
9 | Prince Albert Municipality | Central Karoo | Leeu Gamka Econimic Development | DWS, MISA, DLG | Prince Albert | 40000000 | The municipality has the plan of upgrading the area to be a logistic hub for verious actiovities, like agriculture, processing, other activities that will be suitable for a corridor that is between Beaufort West and Cape Town. | No funding has been committed | No funding stream has been identified for this project. | DEADP, DWS, DMRE, Eskom, DLG | Community Services and Town Planning | Ms Gwynnefer and Vele | gwynnefer@pamun.gov.za /mvele@pamun.gov.za | 2026-02-01 | 2030-06-01 | Projects like this can be a game charger for the area that has the highiest un-employment rate | 2025-11-01
10 | Prince Albert Municipality | Central Karoo | Upgrading of R407 Route | DoI, DLG | Prince Albert | 50000000 | The municipality would like to have a road shoulder provider on both sides of the road | No funding has been committed | No funding stream has been identified for this project. | DoI, DLG | Office of the Municipal Manager | Mr Thys Gilliomee | zolile@pamun.gov.za / thys@pamun.gov.za | 2026-02-01 | 2030-06-01 | The project is about providing safety for the road user. | 2025-11-01
11 | Prince Albert Municipality | Central Karoo | Maintenance of Gravel Roads in Prince Albert | DoI, DLG | Prince Albert | 70000000 | Most of the gravel roads around the area of Prince Albert to the farms are not well maintened | No funding has been committed | No funding stream has been identified for this project. | DoI, DLG | Office of the Municipal Manager | Mr Thys Gilliomee | zolile@pamun.gov.za / thys@pamun.gov.za | 2026-02-01 | 2030-06-01 | The project is about accessability and transportation of goods | 2025-11-01
12 | Prince Albert Municipality | Central Karoo | Upgarding of Leeu Gamka water canal for irrigation | DARDAL | Prince Albert | 120000000 | The water channel that is currently inplace it’s a normal channel and not concrete. There is a need to upgrade it for better management | No funding has been committed | Department of Agriculture might be the best department to fund the project. | Department of Agriculture | Community Services and Town Planning | Ms Gwynnefer and Vele | gwynnefer@pamun.gov.za / mvele@pamun.gov.za | 2026-02-01 | 2030-06-01 | The project is about saving water and also to cover most of the farmers that are located at the down stream of the canal. | 2025-11-01

## LG Stellenbosch
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Source Document | Readiness Stage | Status / Progress | Key Blockages / Constraints | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance Required | Last Update Date
1 | Stellenbosch | Cape Winelands | Upgrade of IdasValley WTP | Community Development | WC024 | 35782609 | IUDG | CEF |  |  | Heritage Western Cape | Sector Department (HWC) | Community Development
2 | Stellenbosch | Cape Winelands | Construction of New Dwarsriver Sewer Pumpstation. | Community Development | WC024 | 13717391 | CRR (Own funds) | CEF |  |  | Heritage Western Cape | Sector Department (HWC) | Community Development
3 | Stellenbosch | Cape Winelands | Upgrade of Dwarsriver Bulk Sewer network and pump lines | Community Services: Library Services | Ward 17 | 450000 | CRR (Own funds) | CEF |  |  | Funding |  | Community Services: Library Services
4 | Stellenbosch | Cape Winelands | Upgrade/Relocation of Stellenbosch Package Plants to Onderpapegaaiberg Reservoir/Treatment site | Sports Grounds and Picnic Sites | WC024 | 35700000 | CRR (Own funds) | CEF |  |  | Funding | Additional Funding - DEADP: RSEP | Sports Grounds and Picnic Sites
5 | Stellenbosch | Cape Winelands | New Onderpapegaaiberg Reservoir | Sports Grounds and Picnic Sites | WC024 | 0 | DevSport | CEF |  |  | Funding | Additional Funding - DEADP: RSEP | Sports Grounds and Picnic Sites
6 | Stellenbosch | Cape Winelands | Adam Tas Road Intersection Upgrades | Cemeteries | Ward 18 | 29536522 | CRR (Own funds) | CEF |  |  | ESKOM approval | ESKOM approval | Cemeteries
7 | Stellenbosch | Cape Winelands | Bridge Assessment and Design - Lacotte River Flood Resilieance | Cemeteries | Ward 18 | 32153478 | IUDG | CEF |  |  | ESKOM approval | ESKOM approval | Cemeteries
8 | Stellenbosch | Cape Winelands | Bridge Assessment and Design - Stiebeuel River Pedestrian Bridges | Fire and Rescue Services | WC024 | 28000000 | CRR (Own funds) | CEF |  |  | Additional Funding request | Additional Funding request | Fire and Rescue Services
9 | Stellenbosch | Cape Winelands | Bridge Assessment and Design Stellenbosch and surrounding | Fire and Rescue Services | Ward 21 | 24476675 | CRR (Own funds) | CEF |  |  | Additional Funding request | Additional Funding request | Fire and Rescue Services
10 | Stellenbosch | Cape Winelands | River Rehabilitation Implementation | Fire and Rescue Services | WC024 | 4000000 | CRR (Own funds) | CEF |  |  | Additional Funding request | Additional Funding request | Fire and Rescue Services
11 | Stellenbosch | Cape Winelands | Upgrade Stormwater System | Fire and Rescue Services | WC024 | 3000000 | CRR (Own funds) | CEF |  |  | Additional Funding request | Additional Funding request | Fire and Rescue Services
12 | Stellenbosch | Cape Winelands | Upgrade: Lower Dorp Street | Disaster Management | WC024 | 2000000 | CRR (Own funds) | CEF |  |  | Additional Funding request | Additional Funding request | Disaster Management
13 | Stellenbosch | Cape Winelands | Bird Street Dualling - Adam Tas to Kayamandi | Waste Management: Solid Waste Management | WC024 | 37000000 | External Loan | CEF |  |  | DEA&DP; ESKOM; FUNDING | SECTOR & FUNDING | Waste Management: Solid Waste Management
14 | Stellenbosch | Cape Winelands | Jamestown Transport Network - School Street | Waste Management: Solid Waste Management | WC024 | 20500000 | External Loan | CEF |  |  | DEA&DP; ESKOM; FUNDING | FUNDING | Waste Management: Solid Waste Management
15 | Stellenbosch | Cape Winelands | Adam Tas - Corridor Transport | Waste Management: Solid Waste Management | WC024 | 0 | CRR (Own funds) | CEF |  |  | Funding | FUNDING | Waste Management: Solid Waste Management
16 | Stellenbosch | Cape Winelands | Adam Tas - Technopark Link Road | Waste Management: Solid Waste Management | Ward 1 | 6000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR (DEA&DP) & FUNDING | Waste Management: Solid Waste Management
17 | Stellenbosch | Cape Winelands | Comprehensive Integrated Transport Plan | Waste Management: Solid Waste Management | Ward 18 | 9141917 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR (DEA&DP) & FUNDING | Waste Management: Solid Waste Management
18 | Stellenbosch | Cape Winelands | Cycle Plan - Design & Implementation | Waste Management: Solid Waste Management | Ward 18 | 0 | DC - Refuse | CEF |  |  | SECTOR & FUNDING | SECTOR (DEA&DP) & FUNDING | Waste Management: Solid Waste Management
19 | Stellenbosch | Cape Winelands | Non-Motorised Transport Implementation | Waste Management: Solid Waste Management | WC024 | 700000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR (DEA&DP) & FUNDING | Waste Management: Solid Waste Management
20 | Stellenbosch | Cape Winelands | Non-Motorised Transport Plan | Waste Management: Solid Waste Management | WC024 | 600000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR (DEA&DP) & FUNDING | Waste Management: Solid Waste Management
21 | Stellenbosch | Cape Winelands | Park and Ride (Transport Interchange) | Waste Management: Solid Waste Management | WC024 | 5800000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR (DEA&DP) & FUNDING | Waste Management: Solid Waste Management
22 | Stellenbosch | Cape Winelands | Pedestrian Streets in Stellenbosch | Waste Management: Solid Waste Management | WC024 | 3500000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR (DEA&DP) & FUNDING | Waste Management: Solid Waste Management
23 | Stellenbosch | Cape Winelands | Public Transport Facilities (Taxi Ranks) Adhoc Upgrades | Electrical Services | WC024 | 520000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
24 | Stellenbosch | Cape Winelands | Public Transport Facilities (taxi ranks) new | Electrical Services | WC024 | 8000000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
25 | Stellenbosch | Cape Winelands | Public Transport Infrastructure ( Public Transport Shelters & Embayments) | Electrical Services | Ward 3 | 139957757 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR (HWC) & FUNDING | Electrical Services
26 | Stellenbosch | Cape Winelands | Re-design of Bergzicht Public Transport Facility | Electrical Services | Ward 3 | 0 | DC - Electricity | CEF |  |  | SECTOR & FUNDING | SECTOR (HWC) & FUNDING | Electrical Services
27 | Stellenbosch | Cape Winelands | Stellenbosch - Bicycle network | Electrical Services | Ward 1 | 5000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
28 | Stellenbosch | Cape Winelands | Stellenbosch Extention Road Network | Electrical Services | WC024 | 31836500 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
29 | Stellenbosch | Cape Winelands | Koelenhof Road Network | Electrical Services | Ward 4 | 34517618.8 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
30 | Stellenbosch | Cape Winelands | Erf 64, Kylemore | Electrical Services | WC024 | 12400000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
31 | Stellenbosch | Cape Winelands | Erf 7001 Cloetesville (380) FLISP | Electrical Services | WC024 | 89500000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
32 | Stellenbosch | Cape Winelands | ISSP Kayamandi | Electrical Services | WC024 | 48720297.2092 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
33 | Stellenbosch | Cape Winelands | Franschhoek Meerlust: Bosdorp (±200 services & ±200 units) | Electrical Services | WC024 | 2500000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
34 | Stellenbosch | Cape Winelands | Jamestown: Housing (Phase 2 & 3) | Electrical Services | WC024 | 735554914.5358 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
35 | Stellenbosch | Cape Winelands | Jamestown: Housing (Phase 4) | Electrical Services | Ward 5 | 0 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
36 | Stellenbosch | Cape Winelands | Kayamandi Town Centre | Electrical Services | Ward 2 | 0 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
37 | Stellenbosch | Cape Winelands | Adam Tas Corridor Precinct 10 | Electrical Services | Ward 9 | 0 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
38 | Stellenbosch | Cape Winelands | Klapmuts La Rochelle (100) | Electrical Services | Ward 16 | 0 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
39 | Stellenbosch | Cape Winelands | Klapmuts La Rochelle (100) | Electrical Services | Ward 11 | 3500000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
40 | Stellenbosch | Cape Winelands | La Motte Old Forest Station (±430 services & ±430 units) | Electrical Services | Ward 7 | 3500000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
41 | Stellenbosch | Cape Winelands | Rehabilitation of Langrug Dam and Engineering Services | Electrical Services | WC024 | 3500000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
42 | Stellenbosch | Cape Winelands | Rehabilitation of Langrug Dam and Engineering Services | Electrical Services | Ward 21 | 3500000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
43 | Stellenbosch | Cape Winelands | Restoration of Landbou Saal | Electrical Services | WC024 | 4500000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
44 | Stellenbosch | Cape Winelands | Upgrade of Op die Berg WwTW (from 0.3ML to 2ML) | Electrical Services | WC024 | 4500000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
45 | Stellenbosch | Cape Winelands | Upgrade of WwTWs | Electrical Services | WC024 | 20000000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
46 | Stellenbosch | Cape Winelands | Upgrading of Prince Alfred Hamlet Chlorine building and system | Electrical Services | WC024 | 4500000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
47 | Stellenbosch | Cape Winelands | Wolseley: Refurbishment of WwTW (3 Phases) | Electrical Services | WC024 | 4500000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
48 | Stellenbosch | Cape Winelands |  | Electrical Services | WC024 | 8816990 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
49 | Stellenbosch | Cape Winelands | Develop Groundwater Monitoring and Management Plans | Electrical Services | WC024 | 0 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
50 | Stellenbosch | Cape Winelands | Op-die-Berg: Water allocation to Op-die-Berg needs to be increased | Electrical Services | WC024 | 13644652 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
51 | Stellenbosch | Cape Winelands | Telemetry and Scada monitoring for all Sewer Pump Stations | Electrical Services | WC024 | 12451895 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
52 | Stellenbosch | Cape Winelands | Telemetry and Scada monitoring for all Water Pump Stations | Electrical Services | WC024 | 13644651 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
53 | Stellenbosch | Cape Winelands | Telemetry and Scada monitoring for all Water Treatment Works | Electrical Services | WC024 | 13644651 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
54 | Stellenbosch | Cape Winelands | AC pipe replacement at Ceres, Prince Alfred Hamlet and Wolseley | Electrical Services | WC024 | 18641342.2236 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
55 | Stellenbosch | Cape Winelands | Network, Water pipes and valve replacement: | Electrical Services | Ward 11 | 60629447.4275 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
56 | Stellenbosch | Cape Winelands | Sewer Network Replacement for all the towns | Electrical Services | WC024 | 72571200 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Electrical Services
57 | Stellenbosch | Cape Winelands | Sewer Pumps Replacement | Project Management Unit (PMU) | Ward 15 | 0 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Project Management Unit (PMU)
58 | Stellenbosch | Cape Winelands | Toilets for Informal Settlements | Project Management Unit (PMU) | Ward 15 | 22630261 | ISUP | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Project Management Unit (PMU)
59 | Stellenbosch | Cape Winelands |  | Project Management Unit (PMU) | Ward 15 | 0 | Human Settlements Grant | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Project Management Unit (PMU)
60 | Stellenbosch | Cape Winelands | Develop and Implement Revenue Enhancement Strategy | Project Management Unit (PMU) | Ward 15 | 3221740 | INEP | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Project Management Unit (PMU)
61 | Stellenbosch | Cape Winelands | Develop and Implement Skills Development Policy (posts are filled, sufficient technical & support staff, training provided, reuired skills / qualifications, appropriate number of staff, etc. | Water and Wastewater Services: Water | Ward 13 | 40281936 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Water
62 | Stellenbosch | Cape Winelands | Establish processes and systems to manage water and sanitation services on farms and in rural areas (ensure SLAs are in place with farmers or Irrigation Boards) | Water and Wastewater Services: Water | Ward 13 | 2608696 | IUDG | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Water
63 | Stellenbosch | Cape Winelands | Improve Blue Drop status and obtain Blue Drop certification (annual WTW Process Audits) | Water and Wastewater Services: Water | Ward 6 | 24000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Water
64 | Stellenbosch | Cape Winelands | Improve Green Drop status and obtain Green Drop certification (annual WwTW Process Audits) | Water and Wastewater Services: Water | WC024 | 13000000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Water
65 | Stellenbosch | Cape Winelands | Review and implement a comprehensive WCDM (with WCDM interventions) Plan & Strategy and update Strategy when necessary | Water and Wastewater Services: Water | WC024 | 244250000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Water
66 | Stellenbosch | Cape Winelands | Review and Implement a Water Resilience Policy to improve water use efficiency | Water and Wastewater Services: Water | WC024 | 24000000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Water
67 | Stellenbosch | Cape Winelands | Review and implement Information Management Systems Plan that addresses IT business rewquirements, ensure adequate IT security exists with back-ups and sufficient staff and budget isavailable to keep IT Systems stable. | Water and Wastewater Services: Water | WC024 | 145000000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Water
68 | Stellenbosch | Cape Winelands | Review and implement O&M Plans to improve the functional life of infrastructure - (operating manuals, maintenance schedules, tools, equipment, staff and funds). | Water and Wastewater Services: Water | WC024 | 235000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Water
69 | Stellenbosch | Cape Winelands | Review and implement Water Safety Plans and review Plans when necessary | Water and Wastewater Services: Sanitation | Ward 11 | 48000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
70 | Stellenbosch | Cape Winelands | Review and update implementation of AC Pipe Replacement Programme | Water and Wastewater Services: Sanitation | Ward 11 | 158450000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
71 | Stellenbosch | Cape Winelands | Review and update Infrastructure Asset Management Strategies and Plans and Asset Register (inclusive of technical water and sanitation asset register) | Water and Wastewater Services: Sanitation | WC024 | 15350000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
72 | Stellenbosch | Cape Winelands | Review and update Sanitation Master Plan | Water and Wastewater Services: Sanitation | WC024 | 9000000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
73 | Stellenbosch | Cape Winelands | Review and update Wastewater Risk Abatement Plans (W2RAP) | Water and Wastewater Services: Sanitation | WC024 | 163000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
74 | Stellenbosch | Cape Winelands | Review and update Water Master Plan | Water and Wastewater Services: Sanitation | WC024 | 0 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
75 | Stellenbosch | Cape Winelands | Review and update Water Services Infrastructure Maintenance and Rehabilitation Programme (Technical assessment of infrastructure) | Water and Wastewater Services: Sanitation | Ward 1 | 70000000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
76 | Stellenbosch | Cape Winelands | Review Indigent Policy and update Indigent Register annually | Water and Wastewater Services: Sanitation | Ward 3 | 15000000 | IUDG | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
77 | Stellenbosch | Cape Winelands | Review WSDP annually and update document every 5 years (2023 - 2028) | Water and Wastewater Services: Sanitation | Ward 18 | 80000000 | External Loan | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
78 | Stellenbosch | Cape Winelands | Section 78: Investigate the process to be followed and deciding on an appropriate delivery mechanism to provide a municipal service within the Municipality - internal (in-house) or external (outsourced) delivery option (Review WSP arrangements) | Water and Wastewater Services: Sanitation | Ward 18 | 26324217 | IUDG | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
79 | Stellenbosch | Cape Winelands |  | Water and Wastewater Services: Sanitation | Ward 18 | 3948633 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
80 | Stellenbosch | Cape Winelands |  | Water and Wastewater Services: Water | Stellenbosch, Idasvalley, Kayamandi, Vlottenburg | 15535217 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Water
81 | Stellenbosch | Cape Winelands | Water Master Plan June 2021 (Table WBW6.4b) | Water and Wastewater Services: Water | Stellenbosch, Idasvalley, Kayamandi, Vlottenburg | 35964783 | IUDG | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Water
82 | Stellenbosch | Cape Winelands | Ceres | Water and Wastewater Services: Sanitation | Pniel, Lanquedoc, Johannesdal | 37000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
83 | Stellenbosch | Cape Winelands | Reinforcement to Main Supply zone (Groenplaatjie to Plantasie Street) | Water and Wastewater Services: Sanitation | Pniel, Lanquedoc, Johannesdal | 12000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
84 | Stellenbosch | Cape Winelands | Reinforcements to Bella Vista network | Water and Wastewater Services: Sanitation | Stellenbosch, Idasvalley, Kayamandi, Vlottenburg | 20500000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Sanitation
85 | Stellenbosch | Cape Winelands | Supply to new development areas | Water and Wastewater Services: Water | Stellenbosch, Idasvalley, Kayamandi, Vlottenburg | 40750000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Water and Wastewater Services: Water
86 | Stellenbosch | Cape Winelands | Ceres water demand management: Implement Ceres PRV 2 zone | Roads and Stormwater | Ward 11 | 10000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Roads and Stormwater
87 | Stellenbosch | Cape Winelands | Ceres pipe replacement & network reinforcement | Roads and Stormwater | Ward 3 | 28000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Roads and Stormwater
88 | Stellenbosch | Cape Winelands | Ceres water demand management: Implement Ceres PRV 1 b zone | Roads and Stormwater | Ward 3 | 3700000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Roads and Stormwater
89 | Stellenbosch | Cape Winelands | Ceres water demand management: Implement Ceres PRV 3 zone | Roads and Stormwater | Ward 2,3 | 8000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Roads and Stormwater
90 | Stellenbosch | Cape Winelands | Nduli booster PS upgrade | Roads and Stormwater | WC024 | 7500000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Roads and Stormwater
91 | Stellenbosch | Cape Winelands | New Bella Vista booster pumping station | Roads and Stormwater | WC024 | 4300000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Roads and Stormwater
92 | Stellenbosch | Cape Winelands | Additional storage capacity for Ceres (Can be phased) | Roads and Stormwater | Ward 11 | 8000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Roads and Stormwater
93 | Stellenbosch | Cape Winelands | Additional reservoir storage for Bella Vista | Traffic Engineering | WC024 | 305000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Traffic Engineering
94 | Stellenbosch | Cape Winelands | Upgrade of bulk supply to Bella Vista | Traffic Engineering | Ward 21 | 16000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Traffic Engineering
95 | Stellenbosch | Cape Winelands | Upgrade of bulk supply to Nduli | Transport Planning | Ward 11 | 3100000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
96 | Stellenbosch | Cape Winelands | Reinforcement to Main Supply zone (R303 Road to R46 Road) | Transport Planning | WC024 | 158998047 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
97 | Stellenbosch | Cape Winelands | Additional reservoir storage for Nduli | Transport Planning | WC024 | 1166957 | ITP | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
98 | Stellenbosch | Cape Winelands | Telemetry | Transport Planning | WC024 | 5000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
99 | Stellenbosch | Cape Winelands | Tulbagh | Transport Planning | WC024 | 37000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
100 | Stellenbosch | Cape Winelands | Development related items for Tulbagh Upper reservoir zone | Transport Planning | WC024 | 5000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
101 | Stellenbosch | Cape Winelands | Network upgrades for Tulbagh Lower reservoir zone | Transport Planning | WC024 | 21000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
102 | Stellenbosch | Cape Winelands | Development related items for Tulbagh Lower reservoir zone | Transport Planning | WC024 | 0 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
103 | Stellenbosch | Cape Winelands | Network upgrades when FDA TB18 develops | Transport Planning | Ward 1 | 4000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
104 | Stellenbosch | Cape Winelands | Rezoning and network upgrades for Tulbagh Upper reservoir zone (After project WTW-B01 is implemented) | Transport Planning |  | 4000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
105 | Stellenbosch | Cape Winelands | New Tulbagh Upper reservoir, pumping station & supply pipes | Transport Planning | WC024 | 4100000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
106 | Stellenbosch | Cape Winelands | New Tulbagh Very High reservoir, PS & supply pipes | Transport Planning | WC024 | 5000000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
107 | Stellenbosch | Cape Winelands | Additional storage capacity for Tulbagh Lower reservoir zone and supply pipes | Transport Planning | WC024 | 500000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
108 | Stellenbosch | Cape Winelands | Telemetry | Transport Planning | Ward 12 | 1500000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
109 | Stellenbosch | Cape Winelands | Water Treatment Works | Transport Planning | Ward 19 | 0 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Transport Planning
110 | Stellenbosch | Cape Winelands | Prince Alfred Hamlet | Housing Development | Ward 4 | 70400000 | Human Settlements Grant | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Housing Development
111 | Stellenbosch | Cape Winelands | Implement PAH Upper reservoir zone (After project WPW-B01 is implemented) | Housing Development | Ward 17 | 16000000 | Human Settlements Grant | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Housing Development
112 | Stellenbosch | Cape Winelands | Reinforce network of the PAH Upper reservoir zone | Housing Development | Ward 12 | 2000000 | ISUP | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Housing Development
113 | Stellenbosch | Cape Winelands | Reinforce network of the PAH Lower reservoir zone | Housing Development | Ward 1 | 27800000 | Human Settlements Grant | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Housing Development
114 | Stellenbosch | Cape Winelands | Supply to developments in PAH Upper reservoir zone | Housing Development | Ward 21 | 93640000 | Human Settlements Grant | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Housing Development
115 | Stellenbosch | Cape Winelands | Supply to developments in PAH Lower reservoir zone | Housing Development |  | 190400000 | Human Settlements Grant | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Housing Development
116 | Stellenbosch | Cape Winelands | New PAH Upper reservoir, pumping station & supply pipe | Housing Development | Ward 13 | 0 | ISUP | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Housing Development
117 | Stellenbosch | Cape Winelands | Telemetry | Housing Development | Ward 12 | 298860000 | Human Settlements Grant | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Housing Development
118 | Stellenbosch | Cape Winelands | Op-Die_Berg | Housing Development | Ward 18 | 0 | ISUP | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Housing Development
119 | Stellenbosch | Cape Winelands | Reinforce existing ODB water network | Housing Development | Ward 18 | 0 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Housing Development
120 | Stellenbosch | Cape Winelands | Additional reservoir storage for Fontein zone | Housing Development | Ward 2 | 210000000 | Human Settlements Grant | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | Housing Development
121 | Stellenbosch | Cape Winelands | Additional reservoir storage for Odendaal zone | IHS: Informal Settlements | Ward 2 | 0 | ISUP | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | IHS: Informal Settlements
122 | Stellenbosch | Cape Winelands | Telemetry | IHS: Informal Settlements | Ward 2 | 10300000 | CRR (Own funds) | CEF |  |  | SECTOR & FUNDING | SECTOR & FUNDING | IHS: Informal Settlements
123 | Stellenbosch | Cape Winelands | Wolseley | Economic Development & Tourism | Admin HQ | 2150000 | CRR (Own funds) | CEF |  |  | SECTOR (HWC) | SECTOR (HWC) | Economic Development & Tourism
124 | Stellenbosch | Cape Winelands | Emergency Housing |  |  |  | CRR (Own funds) |  |  |  | SECTOR & FUNDING | SECTOR & FUNDING | IHS: Informal Settlements

## LG Saldanha Bay
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assitance Required | Last Update Date
1 | Saldanha Bay Municipality | West Coast | Bulk Water Supply Line to St Helena Bay | Water | St Helena Bay | 160000000 | Internal / Capital |  | In process of appointing the Consulting Engineer to start with preliminary designs | Planning: Consulting engineer appointment | Bulk supply constraints due to rapid development | Immediate | N/A | Infrastructure and Planning Servces | G Williams | Construction Start date July 2027 | 2028-12-01 | Delays in the appointment of the Consulting Engineer. We require clarity from National Treasury regarding the implimentation of Circular 44 | Yes
2 | Saldanha Bay Municipality | West Coast | WWTW Sludge Handling Upgrades | Sanitation | Multiple WWTWs | 80000000 | Municipal Capital |  | Implimentation ready with first WWTW | Planned upgrades | Sludge disposal challenges at plants | Immediate | N/A | Infrastructure and Planning Servces | G Williams | Construction to start Jan 2027 | 2030-06-01 | Mechanical dewatering installations to start at Saldanha WWTW as the first project. Vredenburg WWTW and other plants to follow | No
3 | Saldanha Bay Municipality | West Coast | Pump Station Vandalism Mitigation Programme | Water & Sanitation | Municipal wide |  | Municipal O&M |  |  | Ongoing | High vandalism at pump stations and boreholes
4 | Saldanha Bay Municipality | West Coast | Middelpos & Saldanha Site A Serviced Sites | Human Settlements | Saldanha | 128783000 | HS Grants | IDP, HSP | Procurement | Tenders advertised in April 2026 | Project is linked to a relocation area that is currently in feasbility study phase | Short | DEADP | Human Settlements/PMU | L Khuselo | Project commenced | 2029/30 | None | None
5 | Saldanha Bay Municipality | West Coast | Louwville South Erf 123/69 Development | Human Settlements | Louwville | 163000000 | Human Settlements | IDP, HSP | Feasibility study | EIA & LUPA stage | Planning approvals | Medium | None | Human Settlements/PMU | L Khuselo | Project commenced | 2030/31 | None
6 | Saldanha Bay Municipality | West Coast | Urban Revit Project | Urban Development | Municipal area | 45452256 | Human Settlements | IDP, HSP | Feasibility study | Planning | Environmental requirements - biodiversity offset | Immediate | DEAP | Human Settlements/PMU | L Khuselo | Project commenced | 2030/31
7 | Saldanha Bay Municipality | West Coast | Municipal Takeover of Eskom Electrical Networks | Energy | Eskom supply areas | 25000000 | Strategic Programme |  | Concept/Problem definition | Strategic planning | Network reliability and service standard |  | Nersa/ Eskom | EETS | Cassie du Preez | TBC | TBC | SALGA points out that electricity reticulation is explicitly assigned to municipalities in Schedules 4B and 5B of the Constitution and that any deviation from this responsibility must comply with the Municipal Systems Act.
8 | Saldanha Bay Municipality | West Coast | Water Augmentation & Re‑Use Programme | Water | Municipal wide |  | PPP / Capital |  |  | Concept stage | Future water demand and drought risk

## LG Swartland
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assitance Required | Last Update Date
1 | Swartland Municipality | West Coast | Dalsig Urban Restructuring Zone Bulk Services (Bokomo/Voortrekker Upgrade) | Roads & Stormwater | Dalsig | 100000000 | DHS/DOI | Detailed Design | Submitted to DOI CD Design Branch for Approval of Detailed design. | Sourcing Funds from DOI /DHS | Medium Term | DOI/DHS: Funding needed | Civil Engineering Services | Jonhilll Spies | 2028/2029 | 2030/2031 | Project forms part of Swartland Municipality's Housing Pipeline, for the development of FLISP and Socia Housing Opportunities | Acquiring funding from DOI
2 | Swartland Municipality | West Coast | Dalsig Urban Restructuring Zone Wesbank/Abbotsdale Bulk Water Pipeline (355mm HDPE) | Sanitation | Malmesbury Industrial | 21000000 | CRR/MIG | Detailed Design | Detail design complete. Currently compiling tender documents | N/A | Short Term | N/A | Civil Engineering Services | Esias De Jager | 2026-07-01 | 2028-06-30 | N/A | N/A
3 | Swartland Municipality | West Coast | Klipfontein Development Voortrekker/Piketberg Bulk Upgrade | Roads & Stormwater | Tafelzicht | 25000000 | CRR | Inception | Project is currently in Stage 1 | Approval of Upgrade by DOI CD: Design Branch | Medium Term | N/A | Civil Engineering Services | Jonhilll Spies | 2027/2028 | 2029/2030 | N/A | N/A
4 | Swartland Municipality | West Coast | Darling Road Dualling & intersection Upgrades | Roads & Stormwater | Rural Areas | 15000000 | TBC | Inception | Project is currently in Stage 1 | 1. Sourcing Funds from DOI /DHS. 2. Approval of Upgrade by DOI CD: Design Branch | Medium Term | DOI/DHS: Funding needed | Civil Engineering Services | Jonhilll Spies | 2028/2029 | 2030/2031 | Project forms part of the external Services of the De Hoop Development | Acquiring funding from DOI/DHS
5 | Swartland Municipality | West Coast | Darling WWTW Upgrade Programme (2025–2032) | Sanitation | Darling | 92000000 | CRR/MIG | Inception | Project is currently in Stage 1 | 1. Environmental Approval. 2. MIG registration | Medium Term | N/A | Civil Engineering Services | Esias De Jager | 2025/2026 | 2030/2031 | N/A | N/A
6 | Swartland Municipality | West Coast | Swartland Bulk Water System Reservoir Upgrade & 7.5km Pipeline | Water Services | Riebeek Valley | 85000000 | CRR/MIG | Inception | Project is currently in Stage 1-2 | TBC | Short Term | N/A | Civil Engineering Services | Esias De Jager | 2026/2027 | 2029/2030 | N/A | N/A
14 | Swartland Municipality | West Coast | Chatsworth Bulk Water Supply | Water Services | Chatsworth | 35841000 | CRR/MIG | Inception | Inception/Feasbility | Apporval from COCT to Connect to Pella Reservoirs | Short Term | Assistance to obtain approval from COCT to connect ot Pella Reservoirs | Civil Engineering Services | Esias De Jager | 2026/2027 | 2029/2023 | Cant commence with Section 33 process until apporval from COCT has been obtained. | Assistance to obtain approval from COCT to connect ot Pella Reservoirs
7 | Swartland Municipality | West Coast | Chatsworth/Riverlands Bulk Water Supply Pipeline (Pella Reservoir Link) | Water Services | Chatsworth |  |  | Concept/Problem definition |  |  |  |  | Civil Engineering Services | Esias De Jager
9 | Swartland Municipality | West Coast | Swartland Bulk Water Supply Programme (WTP Upgrades & Regional Conveyance) | Water Services | Regional Bulk System | 178652400 | CRR/MIG | Masterplan / Planning Stage | Inception | TBC | Long Term | TBC | Civil Engineering Services | Esias De Jager | 2025/2026 | 2031/2032
10 | Swartland Municipality | West Coast | Swartland WTP to Kasteelberg Bulk Pipeline | Water Services | Regional | 84000000 | CRR/MIG | Masterplan / Planning Stage | Inception | TBC | Long Term | TBC | Civil Engineering Services | Esias De Jager | 2025/2026 | 2031/2032
11 | Swartland Municipality | West Coast | Kasteelberg to Riebeek Valley Bulk Water Supply | Water Services | Riebeek Valley | 26437000 | CRR/MIG | Masterplan / Planning Stage | Inception | TBC | Long Term | TBC | Civil Engineering Services | Esias De Jager | 2025/2026 | 2031/2032
12 | Swartland Municipality | West Coast | Kasteelberg to Glen Lily Bulk Water Corridor | Water Services | Regional | 125000000 | CRR/MIG | Masterplan / Planning Stage | Inception | TBC | Long Term | TBC | Civil Engineering Services | Esias De Jager | 2025/2026 | 2031/2032
13 | Swartland Municipality | West Coast | Glen Lily to Darling & Yzerfontein Bulk Water Supply | Water Services | Darling / Yzerfontein | 249640000 | CRR/MIG | Masterplan / Planning Stage | Masterplan | TBC | Long Term | TBC | Civil Engineering Services | Esias De Jager | 2031/2032 | 2034/2035
15 | Swartland Municipality | West Coast | Swartland Water Distribution Network Renewal | Water Services | Municipal Wide | 92008300 | CRR/MIG | Masterplan / Planning Stage | Masterplan | TBC | Long Term | TBC | Civil Engineering Services | Esias De Jager | 2026/2027 | 2034/2035

## LG Swellendam
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Funding Source | Document Source | Readiness Stage | Status / Progress | Key Blockages / Constraints | Priority | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assitance Required | Last Update Date
1 | Swellendam Municipality | Overberg District | Eskom link, new transmission substation to Vryheid Substation | Energy/Electricity | Overberg District |  | Eskom |  |  |  | Eskom has voltage problems in this area and cannot award any more capacity to municipalities. Both Swellendam and Cape Agulhas municipalities are severely constrained. Development in the area is being blocked as electricity capacity is exhausted. Until Eskom installs new power lines, municipalities in the Overberg District cannot expand their business or approve new development. | High |  | Eskom | W. Treurnicht S. Herbst J. Bester |  |  | Construction of a new Eskom high-voltage transmission lines connecting the Overberg region to the national grid at adequate capacity. The lines are needed to unlock capacity in the region. | Yes | 2026-05-12
2 | Swellendam Municipality | Overberg District | Upgrade Waste Water Treatment Works: Barrydale | Sanitation | Barrydale | 24945000 | MIG | Swellendam Project Pipeline | Detail design | Construction to start in new FY |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2025/26 | 2029 | Upgrade and expansion of the Barrydale Waste Water Treatment Works to increase treatment capacity and bring the facility in line with current Green Drop regulatory requirements. Funded through MIG. This entry reflects the MIG portion of the project budget. ¦ The existing WwTW in Barrydale is operating at or beyond capacity. Without upgrading the treatment works, new residential and commercial development in Barrydale cannot be approved as there is insufficient wastewater treatment capacity. The upgrade is essential to unlock growth and ensure environmental compliance. | No | 2026-05-12
3 | Swellendam Municipality | Overberg District | Upgrade Waste Water Treatment Works: Barrydale | Sanitation | Barrydale | 5280800 | CRR | Swellendam Project Pipeline | Detail design | Construction to start in new FY |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2025/26 | 2029 | Upgrade and expansion of the Barrydale Waste Water Treatment Works — CRR (own-funding) portion of the project, complementing the MIG-funded component. ¦ As above: the Barrydale WwTW upgrade is a prerequisite for any new development in Barrydale. The CRR funding component ensures the municipality can bridge funding gaps and complete the full scope of works. | No | 2026-05-12
4 | Swellendam Municipality | Overberg District | Upgrade Of Barrydale Water Pipeline from Water Treatment Works to Reservoir | Water | Barrydale | 7000000 | CRR | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2030/31 | 2035 | Replacement and upgrading of the bulk water pipeline from the Barrydale Water Treatment Works to the main reservoir, improving flow capacity and reliability of water supply to the town. ¦ The existing pipeline is aged and undersized relative to current and future demand. Failure of this pipeline would cut water supply to Barrydale entirely. Upgrading it is necessary to support population growth and any new development in the town. | Yes | 2026-05-12
5 | Swellendam Municipality | Overberg District | Upgrade Of Barydale Bulk Sewer Line to Waste Water Treatment Works | Sanitation | Swellendam Municipality | 8000000 | CRR | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2028/29 | 2030 | Upgrading of the bulk sewer main from Barrydale to the Waste Water Treatment Works, increasing conveyance capacity to accommodate current loads and future growth. ¦ The bulk sewer line is a critical link in the sanitation chain. An undersized or failing bulk sewer line limits how much wastewater can be conveyed to the treatment works, effectively capping development. This upgrade is required to support the WwTW upgrade and unlock new connections. | Yes | 2026-05-12
6 | Swellendam Municipality | Overberg District | Second Phase of Barrydale Water Treatment Works Upgrade | Water | Barrydale | 26000000 | WSIG | Swellendam Project Pipeline | In construction | In construction |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2025/26 | 2026 | Second phase of the Barrydale Water Treatment Works upgrade, increasing potable water production capacity to meet current demand and support future growth in Barrydale and surrounding areas. ¦ Barrydale's water treatment capacity is constrained. Without increased treatment capacity, the municipality cannot supply potable water to new consumers. This upgrade is a prerequisite for lifting the development moratorium on water connections in Barrydale. | No | 2026-05-12
7 | Swellendam Municipality | Overberg District | New Reservoir Barrydale | Water | Barrydale | 10000000 | WSIG | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2029/30 | 2035 | Construction of a new bulk water storage reservoir in Barrydale to increase the town's storage capacity and improve supply security, particularly during peak demand periods and emergency situations. ¦ Adequate reservoir storage is essential to buffer supply interruptions and meet peak demand. The current storage capacity is insufficient for the existing population and cannot accommodate growth. A new reservoir will improve service reliability and support new development approvals. | Yes | 2026-05-12
8 | Swellendam Municipality | Overberg District | Upgrade Sewer Network Barrydale to Water Born Network (Current Septic System) | Sanitation | Barrydale | 45000000 | CRR | Swellendam Project Pipeline | Concept/Problem definition |  |  |  |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2035/36 | 2040 | Conversion of Barrydale's existing septic tank sanitation system to a waterborne sewerage network, including laying of new sewer reticulation and connections to all properties currently on septic tanks. ¦ The current septic tank system in Barrydale is inadequate for an urban environment and poses long-term public health and groundwater contamination risks. A waterborne system is the accepted standard for urban sanitation, will improve environmental compliance and significantly improve living conditions for residents. | Yes | 2026-05-12
9 | Swellendam Municipality | Overberg District | Upgrading of Roads in The Industrial Area Swellendam | Roads & Stormwater | Swellendam | 27000000 | other | Swellendam Project Pipeline | Planning |  |  | High |  | Engineering Services – Roads & Stormwater | W. Treurnicht B. Burger J. Bester | 2025/26 | 2027 | Upgrading and rehabilitation of roads in the Swellendam industrial area, including stormwater improvements, surfacing and road structure upgrades. This entry covers the primary civil works contract (R27 million). ¦ The industrial area is the economic engine of Swellendam. Poor road conditions limit the movement of heavy goods vehicles, increase transport costs for businesses, and deter new investment. Upgraded industrial roads will improve logistics, attract new business, and support job creation. Department or agriculture showed promise to fund the project but exited after long negotiations which ended up without a positive outcome. | Yes | 2026-05-12
10 | Swellendam Municipality | Overberg District | Upgrading Of Roads in The Industrial Area Swellendam | Roads & Stormwater | Swellendam | 3000000 | other | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Roads & Stormwater | W. Treurnicht B. Burger J. Bester | 2025/26 | 2027 | Upgrading of roads in the Swellendam industrial area — supplementary works component (R3 million) covering ancillary roadworks, kerbing, and drainage. ¦ As above: this component completes the industrial road upgrade programme. Together with the primary contract, it ensures the full industrial road network is upgraded to a standard that supports heavy industrial traffic and economic activity. | Yes | 2026-05-12
11 | Swellendam Municipality | Overberg District | Upgrade of Bakenskop to Railton Bulk Water Pipeline to Reservoir | Water | Railton | 28695650 | WSIG | Swellendam Project Pipeline | In construction | in construction |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2027 | 2028 | Construction of an upgraded bulk water pipeline from the Bakenskop Reservoir to the Railton distribution network, increasing flow capacity to the Railton residential area and informal settlement. ¦ Railton and the adjacent informal settlement are among the fastest-growing residential areas in Swellendam. The existing pipeline is undersized and cannot deliver sufficient water to meet current demand, let alone accommodate growth. This pipeline is a prerequisite for any new housing development in Railton. | No | 2026-05-12
12 | Swellendam Municipality | Overberg District | Upgrading of Sewer Line from Informal to N2 Pumpstation Railton | Sanitation | Railton | 3000000 | Human Settlements Grant | Swellendam Project Pipeline | Concept/Problem definition |  |  |  |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2028/29 | 2029 | Upgrading of the sewer line from the Railton informal settlement to the N2 pump station, replacing the existing undersized pipe to handle current and future wastewater flows from the settlement. ¦ The informal settlement in Railton is a priority area for housing formalisation and service delivery. The existing sewer line is inadequate and prone to blockages and overflows. Upgrading it is essential to support the formalisation programme and ensure dignified sanitation for residents. | No | 2026-05-12
13 | Swellendam Municipality | Overberg District | Upgrade Pumpstation and Rising Main to Bakenskop Swellendam | Water | Swellendam | 10000000 | CRR | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2027/28 | 2030 | Upgrading of the pump station and rising main that conveys water from the lower supply system to the Bakenskop Reservoir, increasing pumping capacity to meet current and future demand. ¦ The pump station and rising main are critical links in Swellendam's water supply chain. Without adequate pumping capacity, the Bakenskop Reservoir cannot be filled at a rate sufficient to meet peak demand. This upgrade is required to ensure reliable water supply to the upper areas of Swellendam and to support new development. | Yes | 2026-05-12
14 | Swellendam Municipality | Overberg District | Upgrading Of Waste Water Treatment Works - Kliprivier Swellendam' | Sanitation | Swellendam | 40400000 | CRR | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2029/30 | 2035 | Upgrade and expansion of the Kliprivier Waste Water Treatment Works, which serves Swellendam town, to increase treatment capacity . ¦ The Kliprivier WwTW is the primary wastewater treatment facility for Swellendam. It is operating within capacity but will need to be upgraded in the future. | Yes | 2026-05-12
15 | Swellendam Municipality | Overberg District | New Reservoir for Informal and Railton Area | Water | Railton | 15000000 | WSIG | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2030/31 | 2035 | Construction of a new bulk water storage reservoir to serve the Railton residential area and the adjacent informal settlement, improving supply security and enabling new housing connections. ¦ There is currently insufficient reservoir storage capacity to supply Railton and the informal settlement reliably. A new reservoir is essential to support the formalisation of the informal settlement and the delivery of new housing units. Water use will increase drastically with the formalisation of the informal settlement. | Yes | 2026-05-12
16 | Swellendam Municipality | Overberg District | New Reservoir Bakenskop | Water | Swellendam Municipality | 25000000 | Loan | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2030/31 | 2035 | Construction of a new bulk water storage reservoir at Bakenskop to increase total storage capacity for Swellendam town, improve supply security, and support new development in the upper areas of the municipality. ¦ Swellendam's current reservoir capacity is insufficient in this area to meet growing demand, particularly during periods of high consumption or supply interruptions. Additional storage is a prerequisite for approving new developments and ensuring the town's water supply is resilient. | Yes | 2026-05-12
17 | Swellendam Municipality | Overberg District | Upgrade Swellendam Water Treatment Works | Water | Swellendam | 25000000 | Loan | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2035/36 | 2040 | Upgrade and expansion of the Swellendam Water Treatment Works to increase potable water production capacity and achieve full Blue Drop compliance with water quality and operational standards. ¦ The Swellendam WTW produces drinking water for the entire town. Its current capacity is constrained and cannot support significant population or economic growth. Upgrading the treatment works is fundamental to ensuring long-term water security and enabling new development approvals. | Yes | 2026-05-12
18 | Swellendam Municipality | Overberg District | Smart Meters and Control System | Energy/Electricty | Swellendam Municipality | 70000000 | DLG Energy Resilience | Swellendam Project Pipeline | Concept/Problem definition |  |  |  |  | Engineering Services – Electromechanical | W. Treurnicht S. Herbst J. Bester | 2027/28 | 2030 | Installation of a smart metering system across the municipality, including automated meter reading, a real-time monitoring and control platform, and integration with billing systems for all water and electricity consumers. ¦ Smart meters significantly reduce non-revenue water and electricity losses by enabling rapid detection of leaks, theft, and billing errors. They improve revenue collection, reduce operational costs, and provide the data needed for effective demand management — all critical for the financial sustainability of municipal services. | Yes | 2026-05-12
19 | Swellendam Municipality | Overberg District | Upgrade Municipal Feeders from Eskom to Bethal Substation | Energy/Electricty | Swellendam Municipality | 52188000 | Loan | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Electromechanical | W. Treurnicht S. Herbst J. Bester | 2027/28 | 2035 | Upgrading of the municipal electricity distribution feeders between the Eskom supply point and the Bethal substation, increasing capacity and reliability of electricity supply to Swellendam. ¦ The existing feeders are operating close to their rated capacity. Without upgrading them, the municipality cannot increase electricity supply to existing consumers or connect new ones. This upgrade is essential to support economic growth and new development in Swellendam, and works in conjunction with the broader Eskom transmission upgrade (Project 1). | Yes | 2026-05-12
20 | Swellendam Municipality | Overberg District | New Reservoir and Upgrade WTW Buffelsjag | Water | Swellendam Municipality | 25000000 | CRR | Swellendam Project Pipeline | Concept/Problem definition |  |  |  |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2027/2028 | 2029 | Construction of a new bulk water reservoir and upgrade of the Water Treatment Works at Buffelsjagrivier to ensure reliable potable water supply to the community. ¦ Buffelsjagrivier currently has adequate water storage capacity. The existing infrastructure cannot support growth or withstand supply disruptions on the purification side. The upgrade of the water purification works is much needed to ensure reliable water quality. | Yes | 2026-05-12
21 | Swellendam Municipality | Overberg District | New Intake Substation Suurbraak Bulk Electricity | Energy/Electricty | Suurbraak | 150000000 | CRR | Swellendam Project Pipeline | Concept/Problem definition |  |  |  |  | Engineering Services – Electromechanical | W. Treurnicht J. Booysen J. Bester | 2035/36 | 2040 | Construction of a new bulk electricity intake substation at Suurbraak to replace the existing inadequate supply infrastructure and provide a reliable, correctly sized electricity supply point for the town. ¦ Suurbraak's current electricity supply infrastructure is aged and undersized. The existing supply cannot reliably meet current demand, let alone accommodate growth. A new intake substation is the foundation of any future electricity supply improvements in Suurbraak and is critical for service delivery and development. | Yes | 2026-05-12
22 | Swellendam Municipality | Overberg District | Solar/Battery/Bes/ Cap Banks System | Energy/Electricty | Swellendam Municipality | 255000000 | other | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Electromechanical | W. Treurnicht J. Booysen J. Bester | 2026/27 | 2030 | Installation of a solar generation, battery energy storage, capacitor bank and Building Energy System (BES) at key municipal facilities, creating a hybrid renewable energy system to reduce dependence on Eskom supply and improve energy resilience across the municipality. ¦ Given the severe electricity supply constraints in the Overberg District, the municipality must reduce its dependence on Eskom grid supply. A solar and battery system will reduce peak demand on the grid, lower electricity costs, improve supply reliability during load shedding, and demonstrate responsible energy management. It also positions the municipality to operate critical services independently of Eskom when necessary. | Yes | 2026-05-12
23 | Swellendam Municipality | Overberg District | Upgrade Railton Bulk Water Distribution and Reticulation | Water | Railton | 8000000 | CRR | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2025/26 | 2026 | Upgrading and extension of the bulk water distribution network in Railton, replacing ageing pipes and increasing reticulation capacity to meet current demand and enable new housing connections. ¦ The Railton water distribution network is inadequate for the current population and cannot support the planned housing development in the area. This upgrade is a direct enabler of new housing delivery and the formalisation of the informal settlement. | Yes | 2026-05-12
24 | Swellendam Municipality | Overberg District | Future Water Security Swellendam | Water | Swellendam | 600000000 | other | Swellendam Project Pipeline | Concept/Problem definition |  |  | High |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2035/36 | 2040 | Investigation, planning and ultimate implementation of a long-term bulk water source augmentation scheme for Swellendam, most likely the construction of an in-stream dam on the Buffeljags River, to provide a secure, long-term water supply for the town and surrounding areas. ¦ Swellendam's current water source — the Grootkloof dam system — has limited yield relative to the town's long-term growth trajectory. Without a new bulk water source, the municipality will face a hard ceiling on population growth and economic development. This is the most strategically important water infrastructure project for Swellendam's future. | Yes | 2026-05-12
25 | Swellendam Municipality | Overberg District | Buffelsjagrivier: Upgrade WTW and new reservoir | Water | Buffelsjagrivier | 25000000 | Other | Swellendam WSA Priority Project List | Concept/Problem definition | Conceptual |  | Priority 6 |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | Post2030 |  | Construction of a new Water Treatment Works and bulk water storage reservoir at Buffelsjagrivier to replace inadequate existing infrastructure and provide a reliable, compliant water supply to the community. ¦ Buffelsjagrivier's water supply infrastructure is inadequate. The existing system cannot reliably treat water for the community. This project is fundamental to achieving basic service delivery standards and enabling any future development. | Yes | 2026-05-12
26 | Swellendam Municipality | Overberg District | Suurbraak: Upgrade of Suurbraak water pipeline from weir to pumpstation | Water | Suurbraak | 5750000 | Other | Swellendam WSA Priority Project List | Concept/Problem definition | Conceptual |  | Priority 4 |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2028/29 |  | Upgrade of the raw water supply pipeline from the Suurbraak weir on the Buffeljagsrivier to the pump station, increasing the volume of raw water that can be abstracted and conveyed to the Water Treatment Works. ¦ The existing raw water pipeline limits how much water can be abstracted from the river, constraining the total volume of potable water that can be produced. This upgrade is essential to improve water security in Suurbraak and support reliable supply to the community. | Yes | 2026-05-12
27 | Swellendam Municipality | Overberg District | Swellendam: New Silo sewer pumpstation | Sanitation | Swellendam | 2800000 | Own-Muni | Swellendam WSA Priority Project List | Implementation | Construction |  | Priority 1 |  | Engineering Services – Water & Sanitation | W. Treurnicht J. Booysen J. Bester | 2025/26 | 2026 | Construction of a new sewer pump station at the Silo area of Swellendam to replace the existing failing pump station infrastructure and ensure reliable conveyance of wastewater from the lower town to the treatment works. ¦ The Silo pump station is a critical node in Swellendam's sewerage system. Failure of this pump station would result in sewage overflows affecting the surrounding area. Replacing it with a new, correctly sized pump station is essential for service continuity and public health. | No | 2026-05-12

## LG Witzenberg
No | Municipality | District | Project Name | Sector | Location / Area | Estimated Total Cost (R) | Source Document | Readiness Stage | Status / Progress | Key Blockages / Constraints | Support Required ( Sector Depts / SIDAFF) | Responsible Municipal Department | Responsible Municipal Official | Target Start Date | Target Completion Date | Comments / Notes | DLG Assistance Required | Last Update Date
| Witzenberg | Cape Winelands | 19.5MW Ceres Solar PV Plant with BESS | Electrical | Ceres | 200000000 | Electrical Master Plan | Design & Environmenatal Authorisation | Design | Unfunded | DLG, DMRE, Eskom | Electrical Services | Victor Dyusha | 2024/2025 | 2025/2026 | Procurement is pending funding. | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Additional 5MVA Capacity at Bon Chretien Substation | Electrical | Ceres | 83000000 | Electrical Master Plan | Design | Design | Unfunded | DLG, DMRE, Eskom | Electrical Services | Victor Dyusha | 2019/2020 | 2026/2027 | Procurement is pending funding. | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Additional 2MVA Capacity at Wolseley Substation | Electrical | Wolseley | 33200000 | Electrical Master Plan | Design | Design | Unfunded | DLG, DMRE, Eskom | Electrical Services | Victor Dyusha | 2019/2020 | 2026/2027 | Procurement is pending funding. | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replacement of Hazardous Electrical Network Components (Master Plan priorities) | Electrical | All towns | 5000000 | Electrical Master Plan | Design | Design | Unfunded | DLG, DMRE | Electrical Services | Victor Dyusha | 2019/2020 | 2026/2027 | Procurement is pending funding. | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Resurfacing of Municipal Roads - Tulbagh (CRR) | Roads and stormwater | Tulbagh | 4035038 | Road Assest Management Plan (RAMP, July 2025) | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2026/2027 | RAMP. Unfunded. | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Resurfacing of Municipal Roads - Tulbagh (MIG) | Roads and stormwater | Tulbagh | 12105113 | Road Assest Management Plan (RAMP, July 2025) | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2027/2028 | 2028/2029 | RAMP. Unfunded. | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Reconstruction of Municipal Roads - Tulbagh (CRR) | Roads and stormwater | Tulbagh | 41380502.625 | Road Assest Management Plan (RAMP, July 2025) | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2029/2030 | RAMP. Unfunded. | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Reconstruction of Municipal Roads - Tulbagh (MIG) | Roads and stormwater | Tulbagh | 4138050.2625 | Road Assest Management Plan (RAMP, July 2025) | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2023/2031 | 2030/2031 | RAMP. Unfunded. | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrading of Municipal Gravel Roads - Tulbagh (CRR) | Roads and stormwater | Tulbagh | 18891244.5 | Road Assest Management Plan (RAMP, July 2025) | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2028/2029 | RAMP. Unfunded. | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrading of Municipal Gravel Roads - Tulbagh (MIG) | Roads and stormwater | Tulbagh | 56673733.5 | Road Assest Management Plan (RAMP, July 2025) | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2029/2030 | 2031/2032 | RAMP. Unfunded. | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrading of Stormwater Pipeline, Obiqua Street | Roads and stormwater | Tulbagh | 779088.874 | Stormwater Master Plan | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Speed Calming | Roads and stormwater | All Wards | 3000000 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replacement of High Pressure drain jetting machine | Roads and stormwater | Ceres | 620000 |  | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2025/2026 | 2025/2026 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [14 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Crane Truck - Electrical - Replacement of existing | Electrical | All Wards | 2500000 |  | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2025/2026 | 2025/2026 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [14 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrading of Montpellier tot Tulbagh Wynkelders | Roads and stormwater | Tulbagh |  | MM E-mai .: Mon 2025/10/06 05:08 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2029/2030 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [14 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh Street and Stormwater & Park Section_Renovation of Building | Roads and stormwater | Tulbagh | 820000 | Zukiswa Zantsi <Zukiswa@witzenberg.gov.za> E-mail .: 2025/10/10 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Charl du Plessis / Elton Lintnaar | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Eating & toilet Facilities: Ceres Cleansing and Solid Waste | Cleansing and Solid Waste | Ceres | 500000 | Patricia Claasen <pclaasen@witzenberg.gov.za> E-mail Thu 2025/10/16 14:15 | Business Case | Budgeting | Unfunded | DLG | Cleansing and Solid Waste | Patricia Claasen | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrading of Street Lighting, Trichartstraat, Ceres | Electrical | Ceres |  | Ald. Dirk Swart. / David Nasson <david@witzenberg.gov.za>E-mail Wed 10/29/2025 5:38 AM | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh - Electrification of Informal Settlements - (1276 Stands) | [13 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh ASLA Camp- (1066 Stands) | Electrical | Tulbagh | 23665200 | Report Compiled by: V. Dyusha : Electro-technical Services Department (October 2025) | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh Die Gaatjie - (113 Stands) | Electrical | Tulbagh | 2508600 | Report Compiled by: V. Dyusha : Electro-technical Services Department (October 2025) | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh Kleinbegin - 997 Stands) | Electrical | Tulbagh | 2153400 | Report Compiled by: V. Dyusha : Electro-technical Services Department (October 2025) | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [14 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [14 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Bella Vista Community Hall - Resurfacing of Parking Area, | Roads and stormwater | Bella Vista | 458995.5725 | Bella Vista Community Hall - Resurfacing of Parking Area, compiled by Charl du Plessis , 27 November 2025 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [14 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Robot, by die Krige- en Voortrekkerstraat kruising | Roads and stormwater | Ceres | 700000 | Adri Fourie <gerrit4@jvanvuuren.co.za> On Behalf Of Gerrit van Vuuren, 2 Desember 2025 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [14 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Boorhole Pipeline Repairs - Ceres | Water and Sanitation | Ceres | 3000000 | Water Resilience Plan | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [14 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Aerator Replacement Programme for all WwTW | Water and Sanitation | Ceres | 600000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Aerator Replacement Programme for all WwTW | Water and Sanitation | Ceres | 800000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Improve safety and security at infrastructure sites, (fencing, alarms, cameras, 24hr response, etc.0 | Water and Sanitation |  | 3500000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New chlorine building and system for Op-die-Berg | Water and Sanitation | Op-Die-Berg | 3800000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Repairs of Prince Alfred Hamelet Reservoir roof | Water and Sanitation | Prince Albert Hamlet | 500000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Require purchasing of one vacuum truck (honey sucker) | Water and Sanitation | All Wards | 1000000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Require purchasing of two water tanker trucks | Water and Sanitation | All Wards | 3200000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Security Upgrades | Water and Sanitation | All Wards | 700000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrade of Ceres WwTW | Water and Sanitation | Ceres | 1400000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrade of components of Tulbagh WwTW | Water and Sanitation | Tulbagh | 2000000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrade of Op die Berg WwTW (from 0.3ML to 2ML) | Water and Sanitation | Op-Die-Berg | 6000000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrade of WwTWs | Water and Sanitation | All Wards | 600000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrading of Prince Alfred Hamlet Chlorine building and system | Water and Sanitation | Prince Albert Hamlet | 3800000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Wolseley: Refurbishment of WwTW (3 Phases) | Water and Sanitation | Wolseley | 0 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [5 empty] | Business Case | Budgeting | Unfunded | DLG, DWS |  |  | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Develop Groundwater Monitoring and Management Plans | Water and Sanitation |  | 0 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Op-die-Berg: Water allocation to Op-die-Berg needs to be increased | Water and Sanitation | Op-Die-Berg | 1000000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry and Scada monitoring for all Sewer Pump Stations | Water and Sanitation | All Wards | 1800000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry and Scada monitoring for all Water Pump Stations | Water and Sanitation | All Wards | 3000000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry and Scada monitoring for all Water Treatment Works |  | All Wards |  | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS |  |  | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | AC pipe replacement at Ceres, Prince Alfred Hamlet and Wolseley | Water and Sanitation | All Wards | 9000000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network, Water pipes and valve replacement: | Water and Sanitation | All Wards | 2000000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Sewer Network Replacement for all the towns | Water and Sanitation | All Wards | 1000000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Sewer Pumps Replacement | Water and Sanitation | All Wards | 300000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Toilets for Informal Settlements | Water and Sanitation | All Wards | 500000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands |  |  | All Wards |  |  | Business Case | Budgeting | Unfunded | DLG, DWS |  |  | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Develop and Implement Revenue Enhancement Strategy | Water and Sanitation | All Wards | 2500000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Develop and Implement Skills Development Policy (posts are filled, sufficient technical & support staff, training provided, reuired skills / qualifications, appropriate number of staff, etc. | Water and Sanitation | All Wards | 1200000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Establish processes and systems to manage water and sanitation services on farms and in rural areas (ensure SLAs are in place with farmers or Irrigation Boards) | Water and Sanitation | All Wards | 0 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Improve Blue Drop status and obtain Blue Drop certification (annual WTW Process Audits) | Water and Sanitation | All Wards | 0 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Improve Green Drop status and obtain Green Drop certification (annual WwTW Process Audits) | Water and Sanitation | All Wards | 0 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review and implement a comprehensive WCDM (with WCDM interventions) Plan & Strategy and update Strategy when necessary | Water and Sanitation | All Wards | 700000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review and Implement a Water Resilience Policy to improve water use efficiency | Water and Sanitation | All Wards | 1500000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review and implement Information Management Systems Plan that addresses IT business rewquirements, ensure adequate IT security exists with back-ups and sufficient staff and budget isavailable to keep IT Systems stable. | Water and Sanitation | All Wards | 0 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review and implement O&M Plans to improve the functional life of infrastructure - (operating manuals, maintenance schedules, tools, equipment, staff and funds). | Water and Sanitation | All Wards | 1500000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review and implement Water Safety Plans and review Plans when necessary | Water and Sanitation | All Wards | 1200000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review and update implementation of AC Pipe Replacement Programme | Water and Sanitation | All Wards | 10000000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review and update Infrastructure Asset Management Strategies and Plans and Asset Register (inclusive of technical water and sanitation asset register) | Water and Sanitation | All Wards | 4500000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review and update Sanitation Master Plan | Water and Sanitation | All Wards | 1000000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review and update Wastewater Risk Abatement Plans (W2RAP) | Water and Sanitation | All Wards | 1200000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review and update Water Master Plan | Water and Sanitation | All Wards | 1000000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review and update Water Services Infrastructure Maintenance and Rehabilitation Programme (Technical assessment of infrastructure) | Water and Sanitation | All Wards | 7500000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review Indigent Policy and update Indigent Register annually | Water and Sanitation | All Wards | 0 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Review WSDP annually and update document every 5 years (2023 - 2028) | Water and Sanitation | All Wards | 850000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Section 78: Investigate the process to be followed and deciding on an appropriate delivery mechanism to provide a municipal service within the Municipality - internal (in-house) or external (outsourced) delivery option (Review WSP arrangements) | Water and Sanitation | All Wards | 3500000 | 5 Year Water and Sanitation Reliability Service Delivery Implementation Plan, October 2025 | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2026/2027 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [14 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [14 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Water Master Plan June 2021 (Table WBW6.4b) | [13 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Ceres | [13 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Reinforcement to Main Supply zone (Groenplaatjie to Plantasie Street) | Water and Sanitation | Ceres | 10350000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 - 2025 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Reinforcements to Bella Vista network | Water and Sanitation | Bella Vista | 851000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2045 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Supply to new development areas | Water and Sanitation | Ceres | 3462000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 - 2040 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Ceres water demand management: Implement Ceres PRV 2 zone | Water and Sanitation | Ceres | 613000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Ceres pipe replacement & network reinforcement | Water and Sanitation | Ceres | 8003000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Ceres water demand management: Implement Ceres PRV 1 b zone | Water and Sanitation | Ceres | 2480000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Ceres water demand management: Implement Ceres PRV 3 zone | Water and Sanitation | Ceres | 424000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2040 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Nduli booster PS upgrade | Water and Sanitation | Nduli | 603000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 - 2030 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New Bella Vista booster pumping station | Water and Sanitation | Bella Vista | 649000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Additional storage capacity for Ceres (Can be phased) | Water and Sanitation | Ceres | 36323000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Additional reservoir storage for Bella Vista | Water and Sanitation | Bella Vista | 8294000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2045 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrade of bulk supply to Bella Vista | Water and Sanitation | Bella Vista | 10057000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrade of bulk supply to Nduli | Water and Sanitation | Nduli | 3916000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Reinforcement to Main Supply zone (R303 Road to R46 Road) | Water and Sanitation | Ceres | 6967000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 - 2040 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Additional reservoir storage for Nduli | Water and Sanitation | Nduli | 8294000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2045 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry | Water and Sanitation | Ceres | 950000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh | Water and Sanitation |  |  | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Development related items for Tulbagh Upper reservoir zone | Water and Sanitation | Tulbagh | 3571000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 - 2035 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for Tulbagh Lower reservoir zone | Water and Sanitation | Tulbagh | 1174000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 - 2045 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Development related items for Tulbagh Lower reservoir zone | Water and Sanitation | Tulbagh | 5596000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 - 2030 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades when FDA TB18 develops | Water and Sanitation | Tulbagh | 1973000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 - 2030 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Rezoning and network upgrades for Tulbagh Upper reservoir zone (After project WTW-B01 is implemented) | Water and Sanitation | Tulbagh | 2996000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 - 2045 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New Tulbagh Upper reservoir, pumping station & supply pipes | Water and Sanitation | Tulbagh | 30806000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 - 2025 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New Tulbagh Very High reservoir, PS & supply pipes | Water and Sanitation | Tulbagh | 5957000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2030 - 2035 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Additional storage capacity for Tulbagh Lower reservoir zone and supply pipes | Water and Sanitation | Tulbagh | 12410000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry | Water and Sanitation | Tulbagh | 550000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Water Treatment Works | Water and Sanitation | Tulbagh | 65000000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2027 - 2029 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Prince Alfred Hamlet | Water and Sanitation | Prince Alfred Hamlet |  | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Implement PAH Upper reservoir zone (After project WPW-B01 is implemented) | Water and Sanitation | Prince Alfred Hamlet | 1435000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 - 2030 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Reinforce network of the PAH Upper reservoir zone | Water and Sanitation | Prince Alfred Hamlet | 304000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Reinforce network of the PAH Lower reservoir zone | Water and Sanitation | Prince Alfred Hamlet | 3256000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2030 - 2040 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Supply to developments in PAH Upper reservoir zone | Water and Sanitation | Prince Alfred Hamlet | 475000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Supply to developments in PAH Lower reservoir zone | Water and Sanitation | Prince Alfred Hamlet | 506000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2040 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New PAH Upper reservoir, pumping station & supply pipe | Water and Sanitation | Prince Alfred Hamlet | 19984000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry | Water and Sanitation | Prince Alfred Hamlet | 500000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Op-Die_Berg | Water and Sanitation | Op-Die_Berg |  | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Reinforce existing ODB water network | Water and Sanitation | Op-Die_Berg | 795000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Additional reservoir storage for Fontein zone | Water and Sanitation | Op-Die_Berg | 1601000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2030 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Additional reservoir storage for Odendaal zone | Water and Sanitation | Op-Die_Berg | 3321000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry | Water and Sanitation | Op-Die_Berg | 300000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Wolseley | Water and Sanitation | Wolseley |  | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Rezoning and network upgrades for Cerespad reservoir zone | Water and Sanitation | Wolseley | 1058000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Stamper Street network upgrades for improved conveyance (Phase 1) | Water and Sanitation | Wolseley | 144000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Development related items for Stamperstraat reservoir zone | Water and Sanitation | Wolseley | 1733000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 - 2045 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Development related upgrades for Cerespad reservoir zone | Water and Sanitation | Wolseley | 781000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2040 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Stamper Street network upgrades for improved conveyance (Phase 2) | Water and Sanitation | Wolseley | 1704000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2045 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Reinforce feeder main to Stamper Street reservoir | Water and Sanitation | Wolseley | 2195000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrade Pine Valley booster pumping station | Water and Sanitation | Wolseley | 435000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2030 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry | Water and Sanitation | Wolseley | 400000 | Water Master Plan June 2021 (Table WBW6.4b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Sewer Master Plan June 2021 (Table WBS6.5b) | Water and Sanitation |  |  |  | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Ceres | Water and Sanitation | Ceres |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for PS 5 catchment | Water and Sanitation | Ceres | 743000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for PS 4 catchment: Phase 1 | Water and Sanitation | Ceres | 2663000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for PS 4 catchment: Phase 4 (Along railway for Vos St to Voortrekker Rd) | Water and Sanitation | Ceres | 3000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2030 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for PS 3 catchment | Water and Sanitation | Ceres | 2462000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New collector sewer for Vredebes development | Water and Sanitation | Ceres | 880000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Infrastructure required for Golf Estate development | Water and Sanitation | Ceres |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Investigate system layout: Route of rising mains | Water and Sanitation | Ceres |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New pumping station and rising main for future area CE10 | Water and Sanitation | Ceres |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2035 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New pumping station and rising main for future area CE12 | Water and Sanitation | Ceres |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2035 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for PS 4 catchment: Phase 6 (Bella Vista, Panorama to Viceland St) | Water and Sanitation | Bella Vista | 7279000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2040 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for PS 4 catchment: Phase 7 (Bella Vista to Ceres) | Water and Sanitation | Bella Vista | 5353000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2045 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for PS 2 catchment | Water and Sanitation | Ceres | 1103000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2045 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for PS 4 catchment: Phase 2 (Cilliers & St Paul Streets) | Water and Sanitation | Ceres | 2867000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Re-route rising main of PS1 | Water and Sanitation | Ceres | 574000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for PS 4 catchment: Phase 3 (Bella Vista, Buiten Street) | Water and Sanitation | Bella Vista | 793000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for PS 4 catchment: Phase 5 (PS & rising main upgrade) | Water and Sanitation | Bella Vista | 15891000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2035 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry | Water and Sanitation | Ceres | 750000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh | Water and Sanitation | Tulbagh |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for Tulbagh PS 1 Catchment | Water and Sanitation | Tulbagh | 2522000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 - 2035 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrade rising main of Tulbagh PS 1 | Water and Sanitation | Tulbagh | 1973000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Infrastructure for when FDA's TB15 - TB17 develop | Water and Sanitation | Tulbagh | 6221000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New outfall sewer and upgrade to pumping station and rising main | Water and Sanitation | Tulbagh | 5957000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 - 2035 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New pumping station and rising main (Future PS T2) | Water and Sanitation | Tulbagh |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2030 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New pumping station, rising main and collector sewer (Industrial area) | Water and Sanitation | Tulbagh | 4001000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2030 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New pumping station and rising main (Future PS T3) | Water and Sanitation | Tulbagh |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2040 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry | Water and Sanitation | Tulbagh | 400000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Waste Water Treatment Works (WwTW) | Water and Sanitation | Tulbagh | 50000000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2028 - 2031 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Prince Alfred Hamlet | Water and Sanitation | Prince Alfred Hamlet |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Sanitation system for unserviced erven in Prince Alfred Hamlet (Phase 1) | Water and Sanitation | Prince Alfred Hamlet | 12636000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2024 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Investigate route of main outfall sewer | Water and Sanitation | Prince Alfred Hamlet | 6000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for PAH PS 2 catchment | Water and Sanitation | Prince Alfred Hamlet | 2802000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrade pumping stations | Water and Sanitation | Prince Alfred Hamlet | 1590000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2040 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Sanitation system for unserviced erven in Prince Alfred Hamlet (Phase 2) | Water and Sanitation | Prince Alfred Hamlet | 13453000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry | Water and Sanitation | Prince Alfred Hamlet | 150000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Op-Die_Berg | Water and Sanitation | Op-Die_Berg |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Sanitation system for unserviced erven in Op die Berg | Water and Sanitation | Op-Die_Berg | 3047000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry | Water and Sanitation | Op-Die_Berg | 150000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Wolseley | Water and Sanitation | Wolseley |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for Pine Valley PS catchment: (Phase 1 Afrika Street) | Water and Sanitation | Wolseley | 1372000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrade existing Pine Valley PS and rising main | Water and Sanitation | Wolseley | 2334000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2030 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network & PS upgrades for Ramanstraat catchment | Water and Sanitation | Wolseley | 1618000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for Swanebergpark PS2 catchment | Water and Sanitation | Wolseley | 417000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New pumping station and rising main for FDA WO1 | Water and Sanitation | Wolseley |  | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Investigate pumping station capacity and rising main diameter | Water and Sanitation | Wolseley | 1355000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2022 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Network upgrades for Pine Valley PS catchment (Phase 2) | Water and Sanitation | Wolseley | 2882000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs | 2025 - 2045 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Telemetry | Water and Sanitation | Wolseley | 400000 | Sewer Master Plan June 2021 (Table WBS6.5b) | Business Case | Budgeting | Unfunded | DLG, DWS | Water and Sanitation | Nathan Jacobs |  | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | [5 empty] | Business Case | [8 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | TRANSPORT PLAN FOR CERES CBD, WITZENBERG MUNICIPALITY |  |  |  | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | [8 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Sidewalk (including cycling path) along Voortrekker Road (both sides) between Nduli and Ceres CBD, 2,5km | Roads and stormwater | Ceres | 18060129 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Intersection upgrade of Nduli access on Voortrekker Road | Roads and stormwater | Ceres | 4374600 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Sidewalk widening along Voortrekker Road between Cilliers Street and Munnik Street, Inclusding brick paving of Voortrekker and de vos Intersection | Roads and stormwater | Ceres | 4228145 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Sidewalk widening along Vos Street between Orange and Voortrekker Street | Roads and stormwater | Ceres | 869400 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Improvements along Vos Street between Orange and Voortrekker Street | Roads and stormwater | Ceres | 279036 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Improvements along Pretorius Street between Muunik Street and Fabrick Street | Roads and stormwater | Ceres | 817650 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New taxi facility at the corner of Vos and Orange Street (excluding purchase price of property | Roads and stormwater | Ceres | 4776180 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Signalisation of Vos and Orange Street, including brick paving of intersection | Roads and stormwater | Ceres | 169800 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Intersection upgrade of Bella Vista intersection on Vos Street | Roads and stormwater | Ceres | 4374600 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Universal access upgrades at various intersections | Roads and stormwater | Ceres | 1035000 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Landscaping improvements to existing parking area | Roads and stormwater | Ceres | 276000 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Improvements to existing taxi rank in Voortrekker Street | Roads and stormwater | Ceres | 1380000 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Brick paving of Voortrekker Road between Retief and Bon Chretien | Roads and stormwater | Ceres | 2456400 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Brick paving of Voortrekker Road/Cilliers Street intersection | Roads and stormwater | Ceres | 1159200 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Optimization of signal plans for Voortrekker/Owen Intersection | Roads and stormwater | Ceres | 70000 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Converting existing pedestrian crossing at Voortrekker/Krige intersection to a signalised crossing | Roads and stormwater | Ceres | 210000 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2031/2032 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replace low water structure with bridge @ Hugo and Pretotius Streets | Roads and stormwater | Ceres | 40000000 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar |  | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands |  | Roads and stormwater | Tulbagh |  | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh CBD Main Road Upgrading (Civils and Landscaping) | Roads and stormwater | Tulbagh | 7191122 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2030/2031 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh New bridge crossing Dwars River tributary | Roads and stormwater | Tulbagh | 19000000 | Witzenberg Municipality: Roads Master Plan, June 2020 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2030/2031 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New bridge connecting Retief Street to New Eastern Development as per SDF | Roads and stormwater | Tulbagh | 31000000 |  | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2030/2031 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Stormwater System Replacement Capital Cost Estimate - Ceres | Roads and stormwater | Ceres | 96743535 | Witzenberg Municipality: Stormwater Master Plan, 2019 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Stormwater System Replacement Capital Cost Estimate - Bella Vista | Roads and stormwater | Bella Vista | 43429305 | Witzenberg Municipality: Stormwater Master Plan, 2019 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Stormwater System Replacement Capital Cost Estimate - Nduli | Roads and stormwater | Nduli | 7990570 | Witzenberg Municipality: Stormwater Master Plan, 2019 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Stormwater System Replacement Capital Cost Estimate - Wolseley | Roads and stormwater | Wolseley | 14783132 | Witzenberg Municipality: Stormwater Master Plan, 2019 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Stormwater System Replacement Capital Cost Estimate - Op-die-Berg | Roads and stormwater | Op-Die_Berg | 2462942 | Witzenberg Municipality: Stormwater Master Plan, 2019 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh - Stormwater Pipe Minor System Upgrades | Roads and stormwater | Tulbagh | 10000000 | Tulbagh : Stormwater Master Plan, 2014 | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2026/2027 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh - Affordable Housing Development (1300 Sites) |  |  |  |  | Business Case | Budgeting | Unfunded | DLG | [5 empty] | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh - Affordable Housing Development (1300 Sites) - Water | Water and Sanitation | Tulbagh | 30358900 | Housing Pipeline | Business Case | Budgeting | Unfunded | DLG | Water and Sanitation | Nathan Jacobs | 2028/2029 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh - Affordable Housing Development (1300 Sites) - Sewer | Water and Sanitation | Tulbagh | 35716200 | Housing Pipeline | Business Case | Budgeting | Unfunded | DLG | Water and Sanitation | Nathan Jacobs | 2028/2029 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh - Affordable Housing Development (1300 Sites) - Roads | Roads and stormwater | Tulbagh | 16965000 | Housing Pipeline | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2028/2029 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh - Affordable Housing Development (1300 Sites) - Stormwater | Roads and stormwater | Tulbagh | 6250400 | Housing Pipeline | Business Case | Budgeting | Unfunded | DLG | Roads and stormwater | Elton Lintnaar | 2028/2029 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh - Affordable Housing Development (1300 Sites) - Electricity | Electrical | Tulbagh | 4865900 | Housing Pipeline | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2028/2029 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh - Affordable Housing Development (1300 Sites) - Amenities | Amenities | Tulbagh | 50000000 | Housing Pipeline | Business Case | Budgeting | Unfunded | DLG | Amenities |  | 2028/2029 | 2031/2032 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh - Affordable Housing Development (1300 Sites) - Acquisition of Land (100 ha) | Human Settlement | Tulbagh | 10000000 | Housing Pipeline | Business Case | Budgeting | Unfunded | DLG | Human Settlement |  | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Electrical | Electrical | Ceres |  |  | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical |  |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replace the existing 11kV circuit breakers in De Bos Switching Station with 8 x new 11kV circuit breakers and a bus-coupler. The new circuit breakers shall be indoor type with 1 250A bus-bar rating and feeder rating at least 800A each. Also install new 300mm2 11kV PILC type cables between Bon Chretien and De Bos Switching Stations | Electrical | Ceres | 7000000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Install new 11kV overhead line with CHICADEE conductors between Bon Chretien Switching Station and the T-off point to TRF Palmyra 1 on the Eselfontein overhead line, and install new RMU Palmyra with 4 x circuit breakers, connected onto the overhead lines with 185mm2 PILC type cables. All new intermediate insulators to be 22kV Class A post-top type, and strain insulators of the 31mm/kV silicon rubber type, all installed on A-frames | Electrical | Ceres | 3200000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replace the existing 11kV circuit breakers in Lyell Switching Station with 6 x new 11kV circuit breakers and a bus-coupler. The new circuit breakers shall be indoor type with 1250A bus-bar rating and feeder rating at least 800A each. | Electrical | Ceres | 2800000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replace the existing 70mm2 cable sections on the “Bon Chretien Farms/Eselfontein” feeder with new 185mm2 PILC type cables. Also replace all conductors smaller than HARE with HARE, install new insulators and A-frames. All new intermediate insulators to be Class A post-top type, and strain insulators of the 31mm/kV silicon rubber type | Electrical | Ceres | 620000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replace the existing 70mm2 cable between Bon Chretien Switching Station and the “Calvinia Road” overhead line feeder with a new 185mm2 PILC type cable | Electrical | Ceres | 1700000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Do pole audit on all poles forming part of the existing 11kV overhead lines and replace poles that are unsafe. At the same time reconductor all overhead lines smaller than HARE with HARE conductors and install new 22kV insulators on A-frames. All new intermediate insulators to be Class A post-top type, and strain insulators of the 31mm/kV silicon rubber type. | Electrical | Ceres | 300000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Install pole mounted auto reclosers on the positions in the overhead networks as indicated on the “future” single line diagram included in Annexure G. | Electrical | Ceres | 1200000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Install pole mounted earth fault indicators on the positions in the overhead networks as indicated on the “future” single line diagram included in Annexure G. | Electrical | Ceres | 150000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replacement of existing old oil type ring main units with new SF6 or vacuum circuit breakers, with minimum 400A rating | Electrical | Ceres | 1750000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replacement of miniature substations that are equipped with oil type ring main units, or that are at the end of their useful life, with new safer units. | Electrical | Ceres | 2100000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | It is recommended that a new labelling methodology of all equipment, based on street names and as shown on the 11kV single line diagram, be adopted and implemented. Apart from the normal identification purposes, correct labelling and logical names for equipment and infrastructure is vital to ensure correct and safe switching operations. | Electrical | Ceres | 80000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Internal services and streetlighting for Vredebes low cost housing project | Electrical | Ceres | 34000000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | SCADA systems for Switching Stations in Ceres | Electrical | Ceres | 750000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Power factor correction and PV plant installation investigation | Electrical | Ceres | 180000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrading of cables between Eskom and Bon Chretien Switching Station | Electrical | Ceres | 2600000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2030/2031 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New 2 x 40MVA 66/11kV substation and link line to Eskom | Electrical | Ceres | 65000000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2030/2031 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | TULBAGH | Electrical | Tulbagh |  | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Install new 185mm2 copper PILC type cable between Eskom Substation and Tulbagh main Switching and install 6 x new 11kV circuit breakers and bus-coupler in Tulbagh Main Switching Station, indoor type with 1250A bus-bar rating and feeder rating at least 800A. | Electrical | Tulbagh | 6500000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Disconnect 70mm² PILC cable between MS WWTW and RMU WWTW from RMU WWTW and extend cable to new 11kV circuit breaker in Tulbagh Main Switching Station. | Electrical | Tulbagh | 100000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Remove SS Marais and RMU Miller and replace with new brickbuild switching station with 5 x indoor circuit breakers with minimum 800A rating each and a bus-coupler. Also install new 95mm² 11kV PILC cable between new RMU Marais and overhead line in Muller Street. | Electrical | Tulbagh | 3500000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Install new 95mm2 11kV cable between new RMU Marais and the municipal main switching station and connect onto the new 11kV circuit breaker panel in main switching station. | Electrical | Tulbagh | 1600000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Install overhead link line between existing overhead lines in Olifant and Kasuur streets, in order to have the pole mounted transformers on the existing radial lines on a ringfeed | Electrical | Tulbagh | 250000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Installation of new circuit breaker panels in Stasieweg switching station (5 x breakers). Panels to have minimum 1250A busbar rating, and breakers to have minimum rating of 800A each. | Electrical | Tulbagh | 2600000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Disconnect MS Eerstelaan from cable feeding from Malherbe RMU, and install new 35mm2 11kV PILC type cable from MS Eerstelaan to existing cable in Obiqua street. In Obiqua street, cut the existing cable and make MS Eerstelaan part of the Obiqua street 35mm2 ring | Electrical | Tulbagh | 200000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Install external and internal services for low cost housing project on erf 1366 & 1435 – 1443 (225 houses) | Electrical | Tulbagh | 4000000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Upgrading of the network in order to supply the Tulbagh Lifestyle Village, including the removal of the existing RMU Digby, the installation of a new ring main unit with 4 circuit breakers, and the installation of the first portion of a secondary 95mm² 11kV PILC type cable ring. | Electrical | Tulbagh | 3000000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2027/2028 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replacement of existing old oil type ring main units with new SF6 or vacuum circuit breakers, with minimum 630A rating | Electrical | Tulbagh | 2100000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replacement of miniature substations that are equipped with oil type ring main units, or that are at the end of their useful life, with new safer units. | Electrical | Tulbagh | 2900000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New 66kV line and 20MVA 66/11kVA substation. | Electrical | Tulbagh | 0 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | It is recommended that the web-based Scada System recently installed elsewhere in the Witzenberg electricity networks be expanded to include a monitoring system in Tulbagh Main and Stasieweg Switching Stations as well. | Electrical | Tulbagh | 500000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | With time it is recommended that all 35mm² Cu, FOX and RABBIT overhead lines be replaced with HARE conductors, and new 22kV insulators and A-frames installed. Insulators to be class A post top type for intermediate, and 31mm/kV silicon rubber type for strain | Electrical | Tulbagh | 500000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2027/2028 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Re-conductoring of all 35mm² Cu, FOX and RABBIT overhead lines with HARE conductors, and installation of new 22kV insulators and A-frames as necessary. All new intermediate insulators to be Class A post-top type, and strain insulators of the 31mm/kV silicon rubber type. | Electrical | Tulbagh | 500000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2027/2028 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replace third avenue MS | Electrical | Tulbagh | 850000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Power factor correction and PV plant installation investigation | Electrical |  | 180000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha |  | 2027/2028 |  | Long term financial plan | 2026-04-09
|  |  | WOLSELEY | Electrical | Wolseley |  | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Installation of an alternative supply to Wolfpack metering point | Electrical | Wolseley | 50000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replacement of existing old oil type ring main units with new SF6 or vacuum circuit breakers, with minimum 630A rating | Electrical | Wolseley | 1650000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replacement of miniature substations that are equipped with oil type ring main units, or that are at the end of their useful life, with new safer units | Electrical | Wolseley | 3600000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Re-conductoring of the existing 11kV overhead line between RMU Montana and the T-off point to RMU Sports Field with HARE conductor, as well as installation of new insulators and A-frames. Also included in this work is the replacement of the existing 16mm2 cable from RMU Montana to the overhead line with new 95mm2 PILC type | Electrical | Wolseley | 750000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Re-conductoring of the existing overhead line between RMU DIF and the Wolfpack metering point with HARE conductor, as well as installation of new insulators and A-frames. | Electrical | Wolseley | 250000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Re-conductoring of all 16mm² overhead lines with HARE conductors, and installation of new 22kV insulators and A-frames. All new intermediate insulators to be Class A post-top type, and strain insulators of the 31mm/kV silicon rubber type. | Electrical | Wolseley | 650000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2030/2031 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Change network at Wolfpack meter point such that the municipal and private networks are adequately separated. A new pole at least 10m from the municipal pole is recommended. This private pole, cable and line must be clearly marked “PRIVATE”. | Electrical | Wolseley | 50000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | It is recommended that a new labelling methodology of all equipment, based on street names and as shown on the 11kV single line diagram, be adopted and implemented. Apart from the normal identification purposes, correct labelling and logical names for equipment and infrastructure is vital to ensure correct and safe switching operations. | Electrical | Wolseley | 80000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | SCADA system for Main SS | Electrical | Wolseley | 250000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Power factor correction and PV plant installation investigation | Electrical | Wolseley | 180000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replacement of overhead line between Main SS and RMU Mill with new 95mm2 cable | Electrical | Wolseley | 450000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Installation of an alternative supply to Wolfpack | Electrical | Wolseley | 750000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replacement of all 16mm2 sections of cable with new 95mm2 cable | Electrical | Wolseley | 600000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2027/2028 | 2029/2030 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Bulk works for Goedgevonden Development (Municipal cost) | Electrical | Wolseley | 1200000 | Electrical Master Plan | Business Case | Budgeting | Unfunded | DLG, DMRE | Electrical | Victor Dyusha | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands |  | Municipal Fleet |  |  |  | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Replacement of Municipal Fleet | Municipal Fleet |  |  |  | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Nissan UD 90 Compactor (Single axle 7 ton), CT2315, Model 2006 / 19 | Municipal Fleet | All Wards | 2184000 | High mileage Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Nissan UD 90 Compactor (Single axle 7 ton), CT6608, Model 2006 / 19 | Municipal Fleet | All Wards | 2184000 | High mileage Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Nissan UD 90 Compactor (Single axle 7 ton), CT15506, Model 2008 / 17 | Municipal Fleet | All Wards | 2184000 | High mileage Past economic life. | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Nissan UD 90 Compactor (Single axle 7 ton), CT14536, Model 2008 / 17 | Municipal Fleet | All Wards | 2184000 | High mileage Past economic life. | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tata LPK 713 4 ton Tipper Refuse cage, CT10625, Model 2009 / 16 | Municipal Fleet | All Wards | 928740 | High mileage Past economic life, bad ergonomics redundant mechanical and ergonomics design long abandoned by Euro and Japanese manufactures long ago is copied. | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Mitsubishi Canter 4 ton Tipper Refuse cage, CT4266, Model 1992 / 33 | Municipal Fleet | All Wards | 928740 | High mileage Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Nissan UD40 4 ton Tipper Refuse cage, CT8399, Model 2002 / 24 | Municipal Fleet | All Wards | 928740 | High mileage Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Nissan UD40 4 ton Tipper Refuse cage, CT 7914, Model 2005/21 | Municipal Fleet | All Wards | 928740 | High mileage Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Hino 300 4 ton Tipper Refuse cage, CT17470, Model 2009 / 16 | Municipal Fleet | All Wards | 928740 | Mileage > 400 000km | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Hino 300 4 ton Tipper Refuse cage, CT17471, Model 2009 / 16 | Municipal Fleet | All Wards | 928740 | Mileage > 400 000km | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Nissan CM14 7 ton Tipper construction, CT5601, Model 1990 / 35 | Municipal Fleet | All Wards | 1342740 | Mileage, Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Nissan UD 90 7 Ton Lift-on Skip Loader Truck, with extendable arms, CT5842, Model 2010/15 | Municipal Fleet | All Wards | 1276500 | Mileage, Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Nissan UD 90 7 Ton Lift-on Skip Loader Truck, with extendable arms, CT10895, Model 2010/15 | Municipal Fleet | All Wards | 1276500 | Mileage, Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | CASE Front End Loader bucket cap1.4m³ , CT17514, Model 1985 / 40 | Municipal Fleet | All Wards | 1180408.5151 | Past economic life, parts availability & outdated. | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Opel Corsa LDV0,7 Ton LCV, CT16845, Model 2009 / 17 | Municipal Fleet | All Wards | 436094.4726 | Mileage 200 000km +; Parts availability General Motors withdrew from South Africa | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Opel Corsa LDV0,7 Ton LCV, CT11346, Model 2009 / 17 | Municipal Fleet | All Wards | 436094.4726 | Mileage 200 000km +; Parts availability General Motors withdrew from South Africa | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Isuzu KB 200I Fleetside 1 Ton LCV, CT8539, Model 2011/14 | Municipal Fleet | All Wards | 436094.4726 | Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Isuzu KB 200I Fleetside 1 Ton LCV, CT8536, Model 2011/14 | Municipal Fleet | All Wards | 436094.4726 | Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Toyota Hilux 2.0 Bakkie 1 Ton LCV, CT17265, Model 2009/16 | Municipal Fleet | All Wards | 436094.4726 | Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Toyota Hilux 1 Ton LCV, CT5275, Model 1999 / 26 | Municipal Fleet | All Wards | 436094.4726 | Past economic life / bad ergonomics by today standards, | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Toyota Hilux1 Ton LCV, CT5278, Model 1999 / 26 | Municipal Fleet | All Wards | 436094.4726 | Past economic life / bad ergonomics by today standards, | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Ford Courier 1800 LWB1 Ton LCV, CT6452, Model 1990 / 35 | Municipal Fleet | All Wards | 436094.4726 | Past economic life / bad ergonomics by today standards, | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2027/2028 | 2027/2028 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Toyota Hilux 1.81 Ton LCV, CT5277, Model 1999 / 26 | Municipal Fleet | All Wards | 436094.4726 | Mileage, Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2028/2029 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Chevrolet Aveo 1.64 door sedan, CT5552, Model 2010 / 15 | Municipal Fleet | All Wards | 387685.2 | Mileage 200 000km +; Parts availability General Motors withdrew from South Africa | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2028/2029 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Chevrolet Aveo 1.6 4 door sedan, CT5749, Model 2011 / 14 | Municipal Fleet | All Wards | 387685.2 | Mileage 200 000km +; Parts availability General Motors withdrew from South Africa | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2028/2029 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Chevrolet Aveo 1.6 4 door sedan, CT8535, Model 2011 / 14 | Municipal Fleet | All Wards | 387685.2 | Mileage 200 000km +; Parts availability General Motors withdrew from South Africa | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2028/2029 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Chevrolet Spark 1.2 5 door hatch back, CT5261, Model 2010 /15 | Municipal Fleet | All Wards | 277960.98 | Mileage 200 000km +; Parts availability General Motors withdrew from South Africa | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2028/2029 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Chevrolet Spark 1.2 5 door hatch back, CT5258, Model 2010 /15 | Municipal Fleet | All Wards | 277960.98 | Mileage 200 000km +; Parts availability General Motors withdrew from South Africa | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2028/2029 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Toyota Fortuner 4.0 V6Luxury SUV, WTZN 001 WP, Model 2010 /15 | Municipal Fleet | All Wards | 945381.2756 | High mileage, Past economic life | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2028/2029 | 2028/2029 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New Municipal Fleet | Municipal Fleet |  |  |  | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene |  |  |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New Plant 4 ton Tipper Refuse cage, CT tba, Newplant | Municipal Fleet | All Wards | 928740 |  | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New Plant6 Ton Crane truck, CT tba, Newplant | Municipal Fleet | All Wards | 1342740 |  | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | New plant 7 ton Tipper construction, CT tba, New plant | Municipal Fleet | All Wards | 1342740 |  | Business Case | Budgeting | Unfunded | DLG | Municipal Fleet | Oswald Gatyene | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09
| Witzenberg | Cape Winelands | Tulbagh CBD_Refuse Bins:I10, Double Baboon-proof Bin in Brown | Cleansing and Solid Waste | Tulbagh | 150000 | manager@tulbaghhotel.co.za, Dated 17 March 2026 | Business Case | Budgeting | Unfunded | DLG | Cleansing and Solid Waste | Patricia Claasen | 2026/2027 | 2026/2027 |  | Long term financial plan | 2026-04-09